## Sheet1
MPPE Action Item List Ver. 2.86 (11 November, 2016)
No. | Action Item | name | Due Date | Status | open/close | closed date | note | MEA | MIA | MSA | HEP | ENA
161111-1 | MPPE will request User HK every 10/20minutes.(In case of emergency or special events higher rate is necessary.) | ISAS | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-2 | LPP will send MSA’s Count Mapping explanation to IRAP. IRAP will propose how to define Variable Attribute for angle mapping mode data. | LPP/IRAP | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-3 | ISAS will ask Markus-san the definition of “CDF CHARACTER Unix Time” and if it is usueful / necessary. | ISAS | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-4 | ISAS will ask Bijorn-san what is the output timing of MSA’s “TI4bytes+2bytes(time elapsed since last sun pulse)” in mission packet. | ISAS | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-5 | ISAS will CHECK the definition of TI +2bytes described on the design document and send the documents to all the team. | ISAS | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-6 | Level0 data format will be decided by negotiation between ISAS/IRAP/LPP. | ISAS/IRAP/LPP | 2017-12-31 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-7 | ISAS will ask SWT tutorial coordinator not to consider MPPE as a single instrument team but as a large instrument consortium. At least ~ One Hour is necessary. | ISAS | 2017-06-02 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
161111-8 | ISAS will inform MMO project that MEA will upload revised sensitivity table to MDP at the similar time when MSA CPU program and MIA velocity moment calculation table are uploaded. MEA will also upload HV table to MEA’s RAM at the time of testing unsent commands. | ISAS | 2016-11-30 |  | open |  |  | N.A. | N.A. | N.A. | N.A. | N.A.
160923-1 | Consider if Level 1 product of “burst trigger data” regenerated from L-mode data is necessary or not. | S. Yokota | 2016-11-30 |  | close | 2016-11-10 | 20160923: [A/I #4 20160923 MMO-SWG] 20161110: burst trigger data cannot be re-generated from only L-mode data (M-mode data are necessary to re-generate. | close | close | close | N.A. | N.A.
160923-2 | Submit the data product list. | MPPE team | 2016-10-31 |  | open |  | 20160923: [A/I #9 20160923 MMO-SWG] MMO Project will provide format file. | open | open | open | open | open
160923-2 | Select the MMO-MPO coordination UCs to be discussed in the next HEWG and inform it to G. Murakami and A. Milillo | MPPE team | 2016-09-30 |  | close | 2016-10-31 | 20160923: [A/I #11 20160923 MMO-SWG] 20161031: UC 17 and 18 | close | close | close | close | close
160923-3 | Discuss the MMO-MPO coordination UCs with counterparts of MPO PI group | MPPE team | 2016-11-07 |  | close | 2016-10-31 | 20160923: [A/I #12 20160923 MMO-SWG] 20161031: UC 17 and 18 will be discussed @ HEWG 7-8 November | close | close | close | close | close
160923-4 | Provide MMO project the updated sequences for NECP | Y. Saito | 2016-09-30 |  | close | 2016-09-29 | 20160923: [A/I #22 20160923 MMO-SWG] 20160929:submitted the updated time table | close | close | close | N.A. | N.A.
160923-5 | Provide MMO project the summary of MPPE software/table updating plan | Y. Saito | 2016-10-14 |  | open |  | 20160923: [A/I #23 20160923 MMO-SWG] | N.A. | open | open | N.A. | N.A.
160519-1 | Bruno-san will make draft Level1 CDF skelton file and send it to MIA, and MEA teams. | Bruno | 2016-08-31 |  | close | 2016-11-11 |  | N.A. | N.A. | close | N.A. | N.A.
160519-2 | MPPE’s Science Target Document@proposal will be revised. ISAS will initiate the revision process. Revision should be finished by next MPPE tutorial @ SWT Italy autumn 2017. | ISAS | 2016-07-31 |  | open |  | 20161111: The output of the young scientists’ activity will be included as a part of this document. Nishino-san is participating to this activity from MPPE. | N.A. | N.A. | N.A. | N.A. | N.A.
160519-3 | MPPE data -> CDPP@IRAP will be considered @SWG meeting in fall 2016 | ISAS | 2016-09-30 |  | close | 2016-09-23 | 20160831: MMO SWG will be held on 23 September 2016 20160923: ”MPPE/LEP data will be also included in AMDA” (minutes of MMO/SWG 20160923) | N.A. | N.A. | N.A. | N.A. | N.A.
150911-1 | MSA team will send ISAS the information about 2 MSA macro-commands and commands to change to / recover from table-E mode. | MSA team | 2015-12-31 |  | close | 2016-05-19 | 20160519:Current Mactro Command is OK. For this only two commands are necessary. | N.A. | N.A. | close | N.A. | N.A.
150911-2 | ISAS will start talking with SERENA team in order to mutually understand the operation / data mode. | ISAS | 2015-10-31 |  | close | 2016-01-21 | 20160121:MPPE has started talking SERENA at HEWG meeting @ Rovaniemi (submitted data/operation information with other instruments on MMO) | N.A. | N.A. | N.A. | N.A. | N.A.
150911-3 | MEA team will circulate MMS CDF format specification document to MSA(LPP), MIA(ISAS). | MEA team | 2015-09-30 |  | close | 2016-05-19 | 20160519:each team has the document | N.A. | N.A. | N.A. | N.A. | N.A.
150911-4 | Based on the information (two files concerning the requirements to be compatible with PDS4.0; MMS CDF format specification) and the requirements to be compatible with “auto-plot”/SPEDAS, MEA, MIA, MSA teams will make CDF skeleton file for Level1 data and compare / modify the skeleton file. Comparison will start from MSA<-> MIA (CDF file for ion data should have much similarity: within ~4 months), then MSA/MIA <-> MEA (by next LEP meeting in May 2016). | MEA/MIA/MSA teams | 2016-09-30 | in progress | open |  | 20160218:due date was changed 20160519:started comparison between MSA <-> MIA Due_date was changed. 20161111: started comparison between MEA<->MSA <-> MIA | open | open | open | N.A. | N.A.
150911-5 | MEA will revise HV initial check procedure in order to reduce the risk of high voltage discharge. MEA team will send ISAS revised HV initial check procedure. | MEA team | 2015-09-30 |  | open |  |  | open | N.A. | N.A. | N.A. | N.A.
150911-6 | Each team will check the agreed definition of the Level0-3 data. The definition can be modifies/improved in the future. | MEA/MIA/MSA teams | 2016-05-19 |  | close | 2016-05-19 | 20160218:due date was changed | open | open | open | N.A. | N.A.
150703-1 | ISAS will evaluate the effect of the OSR charge up due to the lack of the conductive coating at the edge of the OSR. | Y. Saito | 2015-08-31 |  | close | 2015-08-31 |  | N.A. | N.A. | N.A. | N.A. | N.A.
150415-1 | ISAS will send “MPPE DATA MODE ver 2.00 20150413 (After 2nd Integration Test@ISAS)” to MEA/MIA/MSA teams. | Y. Saito | 2015-04-19 |  | close | 2015-05-02 |  | N.A. | N.A. | N.A. | N.A. | N.A.
150415-2 | MEA/MSA/MIA teams will check the contents of “MPPE DATA MODE ver 2.00 20150413 (After 2nd Integration Test@ISAS)” and send comments to ISAS. | MEA/MIA/MSA teams | 2015-05-31 |  | close | 2015-09-11 |  | close | close | close | N.A. | N.A.
150415-3 | LPP MSA team will test downloading data from ISAS data server using SDTP. IRAP will help. | MSA team | 2015-08-31 |  | close | 2015-08-31 |  | N.A. | N.A. | close | N.A. | N.A.
150415-4 | Level0 data format will be decided by negotiation between ISAS and IRAP. IRAP will transfer the information to LPP. | ISAS/IRAP | 2016-11-30 |  | close | 2016-11-11 | ISAS made a header file to make MIA Level0 data (see “2) MPPE LEP Data Management”). The detail of the data format (including the necessity of the common information) will be determined through the comparison of CDF skeleton file between the teams. Due data is changed. 20160519 20160930: Due date was changed. CHANGED to new AI (AI-20161111-6) | close | close | close | N.A. | N.A.
150415-5 | ISAS will check the requirement on CDF data format (relating with the future conversion to PDS 4.0). | ISAS | 2015-08-31 |  | close | 2015-09-11 | I. Shinohara provided us with a document describing the CDF format requirement. | N.A. | N.A. | N.A. | N.A. | N.A.
150415-6 | IRAP will make proposal about the CDF data format. Based on the information and negotiation between IRAP/ISAS/LPP, the detailed CDF data format will be decided. (MEA, MIA, MSA CDF file format should be similar.) | MEA/MIA/MSA teams | 2015-08-31 |  | close | 2015-09-11 | CHANGED to a new AI (AI-1509011-4) | close | close | close | N.A. | N.A.
150415-7 | ISAS will talk with MGF team about inclusion of MGF data in the “data storage for internal use”. Low time resolution / direction only data will also be OK if the full resolution data is difficult. | ISAS | 2016-11-30 | in progress | open |  | Y.Saito talked with A. Matsuoka. "Inclusion of MGF Data" will be possible.Official request should be sent to PI of MGF in the future. 20160218:Due date is changed. 20160519 20160930: not started talking with MGF PI Due date was changed. 20161111: the request has not been sent yet | N.A. | N.A. | N.A. | N.A. | N.A.
150415-8 | TI <-> real time conversion is better to be common to MEA/MIA/MSA. Need further discussion at MMO SWG. | ISAS | 2017-03-31 | in progress | open |  | 20151221:This issue was mentioned at Science Meeting @ISAS;20160218:Due date is changed. 20169519:to be discussed @ MMO SWG to be held in Fall 2016. Due date was changed. 20160831: MMO SWG will be held on 23 September 2016; 20160923: data format has started to be considered due date was changed 20161111: Y. Saito mentioned this point @ MMO SWG in September 2016. | N.A. | N.A. | N.A. | N.A. | N.A.
150415-9 | ISAS will send the ESTEC test (in 4-5 2015) participants information to MMO project by 17 April. | ISAS | 2015-05-17 |  | close | 2015-05-17 |  | N.A. | N.A. | N.A. | N.A. | N.A.
150415-10 | MSA team will send HV & LV initial check plan to ISAS. | MSA team | 2015-04-22 |  | close | 2015-04-21 |  | N.A. | N.A. | close | N.A. | N.A.
150415-11 | MEA team will send LV initial check plan to ISAS. | MEA team | 2015-04-22 |  | close | 2015-04-23 |  | close | N.A. | N.A. | N.A. | N.A.
150415-12 | MEA MIA and MSA teams will have next data management meeting at SWT meeting in September 2015. | MEA/MIA/MSA teams | 2015-08-31 |  | close | 2015-08-02 | Next data management meeting will be held on 11 September in Paris. | close | close | close | N.A. | N.A.
150415-13 | Consider how to use MSA TableE for M-mode data. If additional macro command is necessary, one of the MSA macro commands may be converted to MPPE mode change macro command. | MSA team | 2015-08-31 |  | close |  | CHANGED to a new AI (AI-1509011-1) | N.A. | N.A. | close | N.A. | N.A.
140410-1 | MPPE will evaluate the potential of SCP inter-connector if SCP is replaced for fixing whitening effect. (inter-connecter will be above SCP surface by <4mm) | Y. Saito | 2015-12-31 |  | open | 2015-08-31 | 20140610:due date was changed 20140831:due date was changed 20150911:due date was chaged.20150831:Similar simulation with 150703-1 | N.A. | N.A. | N.A. | N.A. | N.A.
130911-1 | MPPE will evaluate the new SCP CELL with ITO where antireflection (AR) coating is over ITO. | MPPE | 2013-10-31 |  | close | 2014-02-10 | 20140210: It was confirmed that MMO will use solar cell where outer surface is ITO. | close | close | close | N.A. | N.A.
130411-1 | MSA MLI conductor ring should be modified. ISAS will talk with Meisei. ISAS will send a picture to LPP. | ISAS | 2013-04-30 |  | close | 2013-08-21 | 20130513: ISAS sent the picture to LPP, ISAS asked Meisei to re-fabricate the ring 20130713: ISAS received design information from Meisei 20130821:ISAS received re-fabricated conductor ring. | N.A. | N.A. | close | N.A. | N.A.
130411-2 | MPPE meeting schedule will be made taking into account the MMO launch schedule. | all | 2016-12-31 |  | open |  | 20140510:due date was changed 20140801:due date was changed.20141031: due date was changed.20150531:due date was changed.20160218:due date was changed | N.A. | N.A. | N.A. | N.A. | N.A.
130411-3 | Power ON priority in case of MDP Emergency: MEA1 and MEA2 should be exchanged. (correct sequence: <high priority> MEA2 MIA HEPele MSA MEA1 HEPion <low priority>) | ISAS | 2013-04-30 |  | close | 2013-04-30 |  | N.A. | N.A. | N.A. | N.A. | N.A.
121015-1 | Each team should submit revised SIB2 | All | 2012-10-31 |  | close | 2013-03-01 |  | close | close | close | close | close
120614-1 | Each team should submit revised IICD with final mass information . | All | 2012-06-30 |  | close | 2013-03-01 |  | close | close | close | close | close
120614-2 | MLI GND point information should be added to IICD | MSA MEA MIA | 2012-06-30 |  | close | 2013-02-14 | 20130115:ISAS received revised drawings of MEA from Orbital-E | close | close | close | N.A. | N.A.
120614-3 | Each team should submit "macro command" information . | All | 2012-07-01 | in progress | open |  | 20130411: MEA will select 3 macro commands 20130417: MEA sent ISAS 3 macrocommands 20130419: ISAS submitted MEA's macro command information to NEC | close | close | close | open | close
120426-1 | ISAS will keep track of the high temperature MLI dust issue. | ISAS | 2012-10-31 |  | close | 2014-10-31 | Y. Saito talked with MMO project about the MLI dust. 2012.6.14 Project explained the current status. 2012.10.17 Y.Saito received information from MMO project 2013.4.11: some progress expected @ PM 15~17 April 2013 2013.4.15:ISAS requested BC project to reduce the dust as much as possible including the installation of the separation foil 2014.4.29: BC project decided to reduce the dust as much as possible by installing the separation foil between MPO and MMO | N.A. | N.A. | N.A. | N.A. | N.A.
120426-2 | ISAS will check the temperature range of the thermal vacuum test. | ISAS | 2012-05-15 |  | close | 2012-11-10 | Y. Saito sent an e-mail to Ogawa-san about MSA, MIA, MEA Thermal Vacuum test temperature profile. 19 May 2012 MSA min. -35 max. +70deg. 7 July 2012 MEA1 min.-35 max. +70 MEA2 min. -30 max. +75 MIA min. -35 max. +75 | N.A. | N.A. | N.A. | N.A. | N.A.
120426-3 | ISAS will check the recommended import / export procedure of MEA and ENA | ISAS | 2012-08-31 |  | close | 2012-06-14 | 14 June 2012: ENA MEA normal import for 2nd integration test delivery and repairment or carne for the final check after system mechanical test were recommended at #19 Desgin meeting | N.A. | N.A. | N.A. | N.A. | N.A.
120202-1 | Reconsider the MPPE's request on the beam test after system mechanical test | ALL TEAMS | 2012-04-30 |  | close | 2012-03-31 | MPPE requested 1-month final sensor check after system mechanical test. | close | close | close | close | close
111006-1 | Ask HEP team if current HEP mode is OK. (data rate may be slightly increased) | HEP team, ISAS | 2011-12-31 | in progress | open |  |  | N.A. | N.A. | N.A. | open | N.A.
111006-2 | MSA, HEP mode should be categorized into “science topic” MPPE mode. | MSA, HEP teams | 2011-12-31 |  | close | 2015-12-07 | 17 Junuary 2012:ISAS received MSA information 7 December 2015:ISAS received HEP information | N.A. | N.A. | close | close | N.A.
111006-3 | ENA: Global condition -> should be used for triggering | ENA team, ISAS | 2011-12-31 | in progress | close | 2012-10-26 | 2012.2.10: This item was included in the MPPE report @ Design Meeting #18 | N.A. | N.A. | N.A. | N.A. | close
111006-4 | Y. Saito will send the latest MPPE ML to Jea-Andre-san MEA Dominique-san MSA Stas-san and Asamura-san ENA | Y. Saito | 2011-10-31 |  | close | 2011-11-12 | 2011.11.12: Y.saito sent the latest ML to Jea-Andre-san MEA Dominique-san MSA Stas-san and Asamura-san ENA | N.A. | N.A. | N.A. | N.A. | N.A.
111006-5 | Y. Saito will check the launch sequence (including the parking orbit period). | Y. Saito | 2011-12-31 | in progress | close | 2013-04-11 | 2012.2.10: Launch sequence may be influenced if the launch will delay by one year 2013.4.11: see 23rd MPPE meeting memo | N.A. | N.A. | N.A. | N.A. | N.A.
111006-6 | Y. Saito will ask MMO project the current plan of cruising phase operation / fly-by plan etc. | Y. Saito | 2011-12-31 | in progress | open | 2013-04-11 | 2012.2.10: Y. Saito asked MMO project the current plan of cruising phase operation / fly-by plan etc. power on check during cruising phase will be considered in the future 2013.4.11: possibly be turned on every half years | N.A. | N.A. | N.A. | N.A. | N.A.
111006-7 | Check if ISAS system vibration test is whose requirement : since it is not the final configuration, the test will be useless for SIs (same as unit level test) ESTEC vibration test with the final configuration is meaningful. ((we will not be able to check instrument after ISAS system vibration test!!) Reduce to the acceptance level? | Y. Saito | 2011-12-31 | in progress | close | 2012-03-31 | 2012.2.10: This item was included in the MPPE report @ Design Meeting #18 2012.3.31: Instead of changing the test level, MPPE will have 1-month final sensor check opportunity after system mechanical test. | N.A. | N.A. | N.A. | N.A. | N.A.
110406-1 | Thermal Shield EM MSA: FM sensor head is different from EM. Interference should be checked beforehand. | MSA | 2011-04-30 |  | close | 2012-01-10 | Several e-mails are sent between LPP and ISAS and Meisei. Meisei has sent no repsonse to ISAS. At DN#17 this action item was informed to NEC . Interfae was checked during the 1st integration test. | N.A. | N.A. | open | N.A. | N.A.
110406-2 | Purge flow should be equal to all the sensors under the condition without purge cover. Y. Saito will make sure this is satisfied talking with NEC. To protect thin carbon foil, “burst” of the purging should also be avoided. | Y. Saito | 2011-04-30 |  | close | 2011-10-06 | 2011.4.19: Y. Saito sent an e-mail to NEC.At DN#17 this action item was informed to NEC. 2011.7.10 NEC is designing an orifice to regulate the purge flow | N.A. | N.A. | N.A. | N.A. | N.A.
110406-3 | Y. Saito will ask NEC that bas-bar in the center panel can be shielded. Y. Saito will ask NEC to provide MPPE with latest information of “interconnector” structure of the solar cell. | Y. Saito | 2011-04-30 |  | open | 2011-09-21 | 2011.4.19: Y. Saito sent an e-mail to NEC.At DN#17 this action item was informed to NEC.2011.9.21 ISAS received information from NEC all the bus bars will be shielded interconnectors are below the solar cell surface | N.A. | N.A. | N.A. | N.A. | N.A.
110406-4 | Y. Saito will ask Dr. Shinohara (who is responsible for data storage/archive) about data storage and distribution strategy (ex. for data processing by each sensor team). | Y. Saito | 2011-04-30 |  | close |  | Y. Saito asked Dr. Shinohara about data storage. The detail has not yet benn detemined. Questions concerning MPPE data products will be sent from Dr. Shinohara to MPPE in the near future. | N.A. | N.A. | N.A. | N.A. | N.A.
101127-1 | Send new information about electron orbit to MMO project. Low energy electrons/ions are still affected by the SCP potential even the corner part is shielded. | ISAS | 2010-12-10 |  | close | 2010-11-30 |  | N.A. | N.A. | N.A. | N.A. | N.A.
101127-2 | Check the potential change of SCP with respect to the spin phase. | ISAS | 2011-03-22 | Y.saito sent an e-mail to NEC system | close | 2011-09-21 | 2011.4.19: Y. Saito sent an e-mail to NEC 2011.9.21 ISAS received information from NEC all the bus bars will be shielded interconnectors are below the solar cell surface | N.A. | N.A. | N.A. | N.A. | N.A.
101127-3 | Send a figure showing the “inter connector” structure and the size of solar cell to CESR. | ISAS | 2010-12-10 |  | close | 2010-11-28 |  | N.A. | N.A. | N.A. | N.A. | N.A.
101127-4 | Revise MSA data mode & MPPE data mode taking into account the new information provided by Markus-san. | ISAS | 2011-03-22 |  | close | 2011-10-06 | Changed to a new AI (AI-111006-2). | N.A. | N.A. | close | N.A. | N.A.
101127-5 | ISAS will send latest version of MPPE data mode information. (Ver. 10) | ISAS | 2010-12-31 |  | close | 2011-02-10 |  | N.A. | N.A. | N.A. | N.A. | N.A.
100720-1 | All the team will check if unit level cover does not interfere with spacecraft panel (without thermal shield: this configuration will be used during the transportation from ISAS to ESTEC) | ALL TEAMS | 2010-09-15 |  | close | 2012-01-31 | This shold be cheked by MEA team during 1st integration test. 2012.1.31: checked during the 1st integration test | close | close | close | close | close
100720-2 | MSA: ISAS will send spacecraft panel information to MSA (size of the hole etc.) | ISAS | 2010-08-31 |  | close | 2010-08-24 |  | N.A. | N.A. | N.A. | N.A. | N.A.
100720-3 | ISAS will consider to request to lower the system test level (ex. Vibration test level) | ISAS | 2010-09-15 |  | close | 2011-10-06 | Changed to a new AI (AI-MPPE-20111006-7). | N.A. | N.A. | N.A. | N.A. | N.A.
100720-4 | ISAS will start considering import (final : export for Europe) procedure of MSA (for the 1st integration test import/export) | ISAS | 2010-12-31 | ISAS submitted FM delivery schedule to MMO Project. | close | 2011-03-09 | Flight Spare delivery should also be considered in the future. | N.A. | N.A. | N.A. | N.A. | N.A.
100505-1 | ISAS will send schedule information to MPPE team after Design Meeting on 20 May. | ISAS | 2010-05-21 | discussed@MPPE meeting in BREMEN | close | 2010-07-20 | Delivery of sensors to ISAS for 1st integration test is 2E 2011. Delivery of sensors to ISAS for 2nd integration test is 12E 2011. Detailed delivery date is different between MPPE sensors and it will be negotiated in more detail in the near future. Delivery of sensors to ISAS for 1st integration test by 3E 2011 is recommended.
100505-2 | Each sensor team will negotiate the EMC test schedule and delivery schedule. | ALL TEAMS | 2010-05-31 | discussed@MPPE meeting in BREMEN | close | 2010-07-20
100505-3 | MPPE will request spacecraft SYSTEM to open the purge port (spacecraft side) at launch. | ISAS | 2010-05-22 |  | close | 2010-05-20 | During the 15th Design Meeting, MPPE requested spacecraft SYSTEM to open the purge port (spacecraft side) at launch.
100505-4 | Each team will send ISAS what is necessary (Ion beam? Electron beam? What else?) and how long it will take to do the vacuum test after system mechanical test. (If we can.) | ALL TEAMS | 2010-12-31 | discussed@MPPE meeting in BREMEN | close | 2011-04-06 | new actionitem 100720-3 is made relating to this action item 2011.4.6: At MPPE meeting, MPPE found it is difficult to request this test to the MMO system. Of course, MPPE will utilize the opprtunity if there is. | close | close | close | close | close
100505-5 | ISAS will confirm ENA’s FOV in NEC’s document MMO-NT-D10053 ver 1.0 page (3/10) is not correct. | ISAS | 2010-05-22 |  | close | 2010-05-20 | According to NEC, the figure was not correct.
100114-1 | If additional parts is necessary to prevent MLI to stick out to FOV of MEA, MIA, MSA, ISAS & Orbital-E will send a figure showing the recommendations of the additional parts to MEA and MSA team by the end of Jan. 2010. | ISAS / Orbital-E | 2010-05-31 | Information was sent to MSA : MIA & MEA to be determined | close | 2010-05-27 | 30 April 2010: Due Date was changed By 27 May 2010, MEA, MIA, and MSA teams talked with Orbital-E and decided how to modify the analyzer to prevent MLI to stick out to their FOV.
100114-2 | ISAS will check if MEA thermal shield has 45 deg. separated 8 “stays” between the top part and the bottom part. | ISAS | 2010-01-31 |  | close | 2010-04-06 | Yes
100114-3 | ISAS will check how long the total “no-purge time” and maximum duration of continuous “no-purge time”, and the quality of the dust environment during this period. | ISAS | 2010-01-31 |  | close | 2010-04-16 | MMO Purge Interruption PeriodMM-NT-D10093v1.1.doc & Class 100,000
100114-4 | Each team will continue considering how to close the inlet. | ALL THE TEAM | 2010-05-31 | to be discussed in MPPE meeting@Vienna | close | 2010-05-20 | 30 April 2010: Due Date was changed 20 May 2010: cover information was presented @ design meeting on 20 May 2010.
100114-5 | ISAS will check if PA related document is easily downloaded (ex. if they are on the same directory etc.) for CDR. | ISAS | 2010-01-31 |  | close | 2010-04-06 | CDR Web Page
100114-6 | ISAS will talk with ISAS/JAXA PA group if e-mails from ex. Frace PA group can be directly sent to ISAS/JAXA PA group. | ISAS | 2010-01-31 |  | close | 2010-04-06 | PA related e-mails can be sent directly to maejima.hironori@jaxa.jp shimizu.yukio@jaxa.jp
091030-1 | ISAS will send “CDRplanDraft2.0.doc” to all the teams. | ISAS | 2009-11-10 |  | close | 2009-11-03
091030-2 | ISAS will ask NEC to provide new figure (including new spacecraft panel) showing the FOV – spacecraft panel position. | ISAS | 2009-11-10 |  | close | 2010-03-03 | NEC sent FOV information:MMO-NT-D10053 ver 1.0
091030-3 | ISAS will send EMC control excel file to ENA team. | ISAS | 2009-11-10 |  | close | 2009-11-03
091030-4 | ISAS will send “Onboard Data Plan” document to MPPE team(.ppt delivered @SWG and .pdf MDP-IRD). | ISAS | 2009-11-10 |  | close | 2009-11-03
091030-5 | Each team will read the “Onboard Data Plan” document and send comments to ISAS. | TEAM | 2010-11-30 | discussed@MPPE meeting in BREMEN | close | 2011-10-06 | 30 April 2010: Due Date was changed 20 July 2010: Due Date was changed | close | close | close | close | close
091030-6 | ISAS will ask the time resolution and quality (with or without offset etc.) of spacecraft potential data available onboard. | ISAS | 2009-11-30 |  | close | 2010-04-28 | 1 spin
091030-7 | ISAS will ask the time resolution and quality (with or without offset etc.) of magnetometer data available onboard. | ISAS | 2009-11-30 |  | close | 2010-04-28 | 8Hz or 128Hz: Baseline 128Hz without offset
091030-8 | All the team will consider a “cover” to prevent N2 purge gas from leaking after thermal shield installation. | TEAM | 2010-01-14 |  | close | 2010-01-14 | changed to new Action Item: 100114-4
090831-1 | Y. Saito will send draft agenda of 15th MPPE meeting @ Blois | Y. Saito | 2009-09-30 |  | close | 2009-10-26
090701-1 | Each group will send revised individual data mode to ISAS. | TEAM | 2010-09-15 | discussed@MPPE meeting in BREMEN | close | 2011-10-06 | 30 April 2010: Due Date was changed; 20 July 2010 new information from MSA and MEA is requested & due date was changed | close | close | close | close | close
090421-1 | ISAS will check the compression ratio of JPEG (loss less) | ISAS | 2010-11-30 |  | open |  | 30 April 2010: Due Date was changed; 20 July 2010 due date was changed;06 October 2011 Action Item of HEP 2013.4.11: ISAS will ask HEP the current status | N.A. | N.A. | N.A. | open | N.A.
090421-2 | ISAS will consider if RICE, JPEG(loss less), JPEG(lossy) compressions can be switched using command | ISAS | 2010-11-30 |  | close | 2011-10-06 | difficult 30 April 2010: Due Date was changed; 20 July 2010 due date was changed; 06 October 2011 only RICE compression is used. | N.A. | N.A. | N.A. | N.A. | N.A.
090421-3 | ISAS will consider if compression scheme can be actively selected depending on the compression ratio and data transfer rate | ISAS | 2010-11-30 |  | close | 2011-10-06 | difficult 30 April 2010: Due Date was changed; 20 July 2010 due date was changed; 06 October 2011 only RICE compression is used. | N.A. | N.A. | N.A. | N.A. | N.A.
090421-4 | ISAS will consider a possibility to prepare multiple compressed data set (with different time & angular resolution) and select one of them depending on the available data rate | ISAS | 2010-11-30 |  | close | 2011-10-06 | difficult 30 April 2010: Due Date was changed; 20 July 2010 due date was changed; 06 October 2011 only RICE compression is used. | N.A. | N.A. | N.A. | N.A. | N.A.
090421-5 | At least 20min. duration is desirable for H and M modes(ex. to measure full crossing of the magnetotail) | team | 2009-07-01 |  | close | 2009-04-21 | requested to SWG
090421-6 | Request to SWG: to be flexible (after launch) to keep the possibility to record H or M mode within the capacity of MDR and send the data (while stopping generating M or H mode data) using some period (within the limitation of thermal condition) | team | 2009-07-01 |  | close | 2009-07-01
090421-7 | ISAS will send all the member revised MPPE Data Mode document (MPPE_NEW_DATA_MODE_v0_1.doc). Each member will review the document and send the request to ISAS within two weeks (by 8 May 2009). | team | 2009-05-08 |  | close | 2009-07-01 | changed to new AI 090701-1
090124-1 | Y. Saito will send draft agenda of 12th MPPE team meeting by 19 March. | ISAS | 2009-03-19 |  | close | 2009-03-30
090116-1 | MPPE will define "safety mode" common to all the MPPE sensors. | all teams | 2009-04-26 |  | close | 2009-01-16 | two safety modes: HVPS off within 2sec and 10minutes
080913-1 | Each team will send Y. Saito a list of Monthly Report distribution | all teams | 2008-09-30 |  | close | 2008-09-13 | received from ENA and MSA
080913-2 | ISAS will evaluate if RICE compression can be implemented in MDP | ISAS | 2008-10-31 |  | close | 2009-04-21
080913-3 | Each team will check “MPPE NEW DATA MODE” and send Y. Saito comments. | ISAS | 2009-05-08 |  | close | 2009-07-01 | changed tp new AI-090701-1
080720-1 | Y. Saito will send draft agenda of 11th MPPE team meeting by 31 August. | ISAS | 2008-08-31 |  | close | 2008-09-13
080716-1 | ISAS will check the operation temperature of UBE white paint (UBE #0003) | ISAS | 2008-09-13 |  | close | 2009-01-09 | <300deg.C
080716-2 | MMO project will ask UBE if they can sell white paint will foreign countries | ISAS | 2008-09-13 |  | close | 2009-01-09 | ENA received contact information
080716-3 | Y. Saito will ask MMO project to provide MPPE the following information: alpha, epsiron temporal change of alpha and epsiron under operation temperature operation temperature requirement to substrate on which the painting can be attached | ISAS | 2008-09-13 |  | close | 2009-04-21
080716-4 | ISAS will check if OSR and white paint can be used at the same time (OSR can be attached over white paint or not) | ISAS | 2008-09-13 |  | close | 2009-01-09 | test is required in SI side
080716-5 | ENA will send RICE compression source code to ISAS | ENA team | 2008-07-31 |  | close | 2008-09-13
080716-6 | ISAS will evaluate the RICE compression | ISAS | 2008-10-31 |  | close | 2008-09-13 | changed to new AI-080913-2
080716-7 | MSA will reconsider to compress their data inside MSA CPU | MSA team | 2008-09-13 |  | close | 2008-09-13
080716-8 | Draft MPPE Data Mode will be prepared by next MPPE meeting | ISAS | 2008-08-31 |  | close | 2008-09-13
080716-9 | Ask PSS to include all the member to the author list instead of adding member list. | ISAS | 2008-07-31 |  | close | 2008-07-16 | member list is included in the in press paper
080716-10 | Send the member list to each team and each team will confirm the list. Due: send on17 July by e-mail confirm by 23 July | all | 2008-07-23 |  | close | 2008-07-16 | list was sent to core members on 17 July
080716-11 | Markus-san will ask the due date etc. of ASR paper submission | all | 2008-07-23 |  | close | 2008-07-16 | no special volume is planned
080620-1 | Y. Saito will send draft agenda of 10th MPPE team meeting by 30 June. | ISAS | 2008-06-30 |  | close | 2008-06-20
080514-1 | Each team will check the current power and mass and send the result to Y. Saito. | all team | 2008-05-31 |  | close | 2008-05-14 | ENA-> 4.42 MSA-> ask NEC 7.6W? HEP -> revise table
080514-2 | ISAS will ask NEC possible shape of the thermal shield. | ISAS | 2008-05-31 |  | close | 2008-09-13
080514-3 | ISAS will consider the possible testing configuration (including dummy SPC panel, thermal shield (probably from NEC??)) | ISAS | 2008-06-15 |  | close | 2008-09-11
080514-4 | MEA will send Y. Saito possible delivery date of its I/F model within a few weeks. | ISAS | 2008-05-31 |  | close | 2008-05-14
080514-5 | ISAS will send JPEG compression evaluation software to CETP. | ISAS | 2008-07-03 |  | close | 2008-06-20
080514-6 | Each team will send Y. Saito revised data mode of each instrument and information about instrument check mode. | all team | 2008-05-31 |  | close | 2008-09-13 | changed to new AI-080913-3
080514-7 | Y. Saito will make (revised) draft data mode table and send them to MPPE team by e-mail. | Y. Saito | 2008-06-15 |  | close | 2008-05-14 | changed to 080716-8
080514-8 | Y. Saito will request spacecraft potential to PWI. | Y. Saito | 2008-05-31 |  | close | 2008-05-14 | sent an e-mail to PWI
080514-9 | MEA will send Y. Saito requirement to MDP MEA process. | MEA | 2008-05-31 |  | close | 2008-09-17
080514-10 | MIA will send the programming group requirement to MDP MIA process. | MIA | 2008-05-31 |  | close | 2008-05-14 | MIA CDR input package
080514-11 | ISAS will ask NEC the type of connectors used for flight harness and their manufacturer’s name. | ISAS | 2008-05-31 |  | close | 2008-05-14
080514-12 | Consider to hold SERENA-MPPE joint meeting during SWT@sendai in September rather than EGU2009. | Y. Saito | 2008-08-31 |  | close | 2008-09-13 | 1st meeting is planned during SWT@Sendai
080514-13 | ISAS will send MEA’s thermal math model information to MEA team. | ISAS | 2008-05-31 |  | close | 2008-12-28
080417-1 | Spacecraft panel motion: ISAS will send information to ENA. | ISAS | 2008-05-11 |  | close | 2008-04-25 | radial +3mm/-3mm tangential +1mm/-1mm
080417-2 | All team members will consider how to reduce heat input from MPPE sensors. MEA: close at least 70deg. of the FOV of one of the MEAs MSA: reduce the open area of the entrance part by 50% close 90deg. of the FOV consider the possibility of exchange the positions of MEA and MSA MIA: reduce the open area of entrance part HEP-ion: closed half of the FOV ENA: close some of the FOV | team | 2008-05-11 |  | close | 2008-04-17
080417-3 | ISAS will check the performance of JPEG compression using GTL, KAGUYA data | ISAS | 2010-11-30 |  | open |  | 30 April 2010: Due Date was changed; 20 July 2010 due date was changed; 06 October 2011 Action Item of HEP 2013.4.11: ISAS will ask HEP the current status | N.A. | N.A. | N.A. | open | N.A.
080417-4 | ISAS will check the detail of JPEG compression hardware (+Loss less ???) | ISAS | 2008-05-11 |  | close | 2008-04-17
080417-5 | MEA will send “MDP1 programming requirement” to ISAS by 31 August 2008 | MEA | 2008-08-31 |  | close | 2008-09-17 | the ealier the better
080417-6 | Y. Saito will arrange a meeting with MPO SERENA during the week of EGU meeting 2009. | Y. Saito | 2009-02-28 |  | close | 2008-09-13 | 1st meeting is planned during SWT@Sendai
080215-1 | Y. Saito will send draft agenda of 9th MPPE team meeting by 17 March. | ISAS | 2008-03-17 |  | close | 2008-03-31
070920-1 | ISAS will send thermal design & analysis part of the input package to MEA by the end of September. | ISAS | 2007-09-30 |  | close | 2007-10-03
070920-2 | ISAS will send an e-mail to PWI group asking them to attend “data compression meeting” scheduled on 9/25 9:00- @ISAS A5F meeting room | ISAS | 2007-09-21 |  | close
070920-3 | MPPE team will decide the detailed date of 9th MPPE meeting (during EGU meeting 2008). | team | 2008-02-29 |  | close |  | 17 April, 2008
070920-4 | MPPE will consider to hold a meeting with MPO SERENA during the week of EGU meeting 2008. | team | 2008-02-29 |  | close | 2008-04-17 | changed to new AI 080417-6
070715-1 | Y. Saito will send draft agenda of 8th MPPE team meeting by 20 August. | ISAS | 2007-08-20 |  | close | 2007-08-24
070707-1 | CNES will send information about IAS/LANGEVIN Compression IP-code. (VHDL Code Size etc.) | CNES | 2007-09-26 |  | close | 2007-10-25 | detail will be discussed at MPPE meeting@Berlin on 20 September 2007 and DM@ISAS on 24-26 September 2007
070419-1 | ISAS will ask NTSpace if MPPE can have more precise value between the “MLI flange” and spacecraft panel (“10mm”). | ISAS | 2007-05-17 |  | close | 2007-09-20 | ISAS received the following response from NTSpace: 10mm including MLI thickness and thickness of Velcro or some other interface is OK.
070419-2 | Each team will send Y. Saito the design concept of the thermal shield by 6 May 2007. | team | 2007-05-06 |  | close | 2007-05-11 | ISAS received the information and submitted to NTSpace
070419-3 | Each team will send Y. Saito the necessary nitrogen flow rate by 6 May 2007 assuming no non-flight items to prevent leaking nitrogen from the inlet part of each instrument. | team | 2007-05-06 |  | close | 2007-05-11 | ISAS received the information and submitted to NTSpace
070419-4 | Each team will send Y. Saito the information of nitrogen purge port by 6 May 2007. | team | 2007-05-17 |  | close | 2007-05-11 | ISAS received the information and submitted to NTSpace
070419-5 | ISAS will ask NTSpace the exact spacing of OSR and send the information to team. | ISAS | 2007-05-06 |  | close | 2007-05-10 | 0.1mm (NTSpace)
070419-6 | ISAS will inform NTSpace of the following MPPC’s opinion. MPPC cannot accept 280X280 black kapton around MAST compromise plan: change MSA & MEA position to have 135 deg. separation & avoid seeing MASTs | ISAS | 2007-05-06 |  | close | 2007-04-23
070419-7 | IAS/LANGEVIN Compression 1) Gaboriaud-san -> send MPPE Core member information about “test data” information about algorithm by 31 January -> CLOSED sent in February 2) Each team will prepare test data & send them to Gaboriaud-san (ALL SENSORS) by 10 MAY 2007 3) Compression rate, compression time etc. will be evaluated by 30 June | team | 2009-03-31 |  | close | 2009-04-21 | to be used only in MSA CPU
070419-8 | CNES will check the possibility of the following two options and the result is sent to ISAS by the end of MAY 2007. 1) ISAS will receive IAS/LANGEVIN Compression IP-code with support from CNES -> JAXA MHI FPGA 2) ISAS will buy ASIC(WICOM) from ASTRIUM In case of solution 1), ISAS will be able to have IP-CODE by the end of September 2007. In case of solution 1), ISAS will be able to have IF document by T.B.D. (CNES will check the T.B.D. and send the information to ISAS by the end of APRIL 2007.) | CNES | 2007-05-31 |  | close | 2007-07-07 | changed to new AI070707-1
070419-9 | ENA team will estimate the minimum possible data rate estimate nominal data rate estimate the maximum desirable data rate by 4 May 2007. | 2007-05-04 | 2007-05-17 |  | close | 2008-07-31
070419-10 | MSA team will consider reducing the data rate between MSA <-> MDP define data modes MDP <-> Ground by 4 May 2007. | 2007-05-04 | 2007-05-17 |  | close | 2007-05-17
070419-11 | ISAS will estimate the necessary quantity of MDP work area. | ISAS | 2010-11-30 |  | close | 2011-10-06 | 30 April 2010: Due Date was changed; 20 July 2010 due date was changed | N.A. | N.A. | N.A. | N.A. | N.A.
070419-12 | ISAS will send MDP IF information to MPPE CORE members. | ISAS | 2007-05-17 |  | close | 2007-09-20 | Latest information can be dounloaded from MMO WEB page.
070419-13 | Date of 8th MPPE meeting will be decided when the schedule of Bepi-SWT#4 become clear. | team | 2007-06-30 |  | close | 2007-07-15
070406-1 | MPPE sensors have to have “flange” to attach spacecraft MLI without any gaps (minimizing external thermal input). Each sensor team should design their MLI “flange” by next design meeting scheduled on 17, 18 May 2007. | team | 2007-05-17 |  | close | 2007-10-31 | ISAS submitted new Drawings with MLI I/F of MEA, MIA and MSA to NEC
070406-2 | Thermal shield design will be made by NTSpace. (If the design is not too complicated.) Each sensor team should send the design concept of their thermal shield to NTSpace by 6 May 2007. If OSR is used for the thermal shield the size should be a multiple of 2cmX2cm. | team | 2007-05-06 |  | close | 2007-04-19 | changed to new AI 070419-2
070406-3 | MPPE is required to specify the flow rate of Nitrogen purging gas when front cover cannot be installed by 6 May 2007. | team | 2007-05-06 |  | close | 2007-04-19 | changed to new AI 070419-3
070406-4 | MPPE has to send requirements about the purging port & purging tube to NTSpace. | team | 2007-05-17 |  | close | 2007-04-19 | changed to new AI 070419-4
070406-5 | Thermal Math Model update plan MEA: by the end of May 2007 MIA: by the end of May 2007 MSA: by the end of May 2007 HEP: by the end of May 2007 ENA: by the end of May 2007 | team | 2007-06-22 |  | close | 2007-07-20 | New thermal mathmodel of all the sensors were submitted
070215-1 | Y. Saito will send agenda of 7th MPPE team meeting one month before the meeting | Y. Saito | 2007-03-19 |  | close | 2007-04-09
070113-1 | I-ICD revision plan MEA: revised version will be sent from CESR to ISAS on 25 Jan. 2007 revised version will be submitted on 31 January 2007 MIA: to be submitted on 31 January 2007 MSA: to be submitted on 31 January 2007 HEP: to be submitted on 15 January 2007 ENA: to be submitted on 31 January 2007 | team | 2007-01-31 |  | close | 2007-11-12 | ISAS submitted revised MEA, MIA, MSA, ENA and HEP I-ICDs
070113-2 | CDD update plan Each team will check and revise the latest version of CDD if necessary. CDD can be downloaded from the following WEB page. http://www.stp.isas.jaxa.jp/mercury/mmo/official.html | team |  |  | close | 2007-01-22 | CDD was changed to PDD
070113-3 | Thermal Math Model update plan MEA: by June 2007 MIA: by June 2007 MSA: by June 2007 HEP: updated in Dec. 2006 ENA: by June 2007 | team | 2007-06-30 |  | close | 2007-04-06 | changed to new AI 070406-5
070113-4 | HEP will send Y. Saito STBY mode power consumption | HEP | 2007-01-31 |  | close | 2007-04-19
070113-5 | each team will estimate the E2PROM memory usage MEA: Moment calculation table MIA: Moment calculation table MSA: none HEP: Mass Table: 32kbytes (bef. compression) ENA: Initialization command HV table: 800bytes lookup table: 44kbytes | team | 2007-01-31 |  | close | 2008-04-17
070113-6 | IAS/LANGEVIN Compression 1) Gaboriaud-san -> send MPPE Core member information about “test data” information about algorithm by 31 January 2) each team will prepare test data & send them to Gaboriaud-san by 28 February 3) compression rate, compression time etc. will be evaluated by 31 March 4) FPGA gate size etc. : Takashima-san will make contact with Gaboriaud-san immediately | team | 2007-03-31 |  | close | 2007-04-19 | changed to new AI 070419-9
070113-7 | Each team will consider the following items concerning MPPE data mode: due date: next MPPE meeting (during EGU meeting) MEA: E-t mode <-> pitch angle distribution? consider reducing the number of data modes MIA: Velocity moment calculation : use all 3 modes or use only high resolution mode? MSA: consider reducing the data rate between MSA <-> MDP define data modes MDP <-> Ground HEP: revise data mode information ENA: estimate the minimum possible data rate estimate nominal data rate estimate the maximum desirable data rate | team | 7th MPPE meeting |  | close | 2007-04-19 | changed to new AI 070419-7
070113-8 | Requirement shown in MPPE proposal should be revised assuming central purging (purge port will fly with sensor->purge port should be light weight & small) | ISAS |  |  | close | 2007-01-22
061112-1 | Y. Saito will send draft agenda of 6th MPPE team meeting by 13 December. | ISAS | 2006-12-13 |  | close | 2006-12-13
060910-1 | ISAS will send new specifications of MDP to teams | ISAS | A.S.A.P. |  | close | 2006-10-10 | ISAS sent new information to MPPE core members
060910-2 | Each team will check the data rate based on the new specifications of MDP (to be sent from ISAS) and send Y. Saito the result | team | A.S.A.P. |  | close | 2007-01-13
060910-3 | ISAS will send the team JPEG compression sample software. | ISAS | 2008-08-31 |  | close | 2006-09-10
060910-4 | Each team will evaluate the performance of JPEG compression using dummy( or real ) data. <1DCT+1Huffman tables> | team | 2008-08-31 |  | close | 2006-12-13
060910-5 | Each team will consider if MHI JPEG compression FPGA (1DCT + 1Huffman) can be used. Quite Limited tables. | team | 2008-08-31 |  | close | 2006-12-13
060405-1 | Y. Saito will check the status of communication between ENA and NTSpace. | ISAS |  |  | close | 2006-06-10
060405-2 | Each team will consider the sensor delivery schedule based on new MPPE Master Schedule. | team | 2007-01-13 |  | close | 2007-01-13
060405-3 | Each team will send Y. Saito the information about power consumption for different modes. | team | 2007-01-13 |  | close | 2007-12-13 | New A/I070113-4
060405-4 | Space cube with GSE sample software will be supplied to MEA team from JAXA. | ISAS | 2008-03-31 |  | close | 2008-04-17
060405-5 | ISAS will send the summary of sensor <-> MDP I/F information to team. | ISAS | A.S.A.P. |  | close | 2006-09-10 | New A/I060910-1: Specifications of MDP was revised
060405-6 | Each team will check the data rate and send Y. Saito the result | team | 2006-04-30 |  | close | 2006-09-10 | New A/I060910-2: Specifications of MDP was revised
060405-7 | ISAS will send the team JPEG compression sample software | ISAS | 2006-04-30 |  | close | 2006-09-10 | New A/I060910-3: Specifications of MDP was revised
060405-8 | Each team will evaluate the performance of JPEG compression using dummy(or real) data. | team |  |  | close | 2006-09-10 | New A/I060910-4: Specifications of MDP was revised
060405-9 | Each team will consider if MHI JPEG compression FPGA can be used or not. Limited tables. (4DCT 4Haffman) | team |  |  | close | 2006-09-10 | New A/I060910-5: Specifications of MDP was revised
060405-10 | Each team will send Y. Saito the information about other compression (with the availability of VHDL code).P. Wurz will send Y. Saito the information about wavelet compression VHDL code. | team |  |  | close | 2006-09-10 | Y. Saito received the information about wavelet compression VHDL code.
060405-11 | ISAS will send each team a “template” of Data Mode Table as soon as practical. | ISAS | 2006-11-20 |  | close | 2006-10-03 | ISAS sent draft "Data Mode Table" to MPPE core member.
060405-12 | Each team will send Y. Saito the information about “Electrically insulated and thermally conducting” material | team |  |  | close | 2006-09-10
060405-13 | Y. Saito will send the information about “Electrically insulated and thermally conducting” material to all the team. | ISAS |  |  | close | 2006-05-10 | Y. Saito sent MPPE core the information about “Silpad” received from MEA team.
060405-14 | Each team will check the current power and mass table and send the results to Y. Saito by the end of April. | team | 2006-04-30 |  | close | 2006-06-19 | Y. Saito received information from MEA and MSA teams. All the team confirmed the value before 4th Design Meeting.
060310-1 | Y. Saito will send agenda of 5th MPPE team meeting by 20 March. |  |  |  | close | 2006-06-19
051018-1 | Each team will send Y. Saito the revised I-ICD by 28 Oct.New figure (MEA, MIA, MSA: taking into account the metal fitting at the corner, the motion of spacecraft panel) will be submitted at next I-ICD revision. | HEP ENA teams | 2007-01-22 |  | close | 2006-09-10 | Y. Saito received and submitted MEA, MIA, and MSA I-ICD.
051018-2 | 0) ISAS will provide information about Japanese JPEG compression chip to each team within a couple of months. 1) CETP will apply software JPEG compression to Cluster Ion data by the end of March 2006 (interim report: by the end of December). 2) CETP will estimate the error in the velocity moment calculated from the jpeg compressed data by the end of March 2006. 3) CETP will check the required CPU power for Double Star JPEG compression by the end of December 4) Each team will decide the detailed plan of data transmission to the ground by the end of December. |  |  |  | close | 2006-10-10 | Changed to New AI 060910-4
051018-3 | Each team will revise Power Consumption Table assuming BOL and send it to Y. Saito by 28 Oct. |  |  |  | close | 2006-01-10
051018-4 | Each team will send Y. Saito if survival heater is necessary or not by 28 Oct. |  |  |  | close | 2006-01-10
051018-5 | Each team will send Y. Saito if HCE controlled monitor is necessary or not by 28 Oct. |  |  |  | close | 2006-01-10
051018-6 | Each team will check the size and minimum required primary voltage for 3.3V linear regulator. |  |  |  | close | 2006-04-10 | Note: Each MPPE sensor will have its own PSU..
051018-7 | MPPE will request that each voltage ON/OFF should be sequentially controlled by hardware: the sequence is different between sensor groups. |  |  |  | close | 2006-04-10 | Note: Each MPPE sensor will have its own PSU..
051018-8 | Each sensor team will send its preferable ON/OFF sequence to Y. Saito.ISAS will send draft sensor grouping to team. |  |  |  | close | 2006-04-10 | Note: Each MPPE sensor will have its own PSU..
051018-9 | MPPE will request more detailed information (about the metal fitting at the corner of the deck) to MMO system.At the same time MPPE will carefully consider the thermal shield design assuming that the SPC panel moves 2mm-5mm(T.B.C.). |  |  |  | close | 2005-12-10 | MMO system sent MPPE the information about the metal fitting at the corner of the deck.
051018-10 | ISAS will send each team a “template” of Data Mode Table by 10 Nov. Each team will send Data Mode Table to Y. Saito by 31 Dec. 2005. |  |  |  | close | 2006-04-10 | note: converted to new A/I <A/I 060405-11>
050910-1 | Y. Saito will send agenda of 4th MPPE team meeting by the end of September. |  |  |  | close | 2005-09-30
050810-1 | MPPE team should consider if data compression hardware in IDPU (ex. additional FPGA board for data compression) is necessary or not. |  |  |  | close | 2005-10-18 | MPPE team will start detailed evaluation of the data mode and data quantity. <A/I 051018-2>
050721-1 | MSA will send Y. Saito information if -5V is necessary or not. If -5V is necessary, required power should also be informed. |  |  |  | close | 2005-08-01 | MSA needs -5V
050721-2 | Following information will be sent from ISAS to everybody as soon as ISAS gets information CPU processing power:Available CPU processing power for each team |  |  |  | close | 2005-09-30 | CPU processing power : 200MIPS @ max. clk -> Available CPU processing power for each team <10MIPS
050721-3 | ISAS will confirm that +-12V stability is within +-10%. |  |  |  | close | 2006-04-10
050721-4 | There exists FOV interference between MEA and HEP-ion. ISAS should talk with MMO system to solve this problem. MEA FOV : +-3.5 (FWHM) +-5deg (FULL FOV) One possible solution is to change the positions of MEA and MIA FOV interference between CAMERA and MEA should also be noticed. |  |  |  | close | 2005-08-30 | ISAS submitted new draft arrangement (change the positions of MEA and MIA) to MMO System & NTSpace
050721-5 | MEA will have function to change sweep start timing (1/16 sector unit) in order to minimize the secondary electron detection when MEA looks toward the sun. (ex. Highest energy electrons should be measured in this phase.) MIA and MSA will continue considering if ion sensors also have this function. |  |  |  | close | 2008-04-17 | MIA and MSA will not have this function.
050721-6 | MIA will consider if MIA has the following same data mode as MEA. 16chX16azimuthX 64E mode 16chX32azimuthX32E mode |  |  |  | close | 2007-09-20 | MPPE will decide integrated data mode in the near future. (20 September 2007)
050721-7 | The following items should be discussed in the future. <how to synchronize HEP and MEA, MIA, MSA data acquisition sequence?> <how to synchronize ENA and other sensor’s data acquisition sequence?> <how to synchronize MPPE and other SI’s data acquisition sequence?> other SIs : WAVE, MERMAG |  |  |  | close | 2013-04-11 | 06 October 2011 MIA and MEA should be synchronizes as much as possible.H-mode triggering logic should be clarified 2013.4.11: sun synchronization: sun pulse timing = observation start timing for MEA/MIA/MSA | N.A. | N.A. | N.A. | N.A. | N.A.
050721-8 | All the teams will consider the necessary number of energy sweep modes (RAMs). It will be discussed in the future if we can have the systematic energy modes under unified sensor operation concept. |  |  |  | close | 2007-09-20 | MEA Mg. + Sol.2 MIA 2 Mg. +2 Sol. MSA Mg. +ExS+Sl 3
050721-9 | MSA will consider the data reduction method inside MSA. MSA will also consider what data processing by MDP is necessary. |  |  |  | close | 2005-11-10
050721-10 | ENA will consider what data processing by MDP is necessary. |  |  |  | close | 2005-11-10 | included in new A/I <A/I 051018-2>
050721-11 | HEP will consider what data processing by MDP is necessary. |  |  |  | close | 2005-11-10 | included in new A/I <A/I 051018-2>
050721-12 | MPPE will continue considering which option is the best for the final lossless compression. 1) 1 packet all the MPPE data 2) 3 different packets MIA, MEA, MSA data HEP ENA 3) 4 different packets MIA, MEA data MSA HEP ENA |  |  |  | close | 2005-11-10 | included in new A/I <A/I 051018-2>
050428-1 | Y. Saito will send web address of newest CDD version. http://www.stp.isas.jaxa.jp/mercury/mmo/official.html |  |  |  | close | 2005-05-09
050428-2 | revise CDD (Control Data Document) due : 13 May (Fri) each team -> Y. Saito |  |  |  | close | 2005-07-05 | MPPE-CDD “MPPE-CDD_V02” was submitted to MMO System.
050428-3 | Each team (MEA, MIA, MSA, HEP, ENA) will send Y. Saito information if -5V is necessary or not. If -5V is necessary, required power should also be informed. Due: Each team -> Y. Saito : by the end of June |  |  |  | close | 2005-07-21 | New A/I <A/I 050721-1>
050428-4 | PM+-12V: stability should be informed to MEA team by fabrication of HVPS requirement of MEA team -> system with in two weeks |  |  |  | close | 2005-07-21 | New A/I <A/I 050721-3>
050428-5 | MPPE will continue the discussion on data compression by e-mail. |  |  |  | close | 2005-07-21 | New A/I <A/I 050721- 9-12 >
050428-6 | Information will be sent from ISAS to everybody by end of MAY CPU processing power: Available CPU processing power for each team |  |  |  | close | 2005-07-21 | New A/I <A/I 050721-2>
050428-7 | Central purging : ISAS will start considering the detail. Detailed configuration should be determined after 1’ contractor selection. |  |  |  | close | 2010-04-06
050309-1 | ISAS will ask MMO system the possibility of “Installation of instrument thermal shield at very late phase : before installation of nose fairing (within total N2 purge suspension time) |  |  |  | close | 2005-04-28 | Depends on test schedule: Nominal: maybe several months… Encapsulation<-> MMO, MPO stacking:2years (worst case)
050309-2 | ISAS will check the following point: Central purging : Weight of the laying purge tubes on SPC: system side or MPPE side ? |  |  |  | close | 2005-04-28 | Using light tube & connector is necessary
050309-3 | Option a) COM2 is grounded in DC/DC converter in MDP COM2 and sensor chassis is insulated Sensor chassis and Spacecraft is connected Option b) COM2 is grounded in DC/DC converter in MDP COM2 and sensor chassis is connected Sensor chassis and Spacecraft is insulated MSA: either a) or b) is OK ENA: prefer a) MEA: prefer a) <connection between Spacecraft & chassis is necessary> MIA, HEP: prefer b) |  |  |  | close | 2005-04-28