## 確認事項
NO. | 確認事項 | 回答 | CLOSE

## List
|  | Duration (sec) | source filename | filename |  | cmdcount
BUS ON | BUS_SETUP | 687 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 25
BUS ON | BUS_SETUP_D | 577 | main2-BUS_NECP_HV_MONI_ON_XDOR_001_M60.cps | dcsm-EF_BUS_MONI_ON.cps |  | 20
MDP ON | MDP_SETUP | 509 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 11
| MDP_ON_D | 509 | dcsm-EF_MDP_ON | dcsm-EF_MDP_ON.cps |  | 11
| MDP_CRUISE_SET | 42 | main2-MDP_CRUISE_SET.cps | dcsm-EF_MDP_CRUISE_SET.cps |  | 2
SI Check | PWI_CHECK | 2672 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 56 |  | 180 | 348
| MGF_CHECK | 4179 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 52 |  | 168
| MASTWPT_CHECK | 2108 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 46
| MDM_CHECK | 1252 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 19
| ENA_CHECK | 1134 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 17
| MEA_CHECK | 4620 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 51
| MSA_CHECK | 1102 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 18
| MIA_CHECK | 1562 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 16
| HEP_CHECK | 4936 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80.cps |  | 82
| MSASI_CHECK | 6688 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80.cps |  | 22
MDP OFF | MDP_OFF | 120 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80.cps |  | 3
| MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | dcsm-EF_MDP_POWEROFF.cps |  | 3
BUS OFF | BUS_OFF | 220 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART4_XOR_002_M80.cps |  | 5
| BUS_OFF_D | 220 | dcsm-EF_BUS_MONI_OFF | dcsm-EF_BUS_MONI_OFF.cps |  | 5
| TCSF_MSASI | 345 | dcsm-tcfs_tbl1_msasi_set.cps | dcsm-tcfs_tbl1_msasi_set.cps |  | 13
SI Power ON | MSA_ON_SETUP | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON.cps |  | 15
| PME_ON | 80 | main2-PME_ON.cps | dcsm-EF_PME_ON.cps |  | 2
| PWI_ON_SETUP | 868 | dcsm-EF_PWI_ON_CRUSE.cps | dcsm-EF_PWI_ON_CRUISE.cps |  | 27 | 520
| MGF_ON_SETUP | 14 | 20200410_Earth-fly-by_MGF_ON_20200221.cps | dcsm-EF_MGF_ON.cps |  | 3
| MEA_ON_SETUP_SW | 386 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA_ON_SW.cps |  | 21
| MEA1_ON_SETUP_SW | 292 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA1_ON_SW.cps |  | 12
| MEA_ON_SETUP_MAG | 386 | MEA_Earth_Flyby_4_ON_HVOFF.cps | dcsm-EF_MEA_ON_MAG.cps |  | 21
| ENA_ON_SETUP | 564 | ENA_power_ON.cps | dcsm-EF_ENA_power_ON.cps |  | 7
| MIA_ON_SETUP | 382 | main2-MIA_ON.cps | dcsm-EF_MIA_ON.cps |  | 6
| HEP_ON_SETUP | 1230 | main2-HEP_ON_START_for_TL.cps | dcsm-EF_HEP_ON_START_for_TL.cps |  | 34
| MDM_ON_SETUP | 202 | クルーズ観測手順.txt | dcsm-EF_MDM_ON.cps | 暫定的に600sec入れてある | 6
SI HV ON | MEA_HV_ON | 1756 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA_HV_ON.cps |  | 54
| MEA1_HV_ON | 1702 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA1_HV_ON.cps |  | 27
| MIA_HV_ON | 240 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON.cps |  | 6
| MIA_HV_ON_MAG | 142 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG.cps |  | 4
| MIA_HV_ON_SW | 102 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW.cps |  | 3
| MIA_HV_ON_RC | 280 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON_RC.cps |  | 7
| MIA_HV_ON_MAG_RC | 262 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG_RC.cps |  | 7
| MIA_HV_ON_SW_RC | 262 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW_RC.cps |  | 7
| MSA_HV_ON | 10954 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1.cps,dcsm-EF_MSA_HV_ON_2.cps |  | 232
| MSA_HV_ON_VFB | 6144 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps |  | 232
| ENA_HV_ON | 344 | ENA_HV_ON.cps | dcsm-EF_ENA_HV_ON.cps |  | 18
| ENA_HV_ON_H | 344 | ENA_HV_ON_H.cps | dcsm-EF_ENA_HV_ON_H.cps |  | 18
| HEP_HV_ON | 270 | main2-HEPE_HV_ON_OBS_START.cps | dcsm-EF_HEPE_HV_ON_OBS_START.cps |  | 6
TLM mode change (MODE_5) | TLM_MODE_5 | 42 | main2-BUS_TLM_MODE_5.cps | dcsm-EF_BUS_TLM_MODE_5.cps |  | 2
TLM mode change (MODE_10) | TLM_MODE_10 | 42 | main2-BUS_TLM_MODE_10.cps | dcsm-EF_BUS_TLM_MODE_10.cps |  | 2
SI HV OFF | HEP_HV_OFF | 190 | main2-HEPE_HV_OFF_OBS_OFF.cps | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps |  | 5
| ENA_HV_OFF | 198 | ENA_HV_OFF.cps | dcsm-EF_ENA_HV_OFF.cps |  | 4
| MSA_HV_OFF | 714 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF.cps |  | 24
| MSA_HV_OFF_VFB | 774 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF_VFB.cps |  | 25
| MIA_HV_OFF | 60 | main2-MIA_HV_OFF.cps | dcsm-EF_MIA_HV_OFF.cps |  | 1
| MEA_HV_SCAN_OFF | 210 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA_HV_SCAN_OFF.cps |  | 24
| MEA1_HV_SCAN_OFF | 186 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA1_HV_SCAN_OFF.cps |  | 12
| MEA_HV_OFF | 202 | MEA_Earth_Flyby_6_ON_HVOFF.cps | dcsm-EF_MEA_HV_OFF.cps |  | 20
| MEA1_HV_OFF | 182 | dcsm-EF_MEA1_HV_OFF.cps | dcsm-EF_MEA1_HV_OFF.cps |  | 10
SI Power OFF | HEP_OFF | 70 | main2-HEPE_OFF_STOP.cps | dcsm-EF_HEPE_OFF_STOP.cps |  | 4
| MIA_OFF | 160 | main2-MIA_OFF.cps | dcsm-EF_MIA_OFF.cps |  | 4
| ENA_OFF | 88 | ENA_power_OFF.cps | dcsm-EF_ENA_power_OFF.cps |  | 4
| MEA_OFF | 164 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA_OFF.cps |  | 6
| MEA1_OFF | 160 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA1_OFF.cps |  | 4
| MGF_OFF | 8 | 20200410_Earth-fly-by_MGF_OFF_20200221.cps | dcsm-EF_MGF_OFF.cps |  | 1
| PWI_OFF | 80 | main2-PWI_OFF.cps | dcsm-EF_PWI_OFF.cps |  | 2
| PME_OFF | 40 | main2-PME_OFF.cps | dcsm-EF_PME_OFF.cps |  | 1
| MSA_OFF | 380 | main2-MSA_OFF.cps | dcsm-EF_MSA_OFF.cps |  | 25
| MDM_OFF | 160 | クルーズ観測手順.txt | dcsm-EF_MDM_OFF.cps | 暫定的に600sec入れてある | 4
MSA SOFT RESET | MSA_SOFT_RESET2 | 100 | dcsm-EF_MSA_SOFT_RESET2.cps | dcsm-EF_MSA_SOFT_RESET2.cps |  | 5
MACRO COMMAND ENA | MC_ENA | 246 | main2-MC_ENA_MDP_XDOR_001_M58.cps | dcsm-MC_ENA_MDP.cps |  | 21
| WAIT3600 | 3600
| WAIT3500 | 3500
| MSASI_DARK_1 | 768 | dcsm-MSASI_dark_CO_sequence1.cps | dcsm-MSASI_dark_CO_sequence1.cps |  | 11 | 19307
| MSASI_DARK_2 | 19498 | dcsm-MSASI_dark_CO_sequence2.cps | dcsm-MSASI_dark_CO_sequence2.cps |  | 55 | 19307
| MEA2_MEM_DMP | 2550 | dcsm-MEA2_MEM_DMP.cps | dcsm-MEA2_MEM_DMP.cps |  | 36
| WAIT19357 | 19357
| WAIT1800 | 1800 |  | WAIT_SEC 1800

## wheel offloading
|  | CA time | 2021-02-22 06:47
Time to CA [h] | ID |  | date time excel | duration(s)
0 | WOLS |  | 2021-02-22 06:47 | 1200 | WOL#1
| WOLE |  | 2021-02-22 07:07 | 0
19.255 | WOLS |  | 2021-02-23 02:03 | 1200 | WOL#2
| WOLE |  | 2021-02-23 02:23 | 0
-23.5 | WOLS |  | 2021-02-23 22:46 | 1200 | WOL#3
| WOLE |  | 2021-02-23 23:06 | 0
-14.5 | WOLS |  | 2021-02-25 03:25 | 1200 | WOL#4
| WOLE |  | 2021-02-25 03:45 | 0
-4.5 | WOLS |  | 2021-02-26 07:41 | 1200 | WOL#5 | Power cycle
| WOLE |  | 2021-02-26 08:01 | 0
6.5 | WOLS |  | 2021-02-27 07:17 | 1200 | WOL#6
| WOLE |  | 2021-02-27 07:37 | 0
24.5 | WOLS |  | 2021-02-28 03:43 | 1200 | WOL#7
| WOLE |  | 2021-02-28 04:03 | 0
42.5 | WOLS |  | 2021-03-01 03:14 | 1200 | WOL#8
| WOLE |  | 2021-03-01 03:34 | 0
| WOLS |  | 2021-03-02 06:23 | 1200 | WOL#9
| WOLE |  | 2021-03-02 06:43 | 0
Formulas:
date time excel = D1+[Time to CA [h]]/24
date time excel = [date time excel, row above]+[duration(s), row above]/3600/24

## 2021_2_22-23
# 2020/07/28 | [9 empty] | 5days
# WOL#1 |  | 2021-02-22 06:47 | [7 empty] | 495
# WOL#2 |  | 2021-02-23 02:03 | [7 empty] | sum
# WOL#3 |  | 2021-02-23 22:46
# WOL#4 |  | 2021-02-25 03:25
# WOL#5 |  | 2021-02-26 07:41
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 198
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2021-02-22 06:22 | 2021-02-22 06:32 |  | BUS ON | BUS_SETUP_D | 577 |  | dcsm-EF_BUS_MONI_ON.cps | 20
|  | 2021-02-22 06:32 | 2021-02-22 06:40 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2021-02-22 06:40 | 2021-02-22 06:41 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2021-02-22 06:41 | 2021-02-22 06:42 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-22 06:42 | 2021-02-22 06:46 |  | SI Power ON | MEA1_ON_SETUP_SW | 292 |  | dcsm-EF_MEA1_ON_SW.cps | 12
|  | 2021-02-22 06:46 | 2021-02-22 07:07 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2021-02-22 06:47 | 2021-02-22 07:07 | # WOL#1 |  | 600 | 1200 |  | #N/A | 0
|  | 2021-02-22 07:17 | 2021-02-22 07:45 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-22 07:45 | 2021-02-22 07:50 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-22 07:50 | 2021-02-22 07:51 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-22 07:51 | 2021-02-23 01:56 | Observation A |  |  | 65132 | 18.0922 |  | 0
|  | 2021-02-23 01:56 | 2021-02-23 01:57 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-23 01:57 | 2021-02-23 02:00 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-23 02:00 | 2021-02-23 02:03 |  |  | MEA1_HV_OFF | 182 |  | dcsm-EF_MEA1_HV_OFF.cps | 10
|  | 2021-02-23 02:03 | 2021-02-23 02:23 | # WOL#2 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-23 02:33 | 2021-02-23 03:01 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-23 03:01 | 2021-02-23 03:06 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-23 03:06 | 2021-02-23 03:07 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-23 03:07 | 2021-02-23 22:33 | Observation B |  |  | 69999 | 19.4442 |  | 0
|  | 2021-02-23 22:33 | 2021-02-23 22:34 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-23 22:34 | 2021-02-23 22:37 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-23 22:37 | 2021-02-23 22:40 |  |  | MEA1_HV_SCAN_OFF | 186 |  | dcsm-EF_MEA1_HV_SCAN_OFF.cps | 12
|  | 2021-02-23 22:40 | 2021-02-23 22:41 |  | SI OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2021-02-23 22:41 | 2021-02-23 22:44 |  |  | MEA1_OFF | 160 |  | dcsm-EF_MEA1_OFF.cps | 4
|  | 2021-02-23 22:44 | 2021-02-23 22:46 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2021-02-23 22:46 | 2021-02-23 23:06 | # WOL#3 |  | #REF! | 1200 |  | #REF! | 0
Formulas:
Start = [End]-[Duration (sec)]/3600/24
Start = [End, row above]+10/60/24
End = [Start, row below]
End = [End, row below]

## 2021_2_23-26
# 2020/07/28 | [9 empty] | 5days
# WOL#3 |  | 2021-02-23 22:46 | [7 empty] | 497.5
# WOL#4 |  | 2021-02-25 03:25 | [7 empty] | sum
# WOL#5 |  | 2021-02-26 07:41
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 199
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2021-02-23 22:46 | 2021-02-23 23:06 | # WOL#3 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-23 23:16 | 2021-02-23 23:20 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP.cps | 21
|  | 2021-02-23 23:20 | 2021-02-23 23:29 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2021-02-23 23:29 | 2021-02-23 23:29 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2021-02-23 23:29 | 2021-02-23 23:30 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-23 23:30 | 2021-02-23 23:35 |  | SI Power ON | MEA1_ON_SETUP_SW | 292 |  | dcsm-EF_MEA1_ON_SW.cps | 12
|  | 2021-02-23 23:35 | 2021-02-23 23:55 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2021-02-23 23:55 | 2021-02-24 00:24 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-24 00:24 | 2021-02-24 00:28 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-24 00:28 | 2021-02-24 00:29 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-24 00:29 | 2021-02-25 03:18 | Observation C |  |  | 96530 | 26.8139 |  | 0
|  | 2021-02-25 03:18 | 2021-02-25 03:18 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-25 03:18 | 2021-02-25 03:22 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-25 03:22 | 2021-02-25 03:25 |  |  | MEA1_HV_OFF | 182 |  | dcsm-EF_MEA1_HV_OFF.cps | 10
|  | 2021-02-25 03:25 | 2021-02-25 03:45 | # WOL#4 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-25 03:55 | 2021-02-25 04:23 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-25 04:23 | 2021-02-25 04:28 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-25 04:28 | 2021-02-25 04:28 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-25 04:28 | 2021-02-26 07:29 | Observation D |  |  | 97228 | 27.0078 |  | 0
|  | 2021-02-26 07:29 | 2021-02-26 07:29 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-26 07:29 | 2021-02-26 07:33 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-26 07:33 | 2021-02-26 07:36 |  |  | MEA1_HV_SCAN_OFF | 186 |  | dcsm-EF_MEA1_HV_SCAN_OFF.cps | 12
|  | 2021-02-26 07:36 | 2021-02-26 07:37 |  | SI OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2021-02-26 07:37 | 2021-02-26 07:39 |  |  | MEA1_OFF | 160 |  | dcsm-EF_MEA1_OFF.cps | 4
|  | 2021-02-26 07:39 | 2021-02-26 07:41 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2021-02-26 07:41 | 2021-02-26 08:01 | # WOL#5 |  | #REF! | 1200 |  | #REF! | 0
Formulas:
Start = [End, row above]+10/60/24
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24
End = [Start, row below]

## 2021_2_26-28
# 2020/07/28 | [9 empty] | 5days
# WOL#5 |  | 2021-02-26 07:41 | [7 empty] | 497.5
# WOL#6 |  | 2021-02-27 07:17 | [7 empty] | sum
# WOL#7 |  | 2021-02-28 03:43
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 199
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2021-02-26 07:41 | 2021-02-26 08:01 | # WOL#5 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-26 08:11 | 2021-02-26 08:16 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP.cps | 21
|  | 2021-02-26 08:16 | 2021-02-26 08:24 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2021-02-26 08:24 | 2021-02-26 08:25 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2021-02-26 08:25 | 2021-02-26 08:25 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-26 08:25 | 2021-02-26 08:30 |  | SI Power ON | MEA1_ON_SETUP_SW | 292 |  | dcsm-EF_MEA1_ON_SW.cps | 12
|  | 2021-02-26 08:30 | 2021-02-26 08:51 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2021-02-26 08:51 | 2021-02-26 09:19 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-26 09:19 | 2021-02-26 09:24 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-26 09:24 | 2021-02-26 09:24 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-26 09:24 | 2021-02-27 07:10 | Observation E |  |  | 78329 | 21.7581 |  | 0
|  | 2021-02-27 07:10 | 2021-02-27 07:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-27 07:11 | 2021-02-27 07:14 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-27 07:14 | 2021-02-27 07:17 |  |  | MEA1_HV_OFF | 182 |  | dcsm-EF_MEA1_HV_OFF.cps | 10
|  | 2021-02-27 07:17 | 2021-02-27 07:37 | # WOL#6 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-27 07:47 | 2021-02-27 08:15 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-27 08:15 | 2021-02-27 08:20 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-27 08:20 | 2021-02-27 08:20 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-27 08:20 | 2021-02-28 03:31 | Observation F |  |  | 69015 | 19.1708 |  | 0
|  | 2021-02-28 03:31 | 2021-02-28 03:31 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-28 03:31 | 2021-02-28 03:34 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-02-28 03:34 | 2021-02-28 03:38 |  |  | MEA1_HV_SCAN_OFF | 186 |  | dcsm-EF_MEA1_HV_SCAN_OFF.cps | 12
|  | 2021-02-28 03:38 | 2021-02-28 03:39 |  | SI OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2021-02-28 03:39 | 2021-02-28 03:41 |  |  | MEA1_OFF | 160 |  | dcsm-EF_MEA1_OFF.cps | 4
|  | 2021-02-28 03:41 | 2021-02-28 03:43 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2021-02-28 03:43 | 2021-02-28 04:03 | # WOL#7 |  | #REF! | 1200 |  | #REF! | 0
Formulas:
Start = [End, row above]+10/60/24
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24
End = [Start, row below]

## 2021_2_28-3_2
# 2020/07/28 | [9 empty] | 5days
# WOL#7 |  | 2021-02-28 03:43 | [7 empty] | 497.5
# WOL#8 |  | 2021-03-01 03:14 | [7 empty] | sum
# WOL#9 |  | 2021-03-02 06:23
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 199
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2021-02-28 03:43 | 2021-02-28 04:03 | # WOL#7 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-02-28 04:13 | 2021-02-28 04:17 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP.cps | 21
|  | 2021-02-28 04:17 | 2021-02-28 04:26 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2021-02-28 04:26 | 2021-02-28 04:27 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2021-02-28 04:27 | 2021-02-28 04:27 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-02-28 04:27 | 2021-02-28 04:32 |  | SI Power ON | MEA1_ON_SETUP_SW | 292 |  | dcsm-EF_MEA1_ON_SW.cps | 12
|  | 2021-02-28 04:32 | 2021-02-28 04:53 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2021-02-28 04:53 | 2021-02-28 05:21 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-02-28 05:21 | 2021-02-28 05:26 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-02-28 05:26 | 2021-02-28 05:26 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-02-28 05:26 | 2021-03-01 03:07 | Observation G |  |  | 78033 | 21.6758 |  | 0
|  | 2021-03-01 03:07 | 2021-03-01 03:08 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-03-01 03:08 | 2021-03-01 03:11 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-03-01 03:11 | 2021-03-01 03:14 |  |  | MEA1_HV_OFF | 182 |  | dcsm-EF_MEA1_HV_OFF.cps | 10
|  | 2021-03-01 03:14 | 2021-03-01 03:34 | # WOL#8 |  | 1800 | 1200 |  | #N/A | 0
|  | 2021-03-01 03:44 | 2021-03-01 04:12 |  | SI HV ON | MEA1_HV_ON | 1702 |  | dcsm-EF_MEA1_HV_ON.cps | 27
|  | 2021-03-01 04:12 | 2021-03-01 04:17 |  |  | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2021-03-01 04:17 | 2021-03-01 04:17 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2021-03-01 04:17 | 2021-03-02 06:10 | Observation H |  |  | 93189 | 25.8858 |  | 0
|  | 2021-03-02 06:10 | 2021-03-02 06:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2021-03-02 06:11 | 2021-03-02 06:14 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2021-03-02 06:14 | 2021-03-02 06:17 |  |  | MEA1_HV_SCAN_OFF | 186 |  | dcsm-EF_MEA1_HV_SCAN_OFF.cps | 12
|  | 2021-03-02 06:17 | 2021-03-02 06:19 |  | SI OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2021-03-02 06:19 | 2021-03-02 06:21 |  |  | MEA1_OFF | 160 |  | dcsm-EF_MEA1_OFF.cps | 4
|  | 2021-03-02 06:21 | 2021-03-02 06:23 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2021-03-02 06:23 | 2021-03-02 06:43 | # WOL#9 |  | #REF! | 1200 |  | #REF! | 0
Formulas:
Start = [End, row above]+10/60/24
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24
End = [Start, row below]