## 確認事項
NO. | 確認事項 | 回答 | CLOSE

## List
|  | Duration (sec) | source filename | filename |  | cmdcount
BUS ON | BUS_SETUP | 577 | main2-BUS_NECP_HV_MONI_ON_XDOR_001_M60.cps | dcsm-EF_BUS_MONI_ON |  | 20
MDP ON | MDP_SETUP | 509 | main2-MDP_NECP_HV_ON_XDOR_001_M55.cps | dcsm-EF_MDP_ON |  | 11
| MDP_ON_D | 509 | dcsm-EF_MDP_ON | dcsm-EF_MDP_ON |  | 11
| MDP_CRUISE_SET | 42 | main2-MDP_CRUISE_SET.cps | dcsm-EF_MDP_CRUISE_SET |  | 2
SI Power ON | MSA_ON_SETUP | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON |  | 15
| PME_ON | 80 | main2-PME_ON.cps | dcsm-EF_PME_ON |  | 2
| PWI_ON_SETUP | 868 | dcsm-EF_PWI_ON_CRUSE.cps | dcsm-EF_PWI_ON_CRUISE |  | 27 | 520 | 180 | 868
| MGF_ON_SETUP | 14 | 20200410_Earth-fly-by_MGF_ON_20200221.cps | dcsm-EF_MGF_ON |  | 3 |  | 168
| MEA_ON_SETUP_SW | 386 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA_ON_SW |  | 21
| MEA1_ON_SETUP_SW | 292 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA1_ON_SW |  | 12
| MEA_ON_SETUP_MAG | 386 | MEA_Earth_Flyby_4_ON_HVOFF.cps | dcsm-EF_MEA_ON_MAG |  | 21
| ENA_ON_SETUP | 564 | ENA_power_ON.cps | dcsm-EF_ENA_power_ON |  | 7
| MIA_ON_SETUP | 382 | main2-MIA_ON.cps | dcsm-EF_MIA_ON |  | 6
| MIA_ON_C | 582 |  | dcsm-EF_MIA_ON_C |  | 12
| HEP_ON_SETUP | 1230 | main2-HEP_ON_START_for_TL.cps | dcsm-EF_HEP_ON_START_for_TL |  | 34
| MDM_ON_SETUP | 202 | クルーズ観測手順.txt | dcsm-EF_MDM_ON | 暫定的に600sec入れてある | 6
SI HV ON | MEA_HV_ON | 1756 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA_HV_ON |  | 54
| MEA1_HV_ON | 1702 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA1_HV_ON |  | 27
| MIA_HV_ON | 240 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON |  | 6
| MIA_HV_ON_MAG | 142 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG |  | 4
| MIA_HV_ON_SW | 102 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW |  | 3
| MIA_HV_ON_RC | 280 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON_RC |  | 7
| MIA_HV_ON_MAG_RC | 262 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG_RC |  | 7
| MIA_HV_ON_SW_RC | 262 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW_RC |  | 7
| MSA_HV_ON | 10954 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1,dcsm-EF_MSA_HV_ON_2 |  | 232
| MSA_HV_ON_VFB | 6144 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB |  | 232
| ENA_HV_ON | 344 | ENA_HV_ON.cps | dcsm-EF_ENA_HV_ON |  | 18
| ENA_HV_ON_H | 344 | ENA_HV_ON_H.cps | dcsm-EF_ENA_HV_ON_H |  | 18
| HEP_HV_ON | 270 | main2-HEPE_HV_ON_OBS_START.cps | dcsm-EF_HEPE_HV_ON_OBS_START |  | 6
TLM mode change (MODE_5) | TLM_MODE_5 | 42 | main2-BUS_TLM_MODE_5.cps | dcsm-EF_BUS_TLM_MODE_5 |  | 2
TLM mode change (MODE_10) | TLM_MODE_10 | 42 | main2-BUS_TLM_MODE_10.cps | dcsm-EF_BUS_TLM_MODE_10 |  | 2
SI HV OFF | HEP_HV_OFF | 190 | main2-HEPE_HV_OFF_OBS_OFF.cps | dcsm-EF_HEPE_HV_OFF_OBS_OFF |  | 5
| ENA_HV_OFF | 198 | ENA_HV_OFF.cps | dcsm-EF_ENA_HV_OFF |  | 4
| MSA_HV_OFF | 714 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF |  | 24
| MSA_HV_OFF_VFB | 774 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF_VFB |  | 25
| MIA_HV_OFF | 60 | main2-MIA_HV_OFF.cps | dcsm-EF_MIA_HV_OFF |  | 1
| MEA_HV_SCAN_OFF | 210 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA_HV_SCAN_OFF |  | 24
| MEA1_HV_SCAN_OFF | 186 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA1_HV_SCAN_OFF |  | 12
| MEA_HV_OFF | 202 | MEA_Earth_Flyby_6_ON_HVOFF.cps | dcsm-EF_MEA_HV_OFF |  | 20
| MEA1_HV_OFF | 182 | dcsm-EF_MEA1_HV_OFF.cps | dcsm-EF_MEA1_HV_OFF |  | 10
SI Power OFF | HEP_OFF | 70 | main2-HEPE_OFF_STOP.cps | dcsm-EF_HEPE_OFF_STOP |  | 4
| MIA_OFF | 160 | main2-MIA_OFF.cps | dcsm-EF_MIA_OFF |  | 4
| ENA_OFF | 88 | ENA_power_OFF.cps | dcsm-EF_ENA_power_OFF |  | 4
| MEA_OFF | 164 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA_OFF |  | 6
| MEA1_OFF | 160 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA1_OFF |  | 4
| MGF_OFF | 8 | 20200410_Earth-fly-by_MGF_OFF_20200221.cps | dcsm-EF_MGF_OFF |  | 1
| PWI_OFF | 80 | main2-PWI_OFF.cps | dcsm-EF_PWI_OFF |  | 2
| PME_OFF | 40 | main2-PME_OFF.cps | dcsm-EF_PME_OFF |  | 1
| MSA_OFF | 380 | main2-MSA_OFF.cps | dcsm-EF_MSA_OFF |  | 25
| MDM_OFF | 160 | クルーズ観測手順.txt | dcsm-EF_MDM_OFF | 暫定的に600sec入れてある | 4
MDP OFF | MDP_OFF | 120 | main2-MDP_NECP_HV_POWEROFF_XDOR_001_M56.cps | dcsm-EF_MDP_POWEROFF |  | 3
| MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | dcsm-EF_MDP_POWEROFF |  | 3
BUS OFF | BUS_OFF | 220 | main2-BUS_NECP_HV_MONI_OFF_XDOR_001_M61.cps | dcsm-EF_BUS_MONI_OFF |  | 4
| BUS_OFF_D | 220 | dcsm-EF_BUS_MONI_OFF | dcsm-EF_BUS_MONI_OFF |  | 5
| TCSF_MSASI | 345 | dcsm-tcfs_tbl1_msasi_set.cps | dcsm-tcfs_tbl1_msasi_set |  | 13
| MEA_OFF | 0
MDP ERR DUMP | MDP_DUMP | 9080 | main2-MDP_ERR_LOG_DUMP_TL_XDOR_001_M08.cps | dcsm-EF_MDP_ERR_DUMP |  | 6
MDP AP9 DUMP | MDP_AP9_DUMP | 1880 | main2-MDP_AP09_LOG_DUMP_001_M08.cps | dcsm-MDP_AP09_LOG_DUMP |  | 4
MACRO COMMAND ENA | MC_ENA | 246 | main2-MC_ENA_MDP_XDOR_001_M58.cps | dcsm-MC_ENA_MDP |  | 21
| MSA_HV_ON_N | 0
| MSA_HV_OFF_N | 0
MSA SOFT RESET | MSA_SOFT_RESET2 | 100 | dcsm-EF_MSA_SOFT_RESET2.cps | dcsm-EF_MSA_SOFT_RESET2 |  | 5
MSA SOFT RESET | MSA_SOFT_RESET | 120 |  | dcsm-EF_MSA_SOFT_RESET |  | 3
| WAIT3600 | 3600 |  | WAIT_SEC 3600
| WAIT3500 | 3500
| MSASI_DARK_1 | 768 | dcsm-MSASI_dark_CO_sequence1.cps | dcsm-MSASI_dark_CO_sequence1 |  | 11 | 19307
| MSASI_DARK_2 | 19498 | dcsm-MSASI_dark_CO_sequence2.cps | dcsm-MSASI_dark_CO_sequence2 |  | 55 | 19307
| MEA2_MEM_DMP | 2550 | dcsm-MEA2_MEM_DMP.cps | dcsm-MEA2_MEM_DMP |  | 36
| WAIT19357 | 19357
| WAIT139168 | 139168 | 139168 | WAIT_SEC 139168
| WAIT1800 | 1800 |  | WAIT_SEC 1800
| MDP_ERR_LOG_DUMP | 9080 | main2-MDP_ERR_LOG_DUMP_TL_XDOR_001_M08 | dcsm-MDP_ERR_LOG_DUMP |  | 6
CrouseCheckOut | CRCO_BUS_MONI_ON | 310 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_BUS_MONI_ON |  | 10
| CRCO_ENA | 1134 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_ENA_CHECK |  | 18
| CRCO_HEPE | 2206 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPE_CHECK |  | 36
| CRCO_HEPI | 2730 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPI_CHECK |  | 48
| CRCO_MASTWPT | 1848 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MASTWPT_CHECK |  | 41
| CRCO_MDM | 2332 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDM_CHECK |  | 45
| CRCO_MDP_OFF | 120 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_OFF |  | 4
| CRCO_MDP_ON | 509 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_ON |  | 12
| CRCO_MEA | 4620 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MEA_CHECK |  | 52
| CRCO_MGF | 4019 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MGF_CHECK |  | 49
| CRCO_MIA | 1562 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MIA_CHECK |  | 17
| CRCO_MIA_C | 1892 |  | dcsm-CRCO_MIA_CHECK_C |  | 20
| CRCO_MSASI | 6688 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSASI_CHECK |  | 23
| CRCO_MSA_C | 1102 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSA_CHECK_C |  | 19
| CRCO_MSA | 1102 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSA_CHECK |  | 19
| CRCO_PME_OFF | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_OFF |  | 5
| CRCO_PME_ON | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_ON |  | 5
| CRCO_PWI | 2512 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PWI_CHECK |  | 51
| CRCO_SI_READY | 377 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_SI_READY |  | 17
| MSA_TBL_UP1 | 7558 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C636_NECP_M185001_00001 |  | 8
| MSA_TBL_UP2 | 948 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C637_NECP_M185002_00001 |  | 4
| MSA_TBL_UP3 | 160 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C638_NECP_M185003_00001 |  | 4
| MSA_ON_SETUP_C | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON_C |  | 15
MDP TABLE UPLOAD | T_MDP_ON | 200 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C887_NECP_M700101_00002.BC
| T_MDP_DPU1 | 40 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C888_NECP_M700201_00001.BC
| T_MDP_DPU1_LOAD | 232 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C889_NECP_M700202_00008.BC
| T_MDP_DPU1_DUMP | 6000 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C890_NECP_M700203_00001.BC
| T_MDP_DPU2_LOAD | 232 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C891_NECP_M700204_00008.BC
| T_MDP_DPU2_DUMP | 6000 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C892_NECP_M700205_00002.BC
| T_MDP_OFF | 80 | main2-MDP_EEPROM_UPLOAD_XDOR_009_M70 | XDOR_BJXR_C893_NECP_M700301_00002.BC

## wheel offloading
|  | CA time | 2021-08-10 13:48
Time to CA [h] | ID |  | date time excel | duration(s)
-37.5 | WOLS |  | 2021-08-09 00:18 | 1200 | WOL#0
| WOLE |  | 2021-08-09 00:38 | 0
-22.5 | WOLS |  | 2021-08-09 15:18 | 1200 | WOL#1
| WOLE |  | 2021-08-09 15:38 | 0
-8 | WOLS |  | 2021-08-10 05:49 | 1200 | WOL#2
| WOLE |  | 2021-08-10 06:09 | 0
-4.3333 | WOLS |  | 2021-08-10 09:29 | 1200 | WOL#3
| WOLE |  | 2021-08-10 09:49 | 0
1 | WOLS |  | 2021-08-10 14:49 | 1200 | WOL#4
| WOLE |  | 2021-08-10 15:09 | 0
9 | WOLS |  | 2021-08-10 22:48 | 1200 | WOL#5
| WOLE |  | 2021-08-10 23:08 | 0
21 | WOLS |  | 2021-08-11 10:48 | 1200 | WOL#6
| WOLE |  | 2021-08-11 11:08 | 0
33.5 | WOLS |  |  | 1200 | WOL#7
| WOLE |  |  | 0
Formulas:
date time excel = D1+[Time to CA [h]]/24
date time excel = [date time excel, row above]+[duration(s), row above]/3600/24

## 21-08-9_11
START |  |  | 2021-08-06 19:00
# WOL#0 |  | 2021-08-09 00:18
# WOL#1 |  | 2021-08-09 15:18 | [7 empty] | sum
# WOL#2 |  | 2021-08-10 05:49
# WOL#3 |  | 2021-08-10 09:29
# WOL#4 |  | 2021-08-10 14:49
# WOL#5 |  | 2021-08-10 22:48
# WOL#6 |  | 2021-08-11 10:48
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 2556
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2021-08-06 19:00 | 2021-08-06 19:10 |  | BUS ON | BUS_SETUP | 577 |  | dcsm-EF_BUS_MONI_ON | 20 |  | 0000 CALL dcsm-EF_BUS_MONI_ON -Run | cp dcsm-EF_BUS_MONI_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_MONI_ON -Run | 1
|  | 2021-08-06 19:10 | 2021-08-06 19:18 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run | cp dcsm-EF_MDP_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MDP_ON -Run | 1
|  | 2021-08-06 19:18 | 2021-08-06 19:19 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-06 19:19 | 2021-08-06 19:37 |  | MSA ON | MSA_ON_SETUP_C | 1092 |  | dcsm-EF_MSA_ON_C | 15 |  | 0000 CALL dcsm-EF_MSA_ON_C -Run | cp dcsm-EF_MSA_ON_C /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_ON_C -Run | 1
|  | 2021-08-06 19:37 | 2021-08-06 20:37 | WAIT |  | 3600 | 3600 | [5 empty] | cp /tmp/dcsm
|  | 2021-08-06 20:37 | 2021-08-06 20:43 |  | MSA OFF | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF | 25 |  | 0000 CALL dcsm-EF_MSA_OFF -Run | cp dcsm-EF_MSA_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_OFF -Run | 0
|  | 2021-08-06 20:43 | 2021-08-06 20:45 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF | 3 |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | cp dcsm-EF_MDP_POWEROFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | 0
|  | 2021-08-06 20:45 | 2021-08-06 20:54 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run | cp dcsm-EF_MDP_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MDP_ON -Run | 0
|  | 2021-08-06 20:54 | 2021-08-06 21:12 |  | MSA ON | MSA_ON_SETUP_C | 1092 |  | dcsm-EF_MSA_ON_C | 15 |  | 0000 CALL dcsm-EF_MSA_ON_C -Run | cp dcsm-EF_MSA_ON_C /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_ON_C -Run | 0
|  | 2021-08-06 21:12 | 2021-08-06 21:13 |  | MDP CRUSE SET | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET | 2 |  | 0000 CALL dcsm-EF_MDP_CRUISE_SET -Run | cp dcsm-EF_MDP_CRUISE_SET /tmp/dcsm |  | 0000 CALL dcsm-EF_MDP_CRUISE_SET -Run | 0
|  | 2021-08-06 21:13 | 2021-08-08 23:13 | WAIT |  |  | 180021 | 50.0058 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  |  | 0
|  | 2021-08-08 23:13 | 2021-08-08 23:14 |  |  | PME_ON | 80 |  | dcsm-EF_PME_ON | 2 |  | 0000 CALL dcsm-EF_PME_ON -Run | cp dcsm-EF_PME_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_PME_ON -Run | 0
|  | 2021-08-08 23:14 | 2021-08-08 23:29 |  |  | PWI_ON_SETUP | 868 |  | dcsm-EF_PWI_ON_CRUISE | 27 |  | 0000 CALL dcsm-EF_PWI_ON_CRUISE -Run | cp dcsm-EF_PWI_ON_CRUISE /tmp/dcsm |  | 0000 CALL dcsm-EF_PWI_ON_CRUISE -Run | 0
|  | 2021-08-08 23:29 | 2021-08-08 23:29 |  |  | MGF_ON_SETUP | 14 |  | dcsm-EF_MGF_ON | 3 |  | 0000 CALL dcsm-EF_MGF_ON -Run | cp dcsm-EF_MGF_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MGF_ON -Run | 0
|  | 2021-08-08 23:29 | 2021-08-08 23:36 |  |  | MEA_ON_SETUP_SW | 386 |  | dcsm-EF_MEA_ON_SW | 21 |  | 0000 CALL dcsm-EF_MEA_ON_SW -Run | cp dcsm-EF_MEA_ON_SW /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_ON_SW -Run | 0
|  | 2021-08-08 23:36 | 2021-08-08 23:45 |  |  | ENA_ON_SETUP | 564 |  | dcsm-EF_ENA_power_ON | 7 |  | 0000 CALL dcsm-EF_ENA_power_ON -Run | cp dcsm-EF_ENA_power_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_power_ON -Run | 0
|  | 2021-08-08 23:45 | 2021-08-08 23:55 |  |  | MIA_ON_C | 582 |  | dcsm-EF_MIA_ON_C | 12 |  | 0000 CALL dcsm-EF_MIA_ON_C -Run | cp dcsm-EF_MIA_ON_C /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_ON_C -Run | 0
|  | 2021-08-08 23:55 | 2021-08-09 00:15 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL | 34 |  | 0000 CALL dcsm-EF_HEP_ON_START_for_TL -Run | cp dcsm-EF_HEP_ON_START_for_TL /tmp/dcsm |  | 0000 CALL dcsm-EF_HEP_ON_START_for_TL -Run | 0
|  | 2021-08-09 00:15 | 2021-08-09 00:18 |  |  | MDM_ON_SETUP | 202 |  | dcsm-EF_MDM_ON | 6 |  | 0000 CALL dcsm-EF_MDM_ON -Run | cp dcsm-EF_MDM_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MDM_ON -Run | 1
|  | 2021-08-09 00:18 | 2021-08-09 00:38 | # WOL#0 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  |  | 1
|  | 2021-08-09 00:49 | 2021-08-09 00:53 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-09 00:53 | 2021-08-09 00:59 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-09 00:59 | 2021-08-09 01:03 |  |  | MIA_HV_ON_RC | 280 | Safety ON | dcsm-EF_MIA_HV_ON_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | cp dcsm-EF_MIA_HV_ON_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | 1
|  | 2021-08-09 01:03 | 2021-08-09 01:33 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-09 01:33 | 2021-08-09 03:15 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-09 03:15 | 2021-08-09 03:16 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-09 03:16 | 2021-08-09 14:54 | Observation A |  |  | 41898 | 11.6383 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-09 14:54 | 2021-08-09 14:55 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-09 14:55 | 2021-08-09 14:58 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-09 14:58 | 2021-08-09 15:01 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-09 15:01 | 2021-08-09 15:14 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-09 15:14 | 2021-08-09 15:15 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-09 15:15 | 2021-08-09 15:18 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | cp dcsm-EF_MEA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | 1
|  | 2021-08-09 15:18 | 2021-08-09 15:38 | # WOL#1 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  | 0446 WAIT_SEC 1800 | 0
|  | 2021-08-09 15:49 | 2021-08-09 15:53 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-09 15:53 | 2021-08-09 15:59 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-09 15:59 | 2021-08-09 16:03 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | cp dcsm-EF_MIA_HV_ON_SW_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | 1
|  | 2021-08-09 16:03 | 2021-08-09 16:32 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-09 16:32 | 2021-08-09 18:15 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-09 18:15 | 2021-08-09 18:15 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-09 18:15 | 2021-08-10 05:24 | Observation B |  |  | 40116 | 11.1433 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-10 05:24 | 2021-08-10 05:25 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-10 05:25 | 2021-08-10 05:28 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-10 05:28 | 2021-08-10 05:31 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-10 05:31 | 2021-08-10 05:44 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-10 05:44 | 2021-08-10 05:45 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-10 05:45 | 2021-08-10 05:49 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | cp dcsm-EF_MEA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | 1
|  | 2021-08-10 05:49 | 2021-08-10 06:09 | # WOL#2 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  | 0446 WAIT_SEC 1800 | 0
|  | 2021-08-10 06:18 | 2021-08-10 06:23 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-10 06:23 | 2021-08-10 06:29 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-10 06:29 | 2021-08-10 06:33 |  |  | MIA_HV_ON_MAG_RC | 262 | Safety OFF 磁気圏モード | dcsm-EF_MIA_HV_ON_MAG_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_MAG_RC -Run | cp dcsm-EF_MIA_HV_ON_MAG_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | 0
|  | 2021-08-10 06:33 | 2021-08-10 07:02 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-10 07:02 | 2021-08-10 08:45 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-10 08:45 | 2021-08-10 08:45 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-10 08:45 | 2021-08-10 09:04 | Observation C |  |  | 1116.12 | 0.31003 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-10 09:04 | 2021-08-10 09:05 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-10 09:05 | 2021-08-10 09:08 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-10 09:08 | 2021-08-10 09:11 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-10 09:11 | 2021-08-10 09:24 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-10 09:24 | 2021-08-10 09:25 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-10 09:25 | 2021-08-10 09:29 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | cp dcsm-EF_MEA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | 1
|  | 2021-08-10 09:29 | 2021-08-10 09:49 | # WOL#3 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  | 0446 WAIT_SEC 1800 | 0
|  | 2021-08-10 09:59 | 2021-08-10 10:03 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-10 10:03 | 2021-08-10 10:09 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-10 10:09 | 2021-08-10 10:13 |  |  | MIA_HV_ON_MAG_RC | 262 | Safety OFF 磁気圏モード | dcsm-EF_MIA_HV_ON_MAG_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_MAG_RC -Run | cp dcsm-EF_MIA_HV_ON_MAG_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | 0
|  | 2021-08-10 10:13 | 2021-08-10 10:42 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-10 10:42 | 2021-08-10 12:25 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-10 12:25 | 2021-08-10 12:25 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-10 12:25 | 2021-08-10 14:24 | Observation D |  |  | 7115.88 | 1.9766 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-10 14:24 | 2021-08-10 14:25 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-10 14:25 | 2021-08-10 14:28 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-10 14:28 | 2021-08-10 14:31 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-10 14:31 | 2021-08-10 14:44 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-10 14:44 | 2021-08-10 14:45 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-10 14:45 | 2021-08-10 14:49 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | cp dcsm-EF_MEA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | 1
|  | 2021-08-10 14:49 | 2021-08-10 15:09 | # WOL#4 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  | 0446 WAIT_SEC 1800 | 0
|  | 2021-08-10 15:18 | 2021-08-10 15:23 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-10 15:23 | 2021-08-10 15:29 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-10 15:29 | 2021-08-10 15:33 |  |  | MIA_HV_ON_MAG_RC | 262 | Safety OFF 磁気圏モード | dcsm-EF_MIA_HV_ON_MAG_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_MAG_RC -Run | cp dcsm-EF_MIA_HV_ON_MAG_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | 0
|  | 2021-08-10 15:33 | 2021-08-10 16:02 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-10 16:02 | 2021-08-10 17:45 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-10 17:45 | 2021-08-10 17:45 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-10 17:45 | 2021-08-10 22:24 | Observation E |  |  | 16716 | 4.6433 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-10 22:24 | 2021-08-10 22:25 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-10 22:25 | 2021-08-10 22:28 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-10 22:28 | 2021-08-10 22:31 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-10 22:31 | 2021-08-10 22:44 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-10 22:44 | 2021-08-10 22:45 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-10 22:45 | 2021-08-10 22:48 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | cp dcsm-EF_MEA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | 1
|  | 2021-08-10 22:48 | 2021-08-10 23:08 | # WOL#5 |  | 1800 | 1200 |  | #N/A | 0 |  |  | #N/A |  | 0446 WAIT_SEC 1800 | 0
|  | 2021-08-10 23:19 | 2021-08-10 23:23 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | cp dcsm-EF_HEPE_HV_ON_OBS_START /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | 1
|  | 2021-08-10 23:23 | 2021-08-10 23:29 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | cp dcsm-EF_ENA_HV_ON_H /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | 1
|  | 2021-08-10 23:29 | 2021-08-10 23:33 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 |  | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | cp dcsm-EF_MIA_HV_ON_SW_RC /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | 0
|  | 2021-08-10 23:33 | 2021-08-11 00:02 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | cp dcsm-EF_MEA_HV_ON /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_ON -Run | 1
|  | 2021-08-11 00:02 | 2021-08-11 01:45 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB | 232 |  | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | cp dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB /tmp/dcsm | dcsm-EF_MSA_HV_ON_2_VFB | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB -Run | 1
|  | 2021-08-11 01:45 | 2021-08-11 01:45 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | cp dcsm-EF_BUS_TLM_MODE_5 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | 1
|  | 2021-08-11 01:45 | 2021-08-11 09:55 | Observation F |  |  | 29372 | 8.1589 |  | 0 |  | 0000 WAIT_SEC 3600 -Run | cp /tmp/dcsm |  | 0000 WAIT_SEC 3600 | 0
|  | 2021-08-11 09:55 | 2021-08-11 09:56 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10 | 2 |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | cp dcsm-EF_BUS_TLM_MODE_10 /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | 1
|  | 2021-08-11 09:56 | 2021-08-11 09:59 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | cp dcsm-EF_HEPE_HV_OFF_OBS_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | 1
|  | 2021-08-11 09:59 | 2021-08-11 10:02 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | cp dcsm-EF_ENA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | 1
|  | 2021-08-11 10:02 | 2021-08-11 10:15 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | cp dcsm-EF_MSA_HV_OFF_VFB /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | 1
|  | 2021-08-11 10:15 | 2021-08-11 10:16 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | cp dcsm-EF_MIA_HV_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | 1
|  | 2021-08-11 10:16 | 2021-08-11 10:20 |  |  | MEA_HV_SCAN_OFF | 210 |  | dcsm-EF_MEA_HV_SCAN_OFF | 24 |  | 0000 CALL dcsm-EF_MEA_HV_SCAN_OFF -Run | cp dcsm-EF_MEA_HV_SCAN_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_HV_SCAN_OFF -Run | 1
|  | 2021-08-11 10:20 | 2021-08-11 10:21 |  | SI Power OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP | 4 |  | 0000 CALL dcsm-EF_HEPE_OFF_STOP -Run | cp dcsm-EF_HEPE_OFF_STOP /tmp/dcsm |  | 0000 CALL dcsm-EF_HEPE_OFF_STOP -Run | 1
|  | 2021-08-11 10:21 | 2021-08-11 10:23 |  |  | MIA_OFF | 160 |  | dcsm-EF_MIA_OFF | 4 |  | 0000 CALL dcsm-EF_MIA_OFF -Run | cp dcsm-EF_MIA_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MIA_OFF -Run | 1
|  | 2021-08-11 10:23 | 2021-08-11 10:25 |  |  | ENA_OFF | 88 |  | dcsm-EF_ENA_power_OFF | 4 |  | 0000 CALL dcsm-EF_ENA_power_OFF -Run | cp dcsm-EF_ENA_power_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_ENA_power_OFF -Run | 1
|  | 2021-08-11 10:25 | 2021-08-11 10:28 |  |  | MEA_OFF | 164 |  | dcsm-EF_MEA_OFF | 6 |  | 0000 CALL dcsm-EF_MEA_OFF -Run | cp dcsm-EF_MEA_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MEA_OFF -Run | 1
|  | 2021-08-11 10:28 | 2021-08-11 10:28 |  |  | MGF_OFF | 8 |  | dcsm-EF_MGF_OFF | 1 |  | 0000 CALL dcsm-EF_MGF_OFF -Run | cp dcsm-EF_MGF_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MGF_OFF -Run | 1
|  | 2021-08-11 10:28 | 2021-08-11 10:29 |  |  | PWI_OFF | 80 |  | dcsm-EF_PWI_OFF | 2 |  | 0000 CALL dcsm-EF_PWI_OFF -Run | cp dcsm-EF_PWI_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_PWI_OFF -Run | 1
|  | 2021-08-11 10:29 | 2021-08-11 10:30 |  |  | PME_OFF | 40 |  | dcsm-EF_PME_OFF | 1 |  | 0000 CALL dcsm-EF_PME_OFF -Run | cp dcsm-EF_PME_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_PME_OFF -Run | 1
|  | 2021-08-11 10:30 | 2021-08-11 10:36 |  |  | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF | 25 |  | 0000 CALL dcsm-EF_MSA_OFF -Run | cp dcsm-EF_MSA_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MSA_OFF -Run | 1
|  | 2021-08-11 10:36 | 2021-08-11 10:39 |  |  | MDM_OFF | 160 |  | dcsm-EF_MDM_OFF | 4 |  | 0000 CALL dcsm-EF_MDM_OFF -Run | cp dcsm-EF_MDM_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MDM_OFF -Run | 1
|  | 2021-08-11 10:39 | 2021-08-11 10:41 |  | MDP OFF | MDP_OFF | 120 |  | dcsm-EF_MDP_POWEROFF | 3 |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | cp dcsm-EF_MDP_POWEROFF /tmp/dcsm |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | 1
|  | 2021-08-11 10:41 | 2021-08-11 10:45 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP | 21 |  | 0000 CALL dcsm-MC_ENA_MDP -Run | cp dcsm-MC_ENA_MDP /tmp/dcsm |  | 0000 CALL dcsm-MC_ENA_MDP -Run | 1
|  | 2021-08-11 10:45 | 2021-08-11 10:48 |  | BUS OFF | BUS_OFF_D | 220 |  | dcsm-EF_BUS_MONI_OFF | 5 |  | 0000 CALL dcsm-EF_BUS_MONI_OFF -Run | cp dcsm-EF_BUS_MONI_OFF /tmp/dcsm |  | 0000 CALL dcsm-EF_BUS_MONI_OFF -Run | 1
|  | 2021-08-11 10:48 | 2021-08-11 11:08 | # WOL#6 |  | 0 | 1200 |  | #N/A | 0
2021-08-11 10:48
2021-08-11 10:47
Formulas:
Start = [End, row above]
Start = [End]-[Duration (sec)]/3600/24
End = [Start]+[Duration (sec)]/3600/24
End = [Start, row below]