## 確認事項
NO. | 確認事項 | 回答 | CLOSE

## List
|  | Duration (sec) | source filename | filename |  | cmdcount
BUS ON | BUS_SETUP | 687 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 25
BUS ON | BUS_SETUP_D | 577 | main2-BUS_NECP_HV_MONI_ON_XDOR_001_M60.cps | dcsm-EF_BUS_MONI_ON |  | 20
MDP ON | MDP_SETUP | 509 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 11
| MDP_ON_D | 509 | dcsm-EF_MDP_ON | dcsm-EF_MDP_ON |  | 11
| MDP_CRUISE_SET | 42 | main2-MDP_CRUISE_SET.cps | dcsm-EF_MDP_CRUISE_SET |  | 2
| MDP_HK_REPINT_6 | 42 | main2-MDP_HK_RepInt_6.cps | dcsm-MDP_HK_REPINT_6 |  | 2
SI Check | PWI_CHECK | 2672 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 56 |  | 180 | 348
| MGF_CHECK | 4179 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 52 |  | 168
| MASTWPT_CHECK | 2108 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 46
| MDM_CHECK | 1252 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 19
| ENA_CHECK | 1134 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 17
| MEA_CHECK | 4620 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 51
| MSA_CHECK | 1102 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 18
| MIA_CHECK | 1562 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 16
| HEP_CHECK | 4936 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 82
| MSASI_CHECK | 6688 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80 |  | 22
MDP OFF | MDP_OFF | 120 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80 |  | 3
| MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | dcsm-EF_MDP_POWEROFF |  | 3
BUS OFF | BUS_OFF | 220 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART4_XOR_002_M80 |  | 5
| BUS_OFF_D | 220 | dcsm-EF_BUS_MONI_OFF | dcsm-EF_BUS_MONI_OFF |  | 5
| TCSF_MSASI | 345 | dcsm-tcfs_tbl1_msasi_set.cps | dcsm-tcfs_tbl1_msasi_set |  | 13
SI Power ON | MSA_ON_SETUP | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON | 使用禁止 | 15
| PME_ON | 80 | main2-PME_ON.cps | dcsm-EF_PME_ON |  | 2
| PWI_ON_SETUP | 868 | dcsm-EF_PWI_ON_CRUSE.cps | dcsm-EF_PWI_ON_CRUISE |  | 27 | 520
| MGF_ON_SETUP | 14 | 20200410_Earth-fly-by_MGF_ON_20200221.cps | dcsm-EF_MGF_ON |  | 3
| MEA_ON_SETUP_SW | 386 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA_ON_SW |  | 21
| MEA1_ON_SETUP_SW | 292 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA1_ON_SW |  | 12
| MEA_ON_SETUP_MAG | 386 | MEA_Earth_Flyby_4_ON_HVOFF.cps | dcsm-EF_MEA_ON_MAG |  | 21
| ENA_ON_SETUP | 564 | ENA_power_ON.cps | dcsm-EF_ENA_power_ON |  | 7
| MIA_ON_SETUP | 382 | main2-MIA_ON.cps | dcsm-EF_MIA_ON |  | 6
| HEP_ON_SETUP | 1230 | main2-HEP_ON_START_for_TL.cps | dcsm-EF_HEP_ON_START_for_TL |  | 34
| MDM_ON_SETUP | 202 | クルーズ観測手順.txt | dcsm-EF_MDM_ON | 暫定的に600sec入れてある | 6
SI HV ON | MEA_HV_ON | 1756 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA_HV_ON |  | 54
| MEA1_HV_ON | 1702 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA1_HV_ON |  | 27
| MIA_HV_ON | 240 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON |  | 6
| MIA_HV_ON_MAG | 142 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG |  | 4
| MIA_HV_ON_SW | 102 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW |  | 3
| MIA_HV_ON_RC | 280 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON_RC |  | 7
| MIA_HV_ON_MAG_RC | 262 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG_RC |  | 7
| MIA_HV_ON_SW_RC | 262 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW_RC |  | 7
| MSA_HV_ON | 10954 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1,dcsm-EF_MSA_HV_ON_2 |  | 232
| MSA_HV_ON_VFB | 6144 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB |  | 232
| ENA_HV_ON | 344 | ENA_HV_ON.cps | dcsm-EF_ENA_HV_ON |  | 18
| ENA_HV_ON_H | 344 | ENA_HV_ON_H.cps | dcsm-EF_ENA_HV_ON_H |  | 18
| HEP_HV_ON | 270 | main2-HEPE_HV_ON_OBS_START.cps | dcsm-EF_HEPE_HV_ON_OBS_START |  | 6
TLM mode change (MODE_5) | TLM_MODE_5 | 42 | main2-BUS_TLM_MODE_5.cps | dcsm-EF_BUS_TLM_MODE_5 |  | 2
TLM mode change (MODE_10) | TLM_MODE_10 | 42 | main2-BUS_TLM_MODE_10.cps | dcsm-EF_BUS_TLM_MODE_10 |  | 2
TLM mode change (MODE_7) | TLM_MODE_7 | 2 | main2-BUS_TLM_MODE_7.cps | dcsm-EF_BUS_TLM_MODE_7 |  | 1
SI HV OFF | HEP_HV_OFF | 190 | main2-HEPE_HV_OFF_OBS_OFF.cps | dcsm-EF_HEPE_HV_OFF_OBS_OFF |  | 5
| ENA_HV_OFF | 198 | ENA_HV_OFF.cps | dcsm-EF_ENA_HV_OFF |  | 4
| MSA_HV_OFF | 714 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF |  | 24
| MSA_HV_OFF_VFB | 774 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF_VFB |  | 25
| MIA_HV_OFF | 60 | main2-MIA_HV_OFF.cps | dcsm-EF_MIA_HV_OFF |  | 1
| MEA_HV_SCAN_OFF | 210 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA_HV_SCAN_OFF |  | 24
| MEA1_HV_SCAN_OFF | 186 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA1_HV_SCAN_OFF |  | 12
| MEA_HV_OFF | 202 | MEA_Earth_Flyby_6_ON_HVOFF.cps | dcsm-EF_MEA_HV_OFF |  | 20
| MEA1_HV_OFF | 182 | dcsm-EF_MEA1_HV_OFF.cps | dcsm-EF_MEA1_HV_OFF |  | 10
SI Power OFF | HEP_OFF | 70 | main2-HEPE_OFF_STOP.cps | dcsm-EF_HEPE_OFF_STOP |  | 4
| MIA_OFF | 160 | main2-MIA_OFF.cps | dcsm-EF_MIA_OFF |  | 4
| ENA_OFF | 88 | ENA_power_OFF.cps | dcsm-EF_ENA_power_OFF |  | 4
| MEA_OFF | 164 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA_OFF |  | 6
| MEA1_OFF | 160 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA1_OFF |  | 4
| MGF_OFF | 8 | 20200410_Earth-fly-by_MGF_OFF_20200221.cps | dcsm-EF_MGF_OFF |  | 1
| PWI_OFF | 80 | main2-PWI_OFF.cps | dcsm-EF_PWI_OFF |  | 2
| PME_OFF | 40 | main2-PME_OFF.cps | dcsm-EF_PME_OFF |  | 1
| MSA_OFF | 380 | main2-MSA_OFF.cps | dcsm-EF_MSA_OFF |  | 25
| MDM_OFF | 160 | クルーズ観測手順.txt | dcsm-EF_MDM_OFF | 暫定的に600sec入れてある | 4
MSA SOFT RESET | MSA_SOFT_RESET2 | 100 | dcsm-EF_MSA_SOFT_RESET2.cps | dcsm-EF_MSA_SOFT_RESET2 |  | 5
MSA OCL | MSA_OCL_CHK | 7250 | dcsm-MSA_OCL_CHECK | dcsm-MSA_OCL_CHECK |  | 24
MACRO COMMAND ENA | MC_ENA | 246 | main2-MC_ENA_MDP_XDOR_001_M58.cps | dcsm-MC_ENA_MDP |  | 21
| WAIT3600 | 3600 |  | WAIT_SEC 3600
| WAIT3500 | 3500
| MSASI_DARK_1 | 768 | dcsm-MSASI_dark_CO_sequence1.cps | dcsm-MSASI_dark_CO_sequence1 |  | 11 | 19307
| MSASI_DARK_2 | 19498 | dcsm-MSASI_dark_CO_sequence2.cps | dcsm-MSASI_dark_CO_sequence2 |  | 55 | 19307
| MEA2_MEM_DMP | 2550 | dcsm-MEA2_MEM_DMP.cps | dcsm-MEA2_MEM_DMP |  | 36
| WAIT19357 | 19357
| WAIT139168 | 139168 | 139168 | WAIT_SEC 139168
| WAIT1800 | 1800 |  | WAIT_SEC 1800
| MDP_ERR_LOG_DUMP | 9080 | main2-MDP_ERR_LOG_DUMP_TL_XDOR_001_M08 | dcsm-MDP_ERR_LOG_DUMP |  | 6
CrouseCheckOut | CRCO_BUS_MONI_ON | 310 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_BUS_MONI_ON |  | 10
| CRCO_ENA | 1134 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_ENA_CHECK |  | 18
| CRCO_HEPE | 2206 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPE_CHECK |  | 36
| CRCO_HEPI | 2730 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPI_CHECK |  | 48
| CRCO_MASTWPT | 1848 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MASTWPT_CHECK |  | 41
| CRCO_MDM | 2332 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDM_CHECK |  | 45
| CRCO_MDP_OFF | 120 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_OFF |  | 4
| CRCO_MDP_ON | 509 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_ON |  | 12
| CRCO_MEA | 4620 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MEA_CHECK |  | 52
| CRCO_MGF | 4019 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MGF_CHECK |  | 49
| CRCO_MIA | 1562 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MIA_CHECK |  | 17
| CRCO_MIA_C | 1892 |  | dcsm-CRCO_MIA_CHECK_C |  | 20
| CRCO_MSASI | 6688 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSASI_CHECK |  | 23
| CRCO_MSA_C | 1102 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSA_CHECK_C |  | 19
| CRCO_MSA | 1102 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSA_CHECK |  | 19
| CRCO_PME_OFF | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_OFF |  | 5
| CRCO_PME_ON | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_ON |  | 5
| CRCO_PWI | 2512 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PWI_CHECK |  | 51
| CRCO_SI_READY | 377 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_SI_READY |  | 17
| MSA_TBL_UP1 | 7558 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C636_NECP_M185001_00001 |  | 8
| MSA_TBL_UP2 | 948 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C637_NECP_M185002_00001 |  | 4
| MSA_TBL_UP3 | 160 | main2-MSA_TABLE_UPLOAD | XDOR_BJXR_C638_NECP_M185003_00001 |  | 4
| MSA_ON_SETUP_C | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON_C |  | 15
MDP TABLE UPLOAD | T_MDP_ON | 200 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C887_NECP_M700101_00002.BC
| T_MDP_DPU1 | 40 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C888_NECP_M700201_00001.BC
| T_MDP_DPU1_LOAD | 232 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C889_NECP_M700202_00009.BC
| T_MDP_DPU1_DUMP | 6000 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C890_NECP_M700203_00001.BC
| T_MDP_DPU2_LOAD | 232 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C891_NECP_M700204_00009.BC
| T_MDP_DPU2_DUMP | 6000 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C892_NECP_M700205_00002.BC
| T_MDP_OFF | 80 | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | XDOR_BJXR_C893_NECP_M700301_00002.BC
7620
| CRCO_CEL_MONI_OFF | 40 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_CEL_MONI_OFF |  | 1
| BUS_CEL_MONI_ON | 40 | dcsm-BUS_CEL_MONI_ON.cps | dcsm-BUS_CEL_MONI_ON |  | 1
| BUS_CEL_MONI_OFF | 40 | dcsm-BUS_CEL_MONI_OFF.cps | dcsm-BUS_CEL_MONI_OFF |  | 1
| BUS_CHG_BEFORE_CHK | 0 | dcsm-BUS_CHG_BEFORE_CHK.cps | dcsm-BUS_CHG_BEFORE_CHK |  | 0
| BUS_CHG_SET | 298 | dcsm-BUS_CHG_SET.cps | dcsm-BUS_CHG_SET |  | 14
| BUS_CHG_START | 82 | dcsm-BUS_CHG_START.cps | dcsm-BUS_CHG_START |  | 2
| BUS_CHG_STOP_BAT-EXT | 160 | dcsm-BUS_CHG_STOP_BAT-EXT.cps | dcsm-BUS_CHG_STOP_BAT-EXT |  | 4
| BUS_MMO_ON | 80 | dcsm-BUS_MMO_ON.cps | dcsm-BUS_MMO_ON |  | 2
| BUS_MMO_OFF | 140 | dcsm-BUS_MMO_OFF.cps | dcsm-BUS_MMO_OFF |  | 1
| BUS_CHG_EMERGENCY_OFF | 86 | dcsm-BUS_CHG_Emergency_OFF.cps | dcsm-BUS_CHG_Emergency_OFF |  | 5
| WAIT10800 | 10800 |  | WAIT_SEC 10800
| WAIT600 | 600 |  | WAIT_SEC 600

## wheel offloading
|  | CA time | 2021-02-22 06:47
Time to CA [h] | ID |  | date time excel | duration(s)
0 | WOLS |  | 2021-06-13 04:55 | 1200 | WOL#1 |  | 2021-06-13 04:55 | 2021-164T04:55:14.000Z | 2021-164T05:15:14.000Z
| WOLE |  | 2021-06-13 05:15 | 0 |  |  | 2021-06-13 05:15 | 2021-164T05:15:14.000Z | 2021-165T05:48:37.000Z
19.255 | WOLS |  | 2021-06-14 05:29 | 1200 | WOL#2 |  | 2021-06-14 05:29 | 2021-165T05:28:37.000Z | 2021-166T05:49:51.000Z
| WOLE |  | 2021-06-14 05:49 | 0 |  |  | 2021-06-14 05:49 | 2021-165T05:48:37.000Z | 2021-167T05:51:02.000Z
-23.5 | WOLS |  | 2021-06-15 05:30 | 1200 | WOL#3 |  | 2021-06-15 05:30 | 2021-166T05:29:51.000Z | 2021-167T21:54:18.000Z
| WOLE |  | 2021-06-15 05:50 | 0 |  |  | 2021-06-15 05:50 | 2021-166T05:49:51.000Z | 2021-168T05:52:17.000Z
-14.5 | WOLS |  | 2021-06-16 05:31 | 1200 | WOL#4 |  | 2021-06-16 05:31 | 2021-167T05:31:02.000Z | 2021-169T00:04:13.000Z
| WOLE |  | 2021-06-16 05:51 | 0 |  |  | 2021-06-16 05:51 | 2021-167T05:51:02.000Z | 2021-170T08:32:13.000Z
-4.5 | WOLS |  | 2021-06-16 21:34 | 1200 | WOL#5 | Power cycle | 2021-06-16 21:34 | 2021-167T21:34:18.000Z | 2021-171T07:01:41.000Z
| WOLE |  | 2021-06-16 21:54 | 0 |  |  | 2021-06-16 21:54 | 2021-167T21:54:18.000Z | 2021-171T21:11:41.000Z
6.5 | WOLS |  | 2021-06-17 05:32 | 1200 | WOL#6 |  | 2021-06-17 05:32 | 2021-168T05:32:17.000Z | 2021-172T05:17:06.000Z
| WOLE |  | 2021-06-17 05:52 | 0 |  |  | 2021-06-17 05:52 | 2021-168T05:52:17.000Z | 2021-173T05:58:47.000Z
24.5 | WOLS |  | 2021-06-17 23:44 | 1200 | WOL#7 |  | 2021-06-17 23:44 | 2021-168T23:44:13.000Z | 2021-174T07:00:20.000Z
| WOLE |  | 2021-06-18 00:04 | 0 |  |  | 2021-06-18 00:04 | 2021-169T00:04:13.000Z | 2021-175T06:01:06.000Z
42.5 | WOLS |  | 2021-06-19 08:12 | 1200 | WOL#8 |  | 2021-06-19 08:12 | 2021-170T08:12:13.000Z | 2021-175T21:50:00.000Z
| WOLE |  | 2021-06-19 08:32 | 0 |  |  | 2021-06-19 08:32 | 2021-170T08:32:13.000Z | 2021-176T21:24:13.000Z
| WOLS |  | 2021-06-20 06:42 | 1200 | WOL#9 |  | 2021-06-20 06:42 | 2021-171T06:41:41.000Z | 2021-177T13:35:42.000Z
| WOLE |  | 2021-06-20 07:02 | 0 |  |  | 2021-06-20 07:02 | 2021-171T07:01:41.000Z | 2021-178T08:01:41.000Z
| WOLS |  | 2021-06-20 20:52 | 1200 | WOL#10 |  | 2021-06-20 20:52 | 2021-171T20:51:41.000Z | 2021-179T06:35:34.000Z
| WOLE |  | 2021-06-20 21:12 | 0 |  |  | 2021-06-20 21:12 | 2021-171T21:11:41.000Z | 2021-180T07:10:33.000Z
| WOLS |  | 2021-06-21 04:57 | 1200 | WOL#11 |  | 2021-06-21 04:57 | 2021-172T04:57:06.000Z | 2021-181T06:07:08.000Z
| WOLE |  | 2021-06-21 05:17 | 0 |  |  | 2021-06-21 05:17 | 2021-172T05:17:06.000Z | 2021-181T23:56:50.000Z
| WOLS |  | 2021-06-22 05:39 | 1200 | WOL#12 |  | 2021-06-22 05:39 | 2021-173T05:38:47.000Z
| WOLE |  | 2021-06-22 05:59 | 0 |  |  | 2021-06-22 05:59 | 2021-173T05:58:47.000Z
| WOLS |  | 2021-06-23 06:40 | 1200 | WOL#13 |  | 2021-06-23 06:40 | 2021-174T06:40:20.000Z
| WOLE |  | 2021-06-23 07:00 | 0 |  |  | 2021-06-23 07:00 | 2021-174T07:00:20.000Z
| WOLS |  | 2021-06-24 05:41 | 1200 | WOL#14 |  | 2021-06-24 05:41 | 2021-175T05:41:06.000Z
| WOLE |  | 2021-06-24 06:01 | 0 |  |  | 2021-06-24 06:01 | 2021-175T06:01:06.000Z
| WOLS |  | 2021-06-24 21:30 | 1200 | WOL#15 |  | 2021-06-24 21:30 | 2021-175T21:30:00.000Z
| WOLE |  | 2021-06-24 21:50 | 0 |  |  | 2021-06-24 21:50 | 2021-175T21:50:00.000Z
| WOLS |  | 2021-06-25 21:04 | 1200 | WOL#16 |  | 2021-06-25 21:04 | 2021-176T21:04:13.000Z
| WOLE |  | 2021-06-25 21:24 | 0 |  |  | 2021-06-25 21:24 | 2021-176T21:24:13.000Z
| WOLS |  | 2021-06-26 13:16 | 1200 | WOL#17 |  | 2021-06-26 13:16 | 2021-177T13:15:42.000Z
| WOLE |  | 2021-06-26 13:36 | 0 |  |  | 2021-06-26 13:36 | 2021-177T13:35:42.000Z
| WOLS |  | 2021-06-27 07:42 | 1200 | WOL#18 |  | 2021-06-27 07:42 | 2021-178T07:41:41.000Z
| WOLE |  | 2021-06-27 08:02 | 0 |  |  | 2021-06-27 08:02 | 2021-178T08:01:41.000Z
| WOLS |  | 2021-06-28 06:16 | 1200 | WOL#19 |  | 2021-06-28 06:16 | 2021-179T06:15:34.000Z
| WOLE |  | 2021-06-28 06:36 | 0 |  |  | 2021-06-28 06:36 | 2021-179T06:35:34.000Z
| WOLS |  | 2021-06-29 06:51 | 1200 | WOL#20 |  | 2021-06-29 06:51 | 2021-180T06:50:33.000Z
| WOLE |  | 2021-06-29 07:11 | 0 |  |  | 2021-06-29 07:11 | 2021-180T07:10:33.000Z
| WOLS |  | 2021-06-30 05:47 | 1200 | WOL#21 |  | 2021-06-30 05:47 | 2021-181T05:47:08.000Z
| WOLE |  | 2021-06-30 06:07 | 0 |  |  | 2021-06-30 06:07 | 2021-181T06:07:08.000Z
| WOLS |  | 2021-06-30 23:37 | 1200 | WOL#22 |  | 2021-06-30 23:37 | 2021-181T23:36:50.000Z
| WOLE |  | 2021-06-30 23:57 | 0 |  |  | 2021-06-30 23:57 | 2021-181T23:56:50.000Z
| WOLS |  | 2021-07-02 01:52 | 1200 | WOL#23 |  | 2021-07-02 01:52
| WOLE |  | 2021-07-02 02:12 | 0 |  |  | 2021-07-02 02:12
Formulas:
date time excel = [date time excel, row above]+[duration(s), row above]/3600/24

## 2022_3_9(TBL UP)
# 2020/07/28 |  | 2022-03-09 14:11 | MSA software update | [5 empty] | 5days
# WOL#1 |  | 2021-02-22 06:47 | [6 empty] | 47.5
# WOL#2 |  | 2021-02-23 02:03 | [6 empty] | sum
# WOL#3 |  | 2021-02-23 22:46
# WOL#4 |  | 2021-02-25 03:25
# WOL#5 |  | 2021-02-26 07:41
|  | 2022-03-09 19:05 | END TIME
Relative time (h) |  | Absolute time (UTC) | [5 empty] | main2-CRCO_MSA_TABLE_UPLOAD_XDOR_002_M18 | 19
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) | main2-PICHECKOUT_MSA_2_XDOR_001_M18.cps | cmd count | cmd count
|  | 2022-03-09 14:11 | 2022-03-09 14:19 |  | MDP ON | MDP_ON_D | 509 | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run
|  | 2022-03-09 14:19 | 2022-03-09 16:25 |  | MSA software update | MSA_TBL_UP1 | 7558 | XDOR_BJXR_C636_NECP_M185001_00001 | 8 |  | 0000 CALL XDOR_BJXR_C636_NECP_M185001_00001 -Run
|  | 2022-03-09 16:25 | 2022-03-09 17:25 |  |  | WAIT3600 | 3600 | WAIT_SEC 3600
|  | 2022-03-09 17:25 | 2022-03-09 17:41 |  |  | MSA_TBL_UP2 | 948 | XDOR_BJXR_C637_NECP_M185002_00001 | 4 |  | 0000 CALL XDOR_BJXR_C637_NECP_M185002_00001 -Run
|  | 2022-03-09 17:41 | 2022-03-09 17:44 |  |  | MSA_TBL_UP3 | 160 | XDOR_BJXR_C638_NECP_M185003_00001 | 4 |  | 0000 CALL XDOR_BJXR_C638_NECP_M185003_00001 -Run
|  | 2022-03-09 17:44 | 2022-03-09 17:46 |  | MDP OFF | MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | 3 |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run
|  | 2022-03-09 17:46 | 2022-03-09 17:54 |  | MSA function check | MDP_ON_D | 509 | dcsm-EF_MDP_ON | 11
|  | 2022-03-09 17:54 | 2022-03-09 18:13 |  |  | CRCO_MSA_C | 1102 | dcsm-CRCO_MSA_CHECK_C | 19
|  | 2022-03-09 18:13 | 2022-03-09 18:15 |  |  | MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | 3
Formulas:
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24

## 2022_3_10(PWI)
|  | 2022-03-10 11:48 | START
# 2020/07/28 |  | 2022-03-10 14:18 | 3/10 PASS_START | [5 empty] | 5days
|  | 2022-03-11 06:31 | 3/11 PASS_START | [5 empty] | 0
Relative time (h) |  | Absolute time (UTC) | [5 empty] | main2-MDP_EEPROM_UPLOAD_XDOR_010_M70 | 0
main2-PWI_CHK_XDOR_001_M11
main2-MSA_MDP_ON_CRUISESET_XDOR_001_M18
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  | cmd count | cmd count
|  | 2022-03-10 11:48 | 2022-03-10 11:51 |  | MDP_EEPROM_UPLOAD(PWI) | T_MDP_ON | 200 | XDOR_BJXR_C887_NECP_M700101_00002.BC | 0 |  | 0000 CALL XDOR_BJXR_C887_NECP_M700101_00002.BC -Run
|  | 2022-03-10 11:51 | 2022-03-10 11:52 |  |  | T_MDP_DPU1 | 40 | XDOR_BJXR_C888_NECP_M700201_00001.BC | 0 |  | 0000 CALL XDOR_BJXR_C888_NECP_M700201_00001.BC -Run
|  | 2022-03-10 11:52 | 2022-03-10 11:56 |  |  | T_MDP_DPU1_LOAD | 232 | XDOR_BJXR_C889_NECP_M700202_00009.BC | 0 |  | 0000 CALL XDOR_BJXR_C889_NECP_M700202_00009.BC -Run
|  | 2022-03-10 11:56 | 2022-03-10 13:36 |  |  | T_MDP_DPU1_DUMP | 6000 | XDOR_BJXR_C890_NECP_M700203_00001.BC | 0 |  | 0000 CALL XDOR_BJXR_C890_NECP_M700203_00001.BC -Run
|  | 2022-03-10 14:18 | 2022-03-10 14:22 |  |  | T_MDP_DPU2_LOAD | 232 | XDOR_BJXR_C891_NECP_M700204_00009.BC | 0 |  | 0000 CALL XDOR_BJXR_C891_NECP_M700204_00009.BC -Run
|  | 2022-03-10 14:22 | 2022-03-10 16:02 |  |  | T_MDP_DPU2_DUMP | 6000 | XDOR_BJXR_C892_NECP_M700205_00002.BC | 0 |  | 0000 CALL XDOR_BJXR_C892_NECP_M700205_00002.BC -Run
|  | 2022-03-10 16:02 | 2022-03-10 16:03 |  |  | T_MDP_OFF | 80 | XDOR_BJXR_C893_NECP_M700301_00002.BC | 0 |  | 0000 CALL XDOR_BJXR_C893_NECP_M700301_00002.BC -Run
|  | 2022-03-11 06:31 | 2022-03-11 06:39 |  | PWI_CHK | MDP_ON_D | 509 | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run
|  | 2022-03-11 06:39 | 2022-03-11 06:42 |  |  | CRCO_PME_ON | 160 | dcsm-CRCO_PME_ON | 5 |  | 0000 CALL dcsm-CRCO_PME_ON -Run
|  | 2022-03-11 06:42 | 2022-03-11 07:24 |  |  | CRCO_PWI | 2512 | dcsm-CRCO_PWI_CHECK | 51 |  | 0000 CALL dcsm-CRCO_PWI_CHECK -Run
|  | 2022-03-11 07:24 | 2022-03-11 07:27 |  |  | CRCO_PME_OFF | 160 | dcsm-CRCO_PME_OFF | 5 |  | 0000 CALL dcsm-CRCO_PME_OFF -Run
|  | 2022-03-11 07:27 | 2022-03-11 07:29 |  |  | MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | 3 |  | 0000 CALL dcsm-EF_MDP_POWEROFF -Run
|  | 2022-03-11 07:29 | 2022-03-11 07:37 |  | MSA_ON | MDP_ON_D | 509 | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run
|  | 2022-03-11 07:37 | 2022-03-11 07:38 |  |  | MDP_CRUISE_SET | 42 | dcsm-EF_MDP_CRUISE_SET | 2 |  | 0000 CALL dcsm-EF_MDP_CRUISE_SET -Run
|  | 2022-03-11 07:38 | 2022-03-11 07:56 |  |  | MSA_ON_SETUP_C | 1092 | dcsm-EF_MSA_ON_C | 15 |  | 0000 CALL dcsm-EF_MSA_ON_C -Run
Formulas:
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24

## 2022_3_15(MSA OCL)
# 2020/07/28 |  | 2022-03-15 06:20 | MSA software update | [5 empty] | 5days
# WOL#1 |  | 2021-02-22 06:47 | [6 empty] | 87.5
# WOL#2 |  | 2021-02-23 02:03 | [6 empty] | sum
# WOL#3 |  | 2021-02-23 22:46
# WOL#4 |  | 2021-02-25 03:25
# WOL#5 |  | 2021-02-26 07:41
|  | 2022-03-15 10:20 | END TIME
Relative time (h) |  | Absolute time (UTC) | [5 empty] | main2-CRCO_MSA_OCL_CHECK_XDOR_001_M18 | 35
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  | cmd count | cmd count
|  | 2022-03-15 06:20 | 2022-03-15 06:28 |  | MDP ON | MDP_ON_D | 509 | dcsm-EF_MDP_ON | 11 |  | 0000 CALL dcsm-EF_MDP_ON -Run
|  | 2022-03-15 06:28 | 2022-03-15 08:29 |  | MSA OCL CHECk | MSA_OCL_CHK | 7250 | dcsm-MSA_OCL_CHECK | 24 |  | 0000 CALL dcsm-MSA_OCL_CHECK -Run
|  | 2022-03-15 08:29 | 2022-03-15 08:31 |  | MDP OFF | MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF
Formulas:
Start = [End, row above]
End = [Start]+[Duration (sec)]/3600/24