## Summary
| Launch date (UT): | 2018-10-20
Activity |  |  |  | Duration |  |  |  | MMO Data Volume |  |  | MMO condition at end of passes
Activity |  | NECP day | Date | Interactive [hours] | MTL [hours] | Total [min] | Total [hours] | Interactive [Mbit] | MTL [Mbit] | DV Total [Mbit]
| MMO to Cruise standby mode | 15 | 2018-11-06 | 0.1 | 0 | 6 | 0.1 | 2.8674 | 0 | 2.8674
M51 | HK Mode change | 15 | 2018-11-06 | 0.066667 | 0 | 3 | 0.066667 | 1.9116 | 0 | 1.9116
M01 | PCS commissioning | 15 | 2018-11-06 | 1.5 | 0 | 90 | 1.5 | 43.0115 | 0 | 43.0115
M02 | ACS commissioning | 15 | 2018-11-06 | 4.1667 | 0 | 250 | 4.1667 | 119.4763 | 0 | 119.4763
M03 | DMC commissioning | 15 | 2018-11-06 | 1 | 0 | 60 | 1 | 28.6743 | 0 | 28.6743
M04 | TCS commissioning | 16 | 2018-11-07 | 0 | 0.75 | 45 | 0.75 | 0 | 21.5057 | 21.5057 | MMO in Cruise Standby mode TCS commissioning is performed after the pass of NECP day 16
M52 | Preparation for MMO mission commissioning (Set up Before MDP Check) | 16 | 2018-11-07 | 1 | 0 | 60 | 1 | 28.6743 | 0 | 28.6743
M08 | MDP commissioning | 16-18 | 2018/11/7-9 | 10 | 0 | 600 | 10 | 286.7432 | 0 | 286.7432 | For each pass: MDP off, Cruise Standby mode
M55 | MDP ON | 18 | 2018-11-09 | 0.5 | 0 | 30 | 0.5 | 14.3372 | 0 | 14.3372
M12 | MGF commissioning | 18 (MTL: 19) | 2018-11-09 | 1.3333 | 2.6667 | 240 | 4 | 38.2324 | 76.4648 | 114.6973 | MGF turned off at end of pass, switched on for MTL ops afterwards MGF MTL is performed after the pass of NECP day 19
M11 | PWI commissioning | 18-19 | 2018/11/9-10 | 4.5 | 2 | 390 | 6.5 | 129.0344 | 57.3486 | 186.3831 | PWI remains ON for MTL ops outside pass
M09 | MAST latch release (MWE comissioning) | 19 | 2018-11-10 | 3 | 0 | 180 | 3 | 86.0229 | 0 | 86.0229 | MWE commissioning must be done before MAST and WPT-S latch release
M09 | MAST latch release | 20 | 2018-11-11 | 3 | 0 | 180 | 3 | 86.0229 | 0 | 86.0229
M10 | PWI WPT-S latch release | 20 | 2018-11-11 | 4 | 0 | 240 | 4 | 114.6973 | 0 | 114.6973
M56 | MDP OFF | 20 | 2018-11-11 | 0 | 0.3 | 18 | 0.3 | 0 | 8.6023 | 8.6023 | Note MDP off outside coverage acceptable for JAXA
| MMO to Cruise dormant mode | 20 | 2018-11-11 | 0 | 0.1 | 6 | 0.1 | 0 | 2.8674 | 2.8674 | Note MMO to Cruise dormant mode outside coverage acceptable for JAXA
| MMO to Cruise standby mode | 33 | 2018-11-24 | 0.1 | 0 | 6 | 0.1 | 2.8674 | 0 | 2.8674
M53 | Preparation for MMO mission commissioning (Set up MDP off & MMO off) | 33 | 2018-11-24 | 1 | 0 | 60 | 1 | 28.6743 | 0 | 28.6743
M55 | MDP ON | 33 | 2018-11-24 | 0.5 | 0 | 30 | 0.5 | 14.3372 | 0 | 14.3372
M15 | MPPE MEA1 commissioning (LV) | 33 | 2018-11-24 | 1.5833 | 0 | 95 | 1.5833 | 45.401 | 0 | 45.401
M16 | MPPE MEA2 commissioning (LV) | 33 | 2018-11-24 | 1.5833 | 0 | 95 | 1.5833 | 45.401 | 0 | 45.401
M18 | MPPE MSA commissioning (LV) | 33 | 2018-11-24 | 1.3333 | 0 | 80 | 1.3333 | 38.2324 | 0 | 38.2324
M14 | MSASI commissioning (LV) | 33 | 2018-11-24 | 2 | 7.9167 | 595 | 9.9167 | 57.3486 | 227.005 | 284.3536 | All PL off at end of day, MSASI switched for MTL ops afterwards; Note: MSASI should be last during the pass.
M17 | MPPE MIA commissioning (LV) | 34 | 2018-11-25 | 2.3 | 0 | 138 | 2.3 | 65.9509 | 0 | 65.9509
M19 | MPPE ENA commissioning (LV) | 34 | 2018-11-25 | 1.6667 | 0 | 100 | 1.6667 | 47.7905 | 0 | 47.7905
M20 | MPPE HEP commissioning (LV) | 34 | 2018-11-25 | 3 | 0 | 180 | 3 | 86.0229 | 0 | 86.0229
M13 | MDM commissioning | 34 | 2018-11-25 | 1 | 3.8333 | 290 | 4.8333 | 28.6743 | 109.9182 | 138.5925 | MDM is kept on at end of the pass for MTL operations outside pass; Note: MDM should be last during the pass.
M56 | MDP OFF | 34 | 2018-11-25 | 0 | 0.3 | 18 | 0.3 | 0 | 8.6023 | 8.6023 | Note MDP off outside coverage acceptable for JAXA
| MMO to Cruise dormant mode | 34 | 2018-11-25 | 0 | 0.1 | 6 | 0.1 | 0 | 2.8674 | 2.8674 | Note MMO to Cruise dormant mode outside coverage acceptable for JAXA
Delta Commissioning slot #1 | [11 empty] | Pass [h] | Activity [h] | Margin [h]
S36 | Spacecraft preparation for MMO high voltage test | DAY1 | 2019-06-24 | 0.1 | 0 | 6 | 0.1 |  |  |  |  | 8 | 7.7 | 0.3
| MMO to Cruise standby mode | DAY1 | 2019-06-24 | 0.1 | 0 | 6 | 0.1 | 2.8674 | 0 | 2.8674
M31 | Spacecraft preparation for MMO mission commissioning | DAY1 | 2019-06-24 | 1 | 0 | 60 | 1 | 28.6743 | 0 | 28.6743
M54 | MDP ON | DAY1 | 2019-06-24 | 0.5 | 0 | 30 | 0.5 | 14.3372 | 0 | 14.3372
M18 | MPPE MSA delta commissioning (LV) | DAY1 | 2019-06-24 | 6 | 0 | 360 | 6 | 172.0459 | 0 | 172.0459 | MSA remains on in between passes and is switched off after MTL ops
M18 | MPPE MSA commissioning (HV) | DAY2-4 | 2019/06/25-27 | 16.3333 | 3.5 | 1190 | 19.8333 | 468.3472 | 100.3601 | 568.7073 | MSA remains on in between passes and is switched off after MTL ops | 32 | 29.1 | 2.9
M19 | MPPE ENA commissioning (HV) | DAY4-5 | 2019/06/27-28 | 12.7667 | 1 | 826 | 13.7667 | 366.0754 | 28.6743 | 394.7498 | ENA remains on in between passes, is switched off at end
M15 | MPPE MEA1 commissioning (HV) | DAY6 | 2019-07-01 | 7.4167 | 0 | 445 | 7.4167 | 212.6678 | 0 | 212.6678 | MEA1 is switched off at end of pass | 8 | 7.4167 | 0.58333
M16 | MPPE MEA2 commissioning (HV) | DAY7 | 2019-07-02 | 7.4167 | 0 | 445 | 7.4167 | 212.6678 | 0 | 212.6678 | MEA2 is switched off at end of pass | 8 | 7.4167 | 0.58333
M17 | MPPE MIA commissioning (HV) | DAY6-7 | 2019/07/03-04 | 11.5 | 0 | 690 | 11.5 | 329.7546 | 0 | 329.7546 | MIA remains on in between pass | 24 | 22.3333 | 1.6667
M20 | MPPE HEP commissioning (HV) | DAY7-8 | 2019/07/04-05 | 10.8333 | 4.1667 | 900 | 15 | 310.6384 | 119.4763 | 430.1147 | HEP turned off at end of passes, switched on for MTL ops afterwards
M56 | MDP OFF | DAY10 | 2019-07-05 | 0 | 0.3 | 18 | 0.3 | 0 | 8.6023 | 8.6023 | Note MDP off outside coverage acceptable for JAXA
| MMO to Cruise dormant mode | DAY10 | 2019-07-05 | 0 | 0.1 | 6 | 0.1 | 0 | 2.8674 | 2.8674 | Note MMO to Cruise dormant mode outside coverage acceptable for JAXA
Delta Commissioning slot #2 | [11 empty] | Pass [h] | Activity [h] | Margin [h]
S36 | Spacecraft preparation for MMO high voltage test | DAY1 | 2019-07-30 | 0.1 | 0 | 6 | 0.1 |  |  |  |  | 24 | 21.1167 | 2.8833
| MMO to Cruise standby mode | DAY1 | 2019-07-30 | 0.1 | 0 | 6 | 0.1 | 2.8674 | 0 | 2.8674
M59 | Change heater settings for MAST latch release | DAY1 | 2019-07-30 | 0.5 | 0 | 30 | 0.5 | 14.3372 | 0 | 14.3372
M31 | Spacecraft preparation for MMO mission commissioning | DAY1 | 2019-07-30 | 1 | 0 | 60 | 1 | 28.6743 | 0 | 28.6743
M05 | COM-TWTA commissioning | DAY1 | 2019-07-30 | 2 | 0 | 120 | 2 | 57.3486 | 0 | 57.3486
M54 | MDP ON | DAY1 | 2019-07-30 | 0.5 | 0 | 30 | 0.5 | 14.3372 | 0 | 14.3372
M14 | MSASI commissioning (HV) | DAY1-3 | 2019/07/30-2019/08/01 | 16.9167 | 0 | 1015 | 16.9167 | 485.0739 | 0 | 485.0739 | MSASI remains on in between passes
| MDP upload | DAY4 | 2019-08-02 | 8 | 0 | 480 | 8 | 229.3945 | 0 | 229.3945 |  | 8 | 8 | 0
| FNC test after MDP upload | DAY5 | 2019-08-05 | 8 | 0 | 480 | 8 | 229.3945 | 0 | 229.3945 | MIA, HEP, PWI function checks are included | 8 | 8 | 0
M09 | MAST latch release | DAY6 | 2019-08-06 | 3 | 0 | 180 | 3 | 86.0229 | 0 | 86.0229 |  | 8 | 3 | 5
M10 | PWI WPT-S latch release | DAY7 | 2019-08-07 | 4 | 0 | 240 | 4 | 114.6973 | 0 | 114.6973 |  | 8 | 4 | 4
M55 | MDP OFF | DAY7 | 2019-08-07 | 0.3 | 0 | 18 | 0.3 | 8.6023 | 0 | 8.6023
| MMO to Cruise dormant mode | DAY7 | 2019-08-07 | 0 | 0.1 | 6 | 0.1 | 0 | 2.8674 | 2.8674
S36 | Spacecraft preparation for MMO high voltage test - undo | DAY7 | 2019-08-07 | 0 | 0.1 | 6 | 0.1
Formulas:
Date = C1+2+[NECP day]

## Details (hidden)
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments
M01 | Essential bus subsystem commissioning | Essential bus subsystem commissioning Confirm temperature range of PCD, DMC, XTRP-A and XTRP-B | [6 empty] | Constraints: to be done first
1 |  |  | 120 |  | 31 | XDOR_BJXR_NECP_M01_01_00001.bc | TBD | TC by TC
M02 | DMC/DRU commissioning | DMC/DRU checkout includes the operational heater control function.
1 |  |  | 60 |  | 31 | XDOR_BJXR_NECP_M02_01_00001.bc | TBD | TC by TC
2 |  |  |  | 240 | 31 | XDOR_BJXR_NECP_M02_02_00001.bc | TBD | MTL
M03 | PCS commissioning
1 |  |  |  | 240 | 31 | XDOR_BJXR_NECP_M03_01_00001.bc | TBD | MTL
M04 | ACS commissioning
1 |  |  | 60 |  | 31 | XDOR_BJXR_NECP_M04_01_00001.bc | TBD | TC by TC
2 |  |  |  | 240 | 31 | XDOR_BJXR_NECP_M04_02_00001.bc | TBD | MTL
M05 | COM-TWTA commissioning | This activity is including the HV checkout of the TWTA (TWTA-A and TWTA-B). | [6 empty] | Constraints: not earlier as 2 m after launch, Different from the HV checkout of MPPE, stepwise HV increasing approach is not necessary for the TWTA HV checkout.
1 |  |  | 60 |  | 65 | XDOR_BJXR_NECP_M04_01_00001.bc | TBD | TC by TC | HV commissioning during pass
2 |  |  |  | 300 | 65 | XDOR_BJXR_NECP_M04_02_00001.bc | TBD | MTL
M06 | COM-Other commissioning | [7 empty] | Constraints: Together with COM-TWTA
1 |  |  | 60 |  | 65 | XDOR_BJXR_NECP_M04_01_00001.bc | TBD | TC by TC
2 |  |  |  | 120 | 65 | XDOR_BJXR_NECP_M04_02_00001.bc | TBD | MTL
M07 | RCS commissioning | RCS pressure check (passive housekeeping monitoring only) | [6 empty] | Note, when the MMO is in the Cruise Active mode, the acquisition of the RCS pressure telemetry data is always performed by the DMC.
1 |  |  |  | 60 | 31 | XDOR_BJXR_NECP_M09_01_00001.bc | TBD | MTL
M08 | MDP commissioning | Mission Data Processor commissioning | [6 empty] | Constraints: To be done first in mission subsystem commissioning slot
1 | Power ON |  | 20 | 0 | 31 | XDOR_BJXR_NECP_M08_01_00001.bc | TBD | TC by TC
2 | Firm DMC-IF, memory check |  | 170 | 0 | 31 | XDOR_BJXR_NECP_M08_02_00001.bc | TBD | TC by TC
3 | Firm CMD check |  | 250 | 0 | 32 | XDOR_BJXR_NECP_M08_03_00001.bc | TBD | TC by TC
4 | Memory load and dump |  | 60 | 0 | 32 | XDOR_BJXR_NECP_M08_04_00001.bc | TBD | TC by TC
5 | Applications |  | 80 | 0 | 32 | XDOR_BJXR_NECP_M08_05_00001.bc | TBD | TC by TC
6 | Power OFF |  | 20 | 0 | 32 | XDOR_BJXR_NECP_M08_06_00001.bc | TBD | TC by TC
M09 | MAST (latch release operations) | [7 empty] | Constraints: Together with WPT-S latch release
1 | Initial power ON (PME) |  | 20 | 0 | 34 | XDOR_BJXR_NECP_M09_01_00001.bc | TBD | TC by TC
2 | Initial power ON (MWE) |  | 20 | 0 | 34 | XDOR_BJXR_NECP_M09_02_00001.bc | TBD | TC by TC
3 | Power ON (MOTOR-PSU) |  | 10 | 0 | 34 | XDOR_BJXR_NECP_M09_03_00001.bc | TBD | TC by TC
4 | Latch release parameter setting |  | 60 | 0 | 34 | XDOR_BJXR_NECP_M09_04_00001.bc | TBD | TC by TC
5 | MAST-SC latch release operations |  | 60 | 0 | 34 | XDOR_BJXR_NECP_M09_05_00001.bc | TBD | TC by TC
6 | Status check |  | 30 | 0 | 34
7 | MAST-MGF latch release operations |  | 60 | 0 | 34 | XDOR_BJXR_NECP_M09_07_00001.bc | TBD | TC by TC
8 | Status check |  | 30 | 0 | 34
9 | Power OFF (MOTOR-PSU) |  | 10 | 0 | 34 | XDOR_BJXR_NECP_M09_09_00001.bc | TBD | TC by TC
10 | Power OFF (MWE) |  | 10 | 0 | 34 | XDOR_BJXR_NECP_M09_10_00001.bc | TBD | TC by TC
11 | Power OFF (PME) |  | 10 | 0 | 34 | XDOR_BJXR_NECP_M09_11_00001.bc | TBD | TC by TC
M10 | PWI WPT-S (latch release operations) | As part of PWI, a pair of Wire antenna (WPT-S) needs its latch release operation in this activity. | [6 empty] | Constraints: - As soon as possible after launch, whereas around 25 days after launch is still acceptable. - Schedule after DMC, MDP and PWI commissioning - Schedule together with MAST latch release operations
1 | Initial power ON (PME) |  | 20 | 0 | 33 | XDOR_BJXR_NECP_M10_01_00001.bc | TBD | TC by TC
2 | Initial power ON (MWE) |  | 20 | 0 | 33 | XDOR_BJXR_NECP_M10_02_00001.bc | TBD | TC by TC
3 | Power ON (MOTOR-PSU) |  | 10 | 0 | 33 | XDOR_BJXR_NECP_M10_03_00001.bc | TBD | TC by TC
4 | HRM release parameter setting |  | 60 | 0 | 33 | XDOR_BJXR_NECP_M10_04_00001.bc | TBD | TC by TC
5 | WPT-S1 latch release operations |  | 60 | 0 | 33 | XDOR_BJXR_NECP_M10_05_00001.bc | TBD | TC by TC
6 | Status check | Data check | 30 | 0 | 33
7 | WPT-S2 latch release operations |  | 60 | 0 | 33 | XDOR_BJXR_NECP_M10_07_00001.bc | TBD | TC by TC
8 | Status check | Data check | 30 | 0 | 33
9 | Power OFF (MOTOR-PSU) |  | 10 | 0 | 33 | XDOR_BJXR_NECP_M10_09_00001.bc | TBD | TC by TC
10 | Power OFF (MWE) |  | 10 | 0 | 33 | XDOR_BJXR_NECP_M10_08_00001.bc | TBD | TC by TC
11 | Power OFF (PME) |  | 10 | 0 | 33 | XDOR_BJXR_NECP_M10_09_00001.bc | TBD | TC by TC
12 | PWI CAL | Check the latch release result | 90 | 0 | 33 | XDOR_BJXR_NECP_M10_10_00001.bc | TBD | TC by TC
M11 | PWI Commissioning | [7 empty] | Constraints: The PWI activities and the WPT-S latch release need to be grouped together (PWI activities first, then WPT-S latch release).
1 | EWO ON |  | 20 | 0 | 32 | XDOR_BJXR_NECP_M11_01_00001.bc | TBD | TC by TC
2 | SORBET/AM2P/WPT-PRE/DBS-PA |  | 30 | 0 | 32 | XDOR_BJXR_NECP_M11_02_00001.bc | TBD | TC by TC
3 | MEFISTO ON |  | 60 | 0 | 32 | XDOR_BJXR_NECP_M11_03_00001.bc | TBD | TC by TC
4 | PWI Function test (all ON) |  | 80 | 0 | 33 | XDOR_BJXR_NECP_M11_04_00001.bc | TBD | TC by TC
Mission Timeline operation
5 | OFA/EFD command/HK |  | 0 | 120 | 32 | XDOR_BJXR_NECP_M11_05_00001.bc | TBD | MTL
M12 | MGF commissioning
1 | Initial power ON |  | 10 | 0 | 65 | XDOR_BJXR_NECP_M12_01_00001.bc | TBD | TC by TC
2 | Parameter set |  | 10 | 0 | 65 | XDOR_BJXR_NECP_M12_02_00001.bc | TBD | TC by TC
3 | HK check |  | 60 | 0 | 65 |  | TBD | TC by TC
4 | Power OFF |  | 10 | 0 | 65 | XDOR_BJXR_NECP_M14_03_00001.bc | TBD | TC by TC
Mission Timeline operation
5 | Initial power ON |  | 0 | 10 | 65 | XDOR_BJXR_NECP_M15_04_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
6 | Observation sequence (get mission data) |  | 0 | 40 | 65
7 | Repeat observation sequence (get mission data) | includes 1 hour of wait time | 0 | 100 | 65
8 | Power OFF |  | 0 | 10 | 65
M13 | MDM commissioning
1 | Initial power ON |  | 20 | 0 | 65 | XDOR_BJXR_NECP_M13_01_00001.bc | TBD | TC by TC
2 | HK check |  | 10 | 0 | 65 | XDOR_BJXR_NECP_M13_02_00001.bc | TBD | TC by TC
3 | Observation mode check |  | 30 | 0 | 65 | XDOR_BJXR_NECP_M13_03_00001.bc | TBD | TC by TC
Mission Timeline operation
4 | Initial check |  | 0 | 20 | 65 | XDOR_BJXR_NECP_M13_04_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
5 | Function check |  | 0 | 60 | 65
6 | Observation mode check |  | 0 | 40 | 65
7 | Repeat observation mode check | includes 1 hour of wait time | 0 | 100 | 65
M14 | MSASI commissioning | This activity is including the HV checkout of the MSASI, in which the stepwise HV increase approach is necessary. | [6 empty] | Constraints: Typically not earlier than 2 months after launch HV increase rate: < 1 kV/day Assumption: user-HK telemetry rate = 16 sec -> Wait_sec: 1min
LV operation
1 | Initial power ON |  | 25 | 0 | 34 | XDOR_BJXR_NECP_M14_01_00001.bc | 5 | TC by TC
2 | HT check |  | 30 | 0 | 34 | XDOR_BJXR_NECP_M14_02_00001.bc | 10 | TC by TC
3 | G check |  | 50 | 0 | 34 | XDOR_BJXR_NECP_M14_03_00001.bc | 9 | TC by TC
4 | HV check (without HV ON) |  | 20 | 0 | 34 | XDOR_BJXR_NECP_M14_04_00001.bc | 8 | TC by TC
Mission Timeline operation (without HV)
5 | Initial setup | 20 TCs | 0 | 20 | 34 | XDOR_BJXR_NECP_M14_05_00001.bc | 107 | MTL | Only one XDOR file for MTL operations is needed
6 | CMOS check | 34 TCs | 0 | 34 | 34
7 | Observation sequence (get mission data, HV OFF): 13 min (13 CMDs) + 50 min (waiting output of mission data from MDP to DMC) | 13 TCs | 0 | 63 | 34
8 | Repeat observation sequence | includes 1 hour of wait time, 13 TCs | 0 | 123 | 34
9 | Change dummy flag | 3 TCs | 0 | 5 | 34
10 | MSASI OFF | 4 TCs | 0 | 5 | 34
HV increase: +6 kV procedure (nominal: +5.6 kV)
11 | MSASI ON |  | 25 | 0 | 66 | XDOR_BJXR_NECP_M14_06_00001.bc | 5 | TC by TC
12 | Initial HV ON |  | 30 | 0 | 66 | XDOR_BJXR_NECP_M14_07_00001.bc | TBD | TC by TC
13 | 0-1 kV (step by step) |  | 120 | 0 | 66 | XDOR_BJXR_NECP_M14_08_00001.bc | TBD | TC by TC
14 | Keep HV at +1 kV |  | 30 | 0 | 66
15 | 0-1 kV (quickly) and 1-2 kV (step by step) |  | 120 | 0 | 66 | XDOR_BJXR_NECP_M14_09_00001.bc | TBD | TC by TC
16 | Keep HV at +2 kV |  | 30 | 0 | 66
17 | 0-2 kV (quickly) and 2-3 kV (step by step) |  | 120 | 0 | 66 | XDOR_BJXR_NECP_M14_10_00001.bc | TBD | TC by TC
18 | Keep HV at +3 kV |  | 30 | 0 | 66
19 | 0-3 kV (quickly) and 3-4 kV (step by step) |  | 120 | 0 | 67 | XDOR_BJXR_NECP_M14_11_00001.bc | TBD | TC by TC
20 | Keep HV at +4 kV |  | 30 | 0 | 67
21 | 0-4 kV (quickly) and 4-5 kV (step by step) |  | 120 | 0 | 67 | XDOR_BJXR_NECP_M14_12_00001.bc | TBD | TC by TC
22 | Keep HV at +5 kV |  | 30 | 0 | 67
23 | 0-5 kV (quickly) and 5-5.6 kV (step by step) |  | 120 | 0 | 67 | XDOR_BJXR_NECP_M14_13_00001.bc | TBD | TC by TC
24 | Keep HV at +5.6 kV |  | 30 | 0 | 67
25 | 0-5.6 kV (quickly) |  | 30 | 0 | 67 | XDOR_BJXR_NECP_M14_14_00001.bc | TBD | TC by TC
HV increase: -4 kV procedure (nominal: -1.4 kV)
26 | 0-1 kV (step by step ) |  | 120 | 0 | 68 | XDOR_BJXR_NECP_M14_15_00001.bc | TBD | TC by TC
27 | Keep HV at -1 kV |  | 30 | 0 | 68
28 | 0-1 kV (quickly) and 1.0-1.4 kV (step by step) |  | 60 | 0 | 68 | XDOR_BJXR_NECP_M14_16_00001.bc | TBD | TC by TC
29 | Keep HV at -1.4 kV |  | 30 | 0 | 68
30 | 0-1.4 kV (quickly) |  | 30 | 0 | 68 | XDOR_BJXR_NECP_M14_17_00001.bc | TBD | TC by TC
31 | Both P6K and N4K up to nominal |  | 30 | 0 | 68 | XDOR_BJXR_NECP_M14_18_00001.bc | TBD | TC by TC
HV operation (mission data check and observation sequence)
32 | Mission data check with HV (CAL mode) |  | 50 | 0 | 68 | XDOR_BJXR_NECP_M14_19_00001.bc | TBD | TC by TC
33 | Observation sequence with HV (macro commands) |  | 70 | 0 | 68 | XDOR_BJXR_NECP_M14_20_00001.bc | TBD | TC by TC
34 | Repeat observation sequence | includes 1 hour of wait time | 180 | 0 | 69 | XDOR_BJXR_NECP_M14_21_00001.bc | TBD | TC by TC | This procedure can be skipped if packet loss does not happen
35 | MSASI OFF | 4 TCs | 10 | 0 | 69 | XDOR_BJXR_NECP_M14_22_00001.bc | TBD | TC by TC
M15 | MPPE MEA1 commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MEA1 Nominal operation
1 | Initial Power ON |  | 5 | 0 | 35 | XDOR_BJXR_NECP_M15_01_00001.bc | TBD | TC by TC
2 | Cal Check |  | 15 | 0 | 35 | XDOR_BJXR_NECP_M15_02_00001.bc | TBD | TC by TC
3 | Regenerate mission data of Cal Check again: 15 min operation plus 1 h wait time | includes 1 hour of wait time | 75 | 0 | 35 | XDOR_BJXR_NECP_M15_03_00001.bc | TBD | TC by TC
MEA1 HV operation
5 | Power ON |  | 5 | 0 | 69 | XDOR_BJXR_NECP_M15_04_00001.bc | TBD | TC by TC
6 | Cal Check |  | 15 | 0 | 69 | XDOR_BJXR_NECP_M15_05_00001.bc | TBD | TC by TC
7 | DISABLE HV SECURITY |  | 5 | 0 | 69 | XDOR_BJXR_NECP_M15_06_00001.bc | TBD | TC by TC
8 | SWITCH ON MCP (2750V in vacuum) |  | 140 | 0 | 69 | XDOR_BJXR_NECP_M15_07_00001.bc | TBD | TC by TC
9 | SWITCH ON SCAN |  | 120 | 0 | 69 | XDOR_BJXR_NECP_M15_08_00001.bc | TBD | TC by TC
10 | TEST MODE ON |  | 30 | 0 | 69 | XDOR_BJXR_NECP_M15_09_00001.bc | TBD | TC by TC
11 | Regenerate mission data again: 30 min operation plus 1 h wait time | includes 1 hour of wait time | 90 | 0 | 69 | XDOR_BJXR_NECP_M15_10_00001.bc | TBD | TC by TC
12 | TEST MODE OFF |  | 5 | 0 | 69 | XDOR_BJXR_NECP_M15_11_00001.bc | TBD | TC by TC
13 | SWITCH OFF SCAN |  | 5 | 0 | 69 | XDOR_BJXR_NECP_M15_12_00001.bc | TBD | TC by TC
14 | SWITCH OFF MCP |  | 30 | 0 | 69 | XDOR_BJXR_NECP_M15_13_00001.bc | TBD | TC by TC
MEA1 Mission Timeline operation
16 | Initial setup |  | 0 | 10 | 69 | XDOR_BJXR_NECP_M15_14_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
17 | CAL check |  | 0 | 30 | 69
18 | Regenerate mission data again: 30 min operation plus 1 h wait time |  | 0 | 90 | 69
19 | MDP SW check |  | 0 | 15 | 69
M16 | MPPE MEA2 commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MEA2 Nominal operation
1 | Initial Power ON |  | 5 | 0 | 35 | XDOR_BJXR_NECP_M16_01_00001.bc | TBD | TC by TC
2 | Cal Check |  | 15 | 0 | 35 | XDOR_BJXR_NECP_M16_02_00001.bc | TBD | TC by TC
3 | Regenerate mission data of Cal Check again: 15 min operation | includes 1 hour of wait time | 75 | 0 | 35 | XDOR_BJXR_NECP_M16_03_00001.bc | TBD | TC by TC
MEA2 HV operation
4 | Power ON |  | 5 | 0 | 70 | XDOR_BJXR_NECP_M16_04_00001.bc | TBD | TC by TC
5 | Cal Check |  | 15 | 0 | 70 | XDOR_BJXR_NECP_M16_05_00001.bc | TBD | TC by TC
6 | DISABLE HV SECURITY |  | 5 | 0 | 70 | XDOR_BJXR_NECP_M16_06_00001.bc | TBD | TC by TC
7 | SWITCH ON MCP (2750V in vacuum) |  | 140 | 0 | 70 | XDOR_BJXR_NECP_M16_07_00001.bc | TBD | TC by TC
8 | SWITCH ON SCAN |  | 120 | 0 | 70 | XDOR_BJXR_NECP_M16_08_00001.bc | TBD | TC by TC
9 | TEST MODE ON |  | 30 | 0 | 70 | XDOR_BJXR_NECP_M16_09_00001.bc | TBD | TC by TC
10 | Regenerate mission data again: 30 min operation plus 1 h wait time | includes 1 hour of wait time | 90 | 0 | 70 | XDOR_BJXR_NECP_M16_10_00001.bc | TBD | TC by TC
11 | TEST MODE OFF |  | 5 | 0 | 70 | XDOR_BJXR_NECP_M16_11_00001.bc | TBD | TC by TC
12 | SWITCH OFF SCAN |  | 5 | 0 | 70 | XDOR_BJXR_NECP_M16_12_00001.bc | TBD | TC by TC
13 | SWITCH OFF MCP |  | 30 | 0 | 70 | XDOR_BJXR_NECP_M16_13_00001.bc | TBD | TC by TC
MEA2 Mission Timeline operation
14 | Initial setup |  | 0 | 10 | 70 | XDOR_BJXR_NECP_M16_14_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
15 | CAL check |  | 0 | 30 | 70
16 | Regenerate mission data again: 30 min operation plus 1 h wait time |  | 0 | 90 | 70
17 | MDP SW check |  | 0 | 15 | 70
M17 | MPPE MIA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MIA Nominal operation
1 | Initial Power ON |  | 20 | 0 | 35 | XDOR_BJXR_NECP_M17_01_00001.bc | TBD | TC by TC
2 | Cal Check |  | 30 | 0 | 35 | XDOR_BJXR_NECP_M17_02_00001.bc | TBD | TC by TC
3 | Regenerate mission data again: 30 min operation plus 1 h wait time | includes 1 hour of wait time | 90 | 0 | 35 | XDOR_BJXR_NECP_M17_03_00001.bc | TBD | TC by TC
MIA HV operation
4 | Power ON |  | 5 | 0 | 71 | XDOR_BJXR_NECP_M17_04_00001.bc | TBD | TC by TC
5 | Cal Check |  | 15 | 0 | 71 | XDOR_BJXR_NECP_M17_05_00001.bc | TBD | TC by TC
6 | SAFETY ON HV check |  | 60 | 0 | 71 | XDOR_BJXR_NECP_M17_06_00001.bc | TBD | TC by TC
7 | SAFETY OFF |  | 5 | 0 | 71 | XDOR_BJXR_NECP_M17_07_00001.bc | TBD | TC by TC
8 | SAFETY OFF SHORT TIME ON |  | 90 | 0 | 71 | XDOR_BJXR_NECP_M17_08_00001.bc | TBD | TC by TC
9 | SVG HV LEVEL UP |  | 90 | 0 | 71 | XDOR_BJXR_NECP_M17_09_00001.bc | TBD | TC by TC
10 | SVS HV LEVEL UP |  | 120 | 0 | 71 | XDOR_BJXR_NECP_M17_10_00001.bc | TBD | TC by TC
11 | MHV HV LEVEL UP |  | 120 | 0 | 71 | XDOR_BJXR_NECP_M17_11_00001.bc | TBD | TC by TC
12 | SWEEP CHECK |  | 60 | 0 | 72 | XDOR_BJXR_NECP_M17_12_00001.bc | TBD | TC by TC
13 | HV SCAN & PH SCAN check |  | 60 | 0 | 72 | XDOR_BJXR_NECP_M17_13_00001.bc | TBD | TC by TC
14 | Regenerate mission data of sweep check again: 1h operation | 1 h wait time satisfied | 60 | 0 | 72 | XDOR_BJXR_NECP_M17_14_00001.bc | TBD | TC by TC
MIA Mission Timeline operation
15 | Initial setup |  | 0 | 10 | 72 | XDOR_BJXR_NECP_M17_15_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
16 | CAL check |  | 0 | 30 | 72
17 | ASIC check |  | 0 | 30 | 72
18 | PH scan check |  | 0 | 30 | 72
19 | MDP SW check |  | 0 | 15 | 72
20 | Regenerate mission data of Cal Check again: 30 min operation | 1 h wait time satisfied | 0 | 30 | 72
M18 | MPPE MSA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MSA Nominal operation
1 | Initial Power ON |  | 20 | 0 | 36 | XDOR_BJXR_NECP_M18_01_00001.bc | TBD | TC by TC
2 | Cal Check |  | 30 | 0 | 36 | XDOR_BJXR_NECP_M18_02_00001.bc | TBD | TC by TC
3 | Regenerate mission data of Cal Check again: 30 min operation | includes 1 hour of wait time | 30 | 0 | 36 | XDOR_BJXR_NECP_M18_03_00001.bc | TBD | TC by TC
MSA HV operation (max 8V)
4 | Power ON |  | 5 | 0 | 72 | XDOR_BJXR_NECP_M18_04_00001.bc | TBD | TC by TC
5 | Cal Check |  | 15 | 0 | 72 | XDOR_BJXR_NECP_M18_05_00001.bc | TBD | TC by TC
6 | Set HV1 |  | 60 | 0 | 72 | XDOR_BJXR_NECP_M18_06_00001.bc | TBD | TC by TC
7 | Set HV2 |  | 60 | 0 | 72 | XDOR_BJXR_NECP_M18_07_00001.bc | TBD | TC by TC
8 | Set VHV1 and VHV2 |  | 120 | 0 | 72 | XDOR_BJXR_NECP_M18_08_00001.bc | TBD | TC by TC
9 | Set VHV4 |  | 120 | 0 | 73 | XDOR_BJXR_NECP_M18_09_00001.bc | TBD | TC by TC
10 | Set VHV1 and VHV2 |  | 120 | 0 | 73 | XDOR_BJXR_NECP_M18_10_00001.bc | TBD | TC by TC
11 | Adjust VHV4 |  | 60 | 0 | 73 | XDOR_BJXR_NECP_M18_11_00001.bc | TBD | TC by TC
12 | Initiate VHV3 sweep |  | 60 | 0 | 73 | XDOR_BJXR_NECP_M18_12_00001.bc | TBD | TC by TC
13 | Regenerate mission data again: 60 min operation plus 1 h wait time | includes 1 hour of wait time | 120 | 0 | 73 | XDOR_BJXR_NECP_M18_13_00001.bc | TBD | TC by TC
MSA Mission Timeline operation
14 | Initial setup |  | 0 | 10 | 73 | XDOR_BJXR_NECP_M18_14_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
15 | CAL check |  | 0 | 60 | 73
16 | Regenerate mission data again: 60 min operation plus 1 h wait time |  | 0 | 120 | 73
17 | MDP SW check |  | 0 | 10 | 73
M19 | MPPE ENA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
ENA Nominal operation
1 | Initial power ON |  | 20 | 0 | 36 | XDOR_BJXR_NECP_M19_01_00001.bc | TBD | TC by TC
2 | Health check |  | 30 | 0 | 36 | XDOR_BJXR_NECP_M19_02_00001.bc | TBD | TC by TC
3 | Discrimination control (auto/manual) |  | 40 | 0 | 36 | XDOR_BJXR_NECP_M19_03_00001.bc | TBD | TC by TC
ENA HV operation
4 | Power ON |  | 5 | 0 | 74 | XDOR_BJXR_NECP_M19_04_00001.bc | TBD | TC by TC
5 | Cal Check |  | 15 | 0 | 74 | XDOR_BJXR_NECP_M19_05_00001.bc | TBD | TC by TC
6 | SAFETY ON HV check |  | 120 | 0 | 74 | XDOR_BJXR_NECP_M19_06_00001.bc | TBD | TC by TC
7 | SAFETY OFF |  | 6 | 0 | 74 | XDOR_BJXR_NECP_M19_07_00001.bc | TBD | TC by TC
8 | HVMAIN LEVEL UP |  | 90 | 0 | 74 | XDOR_BJXR_NECP_M19_08_00001.bc | TBD | TC by TC
9 | HVDEF LEVEL UP |  | 90 | 0 | 74 | XDOR_BJXR_NECP_M19_09_00001.bc | TBD | TC by TC
10 | HVSTOPMCP LEVEL UP (4 assemblies) |  | 180 | 0 | 74 | XDOR_BJXR_NECP_M19_10_00001.bc | TBD | TC by TC
11 | HVSTARTMCP LEVEL UP |  | 120 | 0 | 75 | XDOR_BJXR_NECP_M19_11_00001.bc | TBD | TC by TC
12 | SWEEP CHECK (4 output) |  | 120 | 0 | 75 | XDOR_BJXR_NECP_M19_12_00001.bc | TBD | TC by TC
13 | HV/DISCRI SCAN 3 |  | 180 | 0 | 75 | XDOR_BJXR_NECP_M19_13_00001.bc | TBD | TC by TC
14 | observation sequence |  | 120 | 0 | 75 | XDOR_BJXR_NECP_M19_14_00001.bc | TBD | TC by TC
15 | Regenerate mission data again: 120 min operation plus 1 h wait time | includes 1 hour of wait time | 180 | 0 | 76 | XDOR_BJXR_NECP_M19_15_00001.bc | TBD | TC by TC
ENA Mission Timeline operation
16 | Initial setup |  | 0 | 10 | 76 | XDOR_BJXR_NECP_M19_16_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
17 | function check |  | 0 | 30 | 76
18 | function check (HV operation) |  | 0 | 20 | 76
19 | Macro command check (mission data are generated) |  | 0 | 120 | 76
20 | Observation sequence (mission data production) |  | 0 | 120 | 76
21 | Regenerate mission data again: 120 min operation plus 1 h wait time | includes 1 hour of wait time | 0 | 180 | 76
M20 | MPPE HEP-e/-l commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
HEP-e Nominal operation
1 | Initial Power ON |  | 30 | 0 | 36 | XDOR_BJXR_NECP_M20_01_00001.bc | TBD | TC by TC
2 | Cal Check |  | 5 | 0 | 36 | XDOR_BJXR_NECP_M20_02_00001.bc | TBD | TC by TC
3 | Regenerate mission data again: 5 min operation plus 1 h wait time | includes 1 hour of wait time | 65 | 0 | 36 | XDOR_BJXR_NECP_M20_03_00001.bc | TBD | TC by TC
HEP-l Nominal operation
4 | Initial Power ON |  | 30 | 0 | 36 | XDOR_BJXR_NECP_M20_04_00001.bc | TBD | TC by TC
5 | Cal Check |  | 5 | 0 | 36 | XDOR_BJXR_NECP_M20_05_00001.bc | TBD | TC by TC
6 | Regenerate mission data again: 5 min operation plus 1 h wait time | includes 1 hour of wait time | 65 | 0 | 36 | XDOR_BJXR_NECP_M20_06_00001.bc | TBD | TC by TC
HEP-e HV operation
7 | HV ON/OFF with 0V output |  | 10 | 0 | 76 | XDOR_BJXR_NECP_M20_07_00001.bc | TBD | TC by TC
8 | HV ON/OFF with a few V output |  | 10 | 0 | 76 | XDOR_BJXR_NECP_M20_08_00001.bc | TBD | TC by TC
9 | HV LEVEL UP |  | 60 | 0 | 76 | XDOR_BJXR_NECP_M20_09_00001.bc | TBD | TC by TC
10 | Data check at the target HV Voltage |  | 30 | 0 | 76 | XDOR_BJXR_NECP_M20_10_00001.bc | TBD | TC by TC
11 | Regenerate mission data again: 30 min operation plus 1 h wait time | includes 1 hour of wait time | 90 | 0 | 76 | XDOR_BJXR_NECP_M20_11_00001.bc | TBD | TC by TC
HEP-l HV operation
12 | HV-L ON/OFF with 0V output |  | 10 | 0 | 76 | XDOR_BJXR_NECP_M20_12_00001.bc | TBD | TC by TC
13 | HV-L ON/OFF with a few V output |  | 10 | 0 | 76 | XDOR_BJXR_NECP_M20_13_00001.bc | TBD | TC by TC
14 | HV-L LEVEL UP |  | 60 | 0 | 76 | XDOR_BJXR_NECP_M20_14_00001.bc | TBD | TC by TC
15 | Data check at the target HV-L Voltage |  | 30 | 0 | 76 | XDOR_BJXR_NECP_M20_15_00001.bc | TBD | TC by TC
16 | Regenerate mission data again: 30min operation plus 1 h wait time | includes 1 hour of wait time | 90 | 0 | 77 | XDOR_BJXR_NECP_M20_16_00001.bc | TBD | TC by TC
17 | HV-H ON/OFF with 0V output |  | 10 | 0 | 77 | XDOR_BJXR_NECP_M20_17_00001.bc | TBD | TC by TC
18 | HV-H ON/OFF with a few V output |  | 20 | 0 | 77 | XDOR_BJXR_NECP_M20_18_00001.bc | TBD | TC by TC
19 | HV-H LEVEL UP (avg 1kV/h) |  | 240 | 0 | 77 | XDOR_BJXR_NECP_M20_19_00001.bc | TBD | TC by TC
20 | Data check at the target HV-H Voltage |  | 60 | 0 | 77 | XDOR_BJXR_NECP_M20_20_00001.bc | TBD | TC by TC
21 | Regenerate mission data again: 60 min operation plus 1 h wait time | includes 1 hour of wait time | 120 | 0 | 77 | XDOR_BJXR_NECP_M20_21_00001.bc | TBD | TC by TC
HEP-e/HEP-l Mission Timeline operation (at the same time)
22 | Initial setup |  | 0 | 30 | 73 | XDOR_BJXR_NECP_M20_22_00001.bc | TBD | MTL | Only one XDOR file for MTL operations is needed
23 | ASIC check |  | 0 | 30 | 73
24 | CAL check |  | 0 | 60 | 73
25 | ASIC parameter scan check |  | 0 | 60 | 73
26 | Regenerate mission data of Cal Check again: 60 min operation | 1 h wait time satisfied | 0 | 60 | 73

## M01 - M05, M51-M54,M57-59BUS
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | cpa file name | cps Chapter
M51 | HK Mode change
1 |  |  | 4 | 0 | 15 | XDOR_BJXR_C001_NECP_M510101_00002.BC | 2 | TC by TC |  |  | main2-BUS_NECP_XDOR_002_M01_M03.cps | 1-3.4
M01 | PCS commissioning | [10 empty] | 3.5 -3.5.5.3
1 |  |  | 90 | 0 | 15 | XDOR_BJXR_C002_NECP_M010101_00002.BC | 6 | Relative
[6 empty] | XDOR_BJXR_C003_NECP_M010102_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C004_NECP_M010103_00002.BC | 6 | Relative
[6 empty] | XDOR_BJXR_C005_NECP_M010104_00002.BC | 5 | TC by TC
[6 empty] | XDOR_BJXR_C006_NECP_M010105_00002.BC | 2 | Relative
M02 | ACS commissioning | [10 empty] | 3.5.7 - 3.8.3.2
1 |  |  | 250 | 0 | 15 | XDOR_BJXR_C007_NECP_M020101_00002.BC | 34 | TC by TC
[6 empty] | XDOR_BJXR_C008_NECP_M020102_00002.BC | 24 | Relative
[6 empty] | XDOR_BJXR_C009_NECP_M020103_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C010_NECP_M020104_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C011_NECP_M020105_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C012_NECP_M020106_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C013_NECP_M020107_00002.BC | 5 | TC by TC
[6 empty] | XDOR_BJXR_C014_NECP_M020108_00002.BC | 9 | Relative
[6 empty] | XDOR_BJXR_C015_NECP_M020109_00002.BC | 1
[6 empty] | XDOR_BJXR_C016_NECP_M020110_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C017_NECP_M020111_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C018_NECP_M020112_00002.BC | 10 | Relative
[6 empty] | XDOR_BJXR_C019_NECP_M020113_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C020_NECP_M020114_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C021_NECP_M020115_00002.BC | 6 | TC by TC
M03 | [11 empty] | 3.9 - 3.13
1 | DMC commissioning |  | 60 | 0 | 15 | XDOR_BJXR_C022_NECP_M030101_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C023_NECP_M030102_00002.BC | 2
[6 empty] | XDOR_BJXR_C024_NECP_M030103_00002.BC | 8
[6 empty] | XDOR_BJXR_C025_NECP_M030104_00002.BC | 5
M04 | [11 empty] | 5.1
1 | TCS comissioning |  | 0 | 45 | 16 | XOR__BJXR_C001_NECP_M040101_00003.BC | 63 | MTL |  |  | main2-BUS_NECP_XOR_002_M04.cps
M05 |  | This activity is including the HV checkout of the TWTA (TWTA-A and TWTA-B). | [6 empty] | Constraints: not earlier as 2 m after launch, Different from the HV checkout of MPPE, stepwise HV increasing approach is not necessary for the TWTA HV checkout.
1 | COM-TWTA commissioning |  | 120 |  | DAY-1 |  | TBD | TC by TC | HV commissioning during pass
M52
1 | Preparation for MMO mission commissioning (Set up Before MDP Check) |  | 60 |  | 17 | XDOR_BJXR_C026_NECP_M520101_00002.BC | 5 | TC by TC, relative |  |  | main2-SETUPa_NECP_XDOR_002_M52.cps
[6 empty] | XDOR_BJXR_C027_NECP_M520102_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C028_NECP_M520103_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C029_NECP_M520104_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C030_NECP_M520105_00002.BC | 64 | Relative
[6 empty] | XDOR_BJXR_C031_NECP_M520106_00002.BC | 32 | Relative
[6 empty] | XDOR_BJXR_C032_NECP_M520107_00002.BC | 8 | Relative
M53
1 | Preparation for MMO mission commissioning (Set up MDP off & MMO off) |  | 60 |  | 33 | XDOR_BJXR_C033_NECP_M530101_00002.BC | 5 | TC by TC |  |  | main2-SETUPb2_NECP_XDOR_002_M53.cps
[6 empty] | XDOR_BJXR_C034_NECP_M530102_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C035_NECP_M530103_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C036_NECP_M530104_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C037_NECP_M530105_00002.BC | 64 | Relative
[6 empty] | XDOR_BJXR_C038_NECP_M530106_00002.BC | 32 | Relative
[6 empty] | XDOR_BJXR_C039_NECP_M530107_00002.BC | 8
[6 empty] | XDOR_BJXR_C040_NECP_M530108_00002.BC | 3
M54
99 | contingency (Set up MDP off & MMO on) |  | 60 |  |  | XDOR_BJXR_C041_NECP_M549901_00002.BC | 1 | TC by TC |  |  | main2-SETUP_contingency_NECP_XDOR_002_M54.cps
[6 empty] | XDOR_BJXR_C042_NECP_M549902_00002.BC | 64 | Relative
[6 empty] | XDOR_BJXR_C043_NECP_M549903_00002.BC | 32 | Relative
[6 empty] | XDOR_BJXR_C044_NECP_M549904_00002.BC | 8 | Relative
[6 empty] | XDOR_BJXR_C045_NECP_M549905_00002.BC | 3 | TC by TC
M57
99 | PPWR_CHNG contingency |  |  |  |  | XDOR_BJXR_C046_NECP_M579901_00001.BC | TBD | TC by TC |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG1(-5)_001.cps
[6 empty] | XDOR_BJXR_C047_NECP_M579902_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG1_001.cps
[6 empty] | XDOR_BJXR_C048_NECP_M579903_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG2_001.cps
[6 empty] | XDOR_BJXR_C049_NECP_M579904_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG3_001.cps
[6 empty] | XDOR_BJXR_C050_NECP_M579905_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG4_001.cps
[6 empty] | XDOR_BJXR_C791_NECP_M579906_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG5_001.cps
[6 empty] | XDOR_BJXR_C792_NECP_M579907_00001.BC |  |  |  |  | main2-BUS_NECP_contingency_XDOR_PPWR_CHNG1(-5)_001.cps
M58
99 | Macro ENA contingency |  |  |  |  | XDOR_BJXR_C793_NECP_M589901_00001.BC | 1 | TC by TC |  |  | dcsm-7740_20181109.cps
[6 empty] | XDOR_BJXR_C794_NECP_M589902_00001.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C795_NECP_M589903_00002.BC | 14 | Relative
[6 empty] | XDOR_BJXR_C796_NECP_M589904_00001.BC | 1 | TC by TC
M59
1 | TCFS ROM REWRITE | TCFS ROM REWRITE |  |  |  | XDOR_BJXR_C804_NECP_M590101_00001.BC | 23 | TC by TC |  |  | main2-TCFS_TBL_WRITE_NECP_XDOR_M59_001.cps
[6 empty] | XDOR_BJXR_C805_NECP_M590102_00001.BC | 24
2 | TLM MODE change (TLMmode6) | TLMmode変更 (TLMmode6） |  |  |  | XDOR_BJXR_C806_NECP_M590201_00001.BC | 2 | TC by TC |  |  | dcsm-tcfs_tbl1_deck_dty_set-1(2)_XDOR_M59_001.cps,dcsm-tcfs_tbl1_deck_5(,10,15)degC-1(2)_XDOR_M59_001.cps. dcsm-tcfs_tbl1_ram_rewrite_XDOR_M59_001.cps, dcsm-tcfs_tbl1_bat_set_XDOR_M59_001.cps
| BAT heater setting | BAT設定 |  |  |  | XDOR_BJXR_C807_NECP_M590202_00001.BC | 8 |  |  |  | dcsm-tcfs_tbl1_bat_set_XDOR_M59_001.cps
[6 empty] | XDOR_BJXR_C808_NECP_M590203_00001.BC | 2
[6 empty] | XDOR_BJXR_C809_NECP_M590204_00001.BC | 6
| DUTY100% Lower/Upper2,6(HTR ch. 9,11,17,19) | DUTY（100％）変更 Lower/Upper2,6(ヒータCH9,11,17,19) |  |  |  | XDOR_BJXR_C810_NECP_M590205_00001.BC | 4 |  |  |  | dcsm-tcfs_tbl1_deck_dty_set-1_XDOR_M59_001.cps
[6 empty] | XDOR_BJXR_C811_NECP_M590206_00001.BC | 3
| HTR setting change: Lower/Upper2,6(HTR ch. 9,11,17,19) +5℃ | 制御温度変更 Lower/Upper2,6(ヒータCH9,11,17,19) ＋5℃設定 |  |  |  | XDOR_BJXR_C812_NECP_M590207_00001.BC | 4 |  |  |  | dcsm-tcfs_tbl1_deck_5degC-1_XDOR_M59_001.cps
| HTR setting change: Lower/Upper2,6(HTR ch. 9,11,17,19) ＋10℃ | 制御温度変更 Lower/Upper2,6(ヒータCH9,11,17,19) ＋10℃設定 |  |  |  | XDOR_BJXR_C813_NECP_M590208_00001.BC | 4 |  |  |  | dcsm-tcfs_tbl1_deck_10degC-1_XDOR_M59_001.cps
| HTR setting change: Lower/Upper2,6(HTR ch. 9,11,17,19) ＋15℃ | 制御温度変更 Lower/Upper2,6(ヒータCH9,11,17,19) ＋15℃設定 |  |  |  | XDOR_BJXR_C814_NECP_M590209_00001.BC | 4 |  |  |  | dcsm-tcfs_tbl1_deck_15degC-1_XDOR_M59_001.cps
| ONESHOT TLM | ONESHOT |  |  |  | XDOR_BJXR_C815_NECP_M590210_00001.BC | 3 |  |  |  | dcsm-tcfs_tbl1_deck_5(,10,15)degC-1(2)_XDOR_M59_001.cps
| DUTY100% Lower/Upper1,3,5,7(HTR ch. 1-4,25-28) | DUTY（100％）変更 Lower/Upper1,3,5,7(ヒータCH1-4,25-28) |  |  |  | XDOR_BJXR_C816_NECP_M590211_00001.BC | 8 |  |  |  | dcsm-tcfs_tbl1_deck_dty_set-2_XDOR_M59_001.cps
[6 empty] | XDOR_BJXR_C817_NECP_M590212_00001.BC | 3
| HTR setting change: Lower/Upper1,3,5,7(HTR ch. CH1-4,25-28) +5℃ | 制御温度変更 Lower/Upper1,3,5,7(ヒータCH1-4,25-28) ＋5℃設定 |  |  |  | XDOR_BJXR_C818_NECP_M590213_00001.BC | 8 |  |  |  | dcsm-tcfs_tbl1_deck_5degC-2_XDOR_M59_001.cps
| HTR setting change: Lower/Upper1,3,5,7(HTR ch. CH1-4,25-28) +10℃ | 制御温度変更 Lower/Upper1,3,5,7(ヒータCH1-4,25-28) ＋10℃設定 |  |  |  | XDOR_BJXR_C819_NECP_M590214_00001.BC | 8 |  |  |  | dcsm-tcfs_tbl1_deck_10degC-2_XDOR_M59_001.cps
| HTR setting change: Lower/Upper1,3,5,7(HTR ch. CH1-4,25-28) +15℃ | 制御温度変更 Lower/Upper1,3,5,7(ヒータCH1-4,25-28) ＋15℃設定 |  |  |  | XDOR_BJXR_C820_NECP_M590215_00001.BC | 8 |  |  |  | dcsm-tcfs_tbl1_deck_15degC-2_XDOR_M59_001.cps
| Set Peak Power 100Ｗ | ピークパワー100Ｗ設定 |  |  |  | XDOR_BJXR_C821_NECP_M590216_00001.BC | 5 |  |  |  | dcsm-tcfs_ppwr_100_XDOR_M59_001.cps
| Set Peak Power 150Ｗ | ピークパワー150Ｗ設定 |  |  |  | XDOR_BJXR_C822_NECP_M590217_00001.BC | 5 |  |  |  | dcsm-tcfs_ppwr_150_XDOR_M59_001.cps
| Set Peak Power 200Ｗ | ピークパワー200Ｗ設定 |  |  |  | XDOR_BJXR_C823_NECP_M590218_00001.BC | 5 |  |  |  | dcsm-tcfs_ppwr_200_XDOR_M59_001.cps
| Reset Heater tables to default value(TBL_ROM) | TBL_ROMの内容へ設定戻し |  |  |  | XDOR_BJXR_C824_NECP_M590219_00001.BC | 24 |  |  |  | dcsm-tcfs_tbl1_ram_rewrite_XDOR_M59_001.cps
[6 empty] | XDOR_BJXR_C825_NECP_M590220_00001.BC | 2
[6 empty] | XDOR_BJXR_C826_NECP_M590221_00001.BC | 3
[6 empty] | XDOR_BJXR_C827_NECP_M590222_00001.BC | 2
[6 empty] | XDOR_BJXR_C828_NECP_M590223_00001.BC | 1
99 | TCSF Setting Change | used in 1st commisioning slot |  |  |  | XDOR_BJXR_C798_NECP_M599901_00002.BC | 2 |  |  |  | dcsm-tcfs_tbl1_ram_chng_M59_002.cps
[6 empty] | XDOR_BJXR_C799_NECP_M599902_00001.BC | 6 | Relative
[6 empty] | XDOR_BJXR_C800_NECP_M599903_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C801_NECP_M599904_00001.BC | 3
[6 empty] | XDOR_BJXR_C802_NECP_M599905_00001.BC | 2
[6 empty] | XDOR_BJXR_C803_NECP_M599906_00001.BC | 2

## M06 BUS BATCHK
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | cpa file name | cps Chapter
M06 | BAT Check
1 | MONI_ON~BUS_SETUP |  | 4 | 0 | 15 | XOR__BJXR_C002_BATC_M060101_00001.BC |  |  |  |  | main2-BAT_CHK_PART1-1_MONI_ON_TO_BUS_SETUP_XOR_001_M06.cps
2 | MONI_OFF～MMO_OFF |  |  |  |  | XOR__BJXR_C003_BATC_M060102_00001.BC |  |  |  |  | main2-BAT_CHK_PART1-2_MONI_OFF_TO_MMO_OFF_XOR_001_M06.cps
3 | MONI_ON~LR_Charge_BAT_EXT |  | 90 | 0 | 15 | XOR__BJXR_C004_BATC_M060201_00001.BC |  |  |  |  | main2-BAT_CHK_PART2-1_MONI_ON_TO_LR_Charge_BAT_EXT_XOR_001_M06.cps
4 | MONI_OFF～MMO_OFF |  |  |  |  | XOR__BJXR_C005_BATC_M060202_00001.BC |  |  |  |  | main2-BAT_CHK_PART2-2_MONI_OFF_TO_MMO_OFF_XOR_001_M06.cps

## M08 MDP
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M08 | MDP commissioning | Mission Data Processor commissioning | [6 empty] | Constraints: To be done first in mission subsystem commissioning slot
1 | Power ON |  | 20 | 0 | 16 | XDOR_BJXR_C101_NECP_M080101_00002.BC | 2 | Relative | [5 empty] | main2-MDP_NECP_LV_XDOR_002_M08.cps
[6 empty] | XDOR_BJXR_C102_NECP_M080102_00002.BC | 5 | Relative
2 | Firm DMC-IF, memory check |  | 170 | 0 | 16 | XDOR_BJXR_C103_NECP_M080201_00002.BC | 2 | Relative |  |  | ERR CHECK |  | Power OFF after this step |  | 3.1667 | h
[6 empty] | XDOR_BJXR_C104_NECP_M080202_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C105_NECP_M080203_00002.BC | 10 | Relative
[6 empty] | XDOR_BJXR_C106_NECP_M080204_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C107_NECP_M080205_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C108_NECP_M080206_00002.BC | 7 | Relative
[6 empty] | XDOR_BJXR_C109_NECP_M080207_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C110_NECP_M080208_00002.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C111_NECP_M080209_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C112_NECP_M080210_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C113_NECP_M080211_00002.BC | 5 | Relative
3 | Firm CMD check |  | 250 | 0 | 17 | XDOR_BJXR_C114_NECP_M080301_00002.BC | 5 | Relative |  |  | ERR CHECK | Before this step | Power ON in this step |  | 6.8333 | h
[6 empty] | XDOR_BJXR_C115_NECP_M080302_00002.BC | 18 | Relative
[6 empty] | XDOR_BJXR_C116_NECP_M080303_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C117_NECP_M080304_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C118_NECP_M080305_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C119_NECP_M080306_00002.BC | 12 | Relative
[6 empty] | XDOR_BJXR_C120_NECP_M080307_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C121_NECP_M080308_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C122_NECP_M080309_00002.BC | 7 | Relative
[6 empty] | XDOR_BJXR_C123_NECP_M080310_00002.BC | 8 | Relative
[6 empty] | XDOR_BJXR_C124_NECP_M080311_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C125_NECP_M080312_00002.BC | 22 | Relative
[6 empty] | XDOR_BJXR_C126_NECP_M080313_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C127_NECP_M080314_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C128_NECP_M080315_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C129_NECP_M080316_00002.BC | 16 | Relative
[6 empty] | XDOR_BJXR_C130_NECP_M080317_00002.BC | 7 | Relative | [5 empty] | main2-MDP_NECP_LV_XDOR_003_M08.cps
[6 empty] | XDOR_BJXR_C131_NECP_M080318_00002.BC | 6 | Relative
[6 empty] | XDOR_BJXR_C132_NECP_M080319_00002.BC | 10 | Relative
[6 empty] | XDOR_BJXR_C133_NECP_M080320_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C134_NECP_M080321_00002.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C135_NECP_M080322_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C136_NECP_M080323_00002.BC | 10 | Relative
[6 empty] | XDOR_BJXR_C137_NECP_M080324_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C138_NECP_M080325_00002.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C139_NECP_M080326_00002.BC | 4 | Relative
4 | Memory load and dump |  | 60 | 0 | 17 | XDOR_BJXR_C140_NECP_M080401_00002.BC | 1 | TC by TC |  |  | ERR CHECK
[6 empty] | XDOR_BJXR_C141_NECP_M080402_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C142_NECP_M080403_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C143_NECP_M080404_00002.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C144_NECP_M080405_00002.BC | 7 | Relative
[6 empty] | XDOR_BJXR_C145_NECP_M080406_00002.BC | 3 | Relative
[6 empty] | XDOR_BJXR_C146_NECP_M080407_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C147_NECP_M080408_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C148_NECP_M080409_00002.BC | 5 | Relative
[6 empty] | XDOR_BJXR_C149_NECP_M080410_00002.BC | 7 | Relative
[6 empty] | XDOR_BJXR_C150_NECP_M080411_00003.BC | 5 | Relative
5 | Applications |  | 80 | 0 | 18 | XDOR_BJXR_C779_NECP_M080501_00003.BC | 3 | Relative |  |  | ERR CHECK
[6 empty] | XDOR_BJXR_C780_NECP_M080502_00002.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C781_NECP_M080503_00002.BC | 2 | Relative
6 | Power OFF |  | 20 | 0 | 18 | XDOR_BJXR_C782_NECP_M080601_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C783_NECP_M080602_00002.BC | 1 | TC by TC
contingency
98 | MDP ERR LOG DUMP contingency |  | 20? | 0 |  | XDOR_BJXR_C797_NECP_M089801_00003.BC | 8 | TC by TC | [5 empty] | main2-MDP_NECP_ERR_LOG_DUMP_contingency_003_M08.cps
99 | contingency |  | 20? | 0 |  | XDOR_BJXR_C789_NECP_M089901_00001.BC | 2 | TC by TC | [5 empty] | main2-MDP_NECP_contingency_001_M08.cps
[6 empty] | XDOR_BJXR_C790_NECP_M089902_00001.BC | 1

## M55 MDP ON
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M55 | MDP ON
1 | Power ON |  | 30 | 0 | 18 | XDOR_BJXR_C784_NECP_M550101_00002.BC | 2 | Relative | [5 empty] | main2-MDP_NECP_POWERON_XDOR_003_M55.cps
[6 empty] | XDOR_BJXR_C785_NECP_M550102_00002.BC | 1 | TC by TC
[6 empty] | XDOR_BJXR_C786_NECP_M550103_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C787_NECP_M550104_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C788_NECP_M550105_00003.BC | 4 | Relative

## M56 MDP OFF
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M56 | MDP OFF
Timeline operation
1 | Power OFF |  | 0 | 20 | 20 | XOR__BJXR_C101_NECP_M560101_00003.BC | 4 | MTL | [5 empty] | main2-MDP_NECP_POWEROFF_XOR_002_M56.cps

## M09 MAST
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments/Open Points | Comments | Contingency XDOR | Split point | Power ON status | cpa file name
M09 | MAST (latch release operations) | [7 empty] | Constraints: Quickly after WPT-S latch release
1 | PME ON |  | 10 | 0 | 19 | XDOR_BJXR_C151_NECP_M090101_00002.BC | 3 | TC by TC | [5 empty] | main2-MAST_NECP_LV_XDOR_002_M09.cps
2 | MWE ON and HK CHECK |  | 10 | 0 | 19 | XDOR_BJXR_C152_NECP_M090201_00002.BC | 1 | TC by TC
3 | MOTOR-PSU_ON CHECK |  | 20 | 0 | 19 | XDOR_BJXR_C153_NECP_M090301_00002.BC | 6 | TC by TC
4 | Control Command Check |  | 60 | 0 | 19 | XDOR_BJXR_C154_NECP_M090401_00002.BC | 15 | TC by TC
5 | MAST Command Check |  | 20 | 0 | 19 | XDOR_BJXR_C155_NECP_M090501_00002.BC | 5 | TC by TC
6 | WPT-S Command Check |  | 30 | 0 | 19 | XDOR_BJXR_C156_NECP_M090601_00002.BC | 9 | TC by TC
7 | Safety Command Check |  | 10 | 0 | 19 | XDOR_BJXR_C157_NECP_M090701_00002.BC | 2 | TC by TC
8 | MWE OFF |  | 10 | 0 | 19 | XDOR_BJXR_C158_NECP_M090801_00002.BC | 1 | TC by TC
9 | PME OFF |  | 10 | 0 | 19 | XDOR_BJXR_C159_NECP_M090901_00002.BC | 3 | TC by TC
10 | PME ON |  | 10 | 0 | 20 | XDOR_BJXR_C160_NECP_M091001_00002.BC | 3 | TC by TC |  |  |  | Can be split before this step
11 | MWE ON and HK CHECK |  | 10 | 0 | 20 | XDOR_BJXR_C161_NECP_M091101_00002.BC | 2 | TC by TC
12 | MAST latch release control command |  | 10 | 0 | 20 | XDOR_BJXR_C162_NECP_M091201_00002.BC | 4 | TC by TC
13 | MAST-SC latch release 1st |  | 60 | 0 | 20 | XDOR_BJXR_C163_NECP_M091301_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C164_NECP_M091302_00003.BC | 4
[6 empty] | XDOR_BJXR_C165_NECP_M091303_00002.BC | 1
| MAST-SC latch release 2nd |  |  |  |  | XDOR_BJXR_C166_NECP_M091304_00002.BC | 3
[6 empty] | XDOR_BJXR_C167_NECP_M091305_00003.BC | 4
[6 empty] | XDOR_BJXR_C168_NECP_M091306_00002.BC | 1
| MAST-SC latch release 3rd |  |  |  |  | XDOR_BJXR_C169_NECP_M091307_00002.BC | 3
[6 empty] | XDOR_BJXR_C170_NECP_M091308_00003.BC | 4
[6 empty] | XDOR_BJXR_C171_NECP_M091309_00002.BC | 1
| MAST-SC strap storage |  |  |  |  | XDOR_BJXR_C172_NECP_M091310_00002.BC | 3
[6 empty] | XDOR_BJXR_C173_NECP_M091311_00003.BC | 4
[6 empty] | XDOR_BJXR_C174_NECP_M091312_00002.BC | 1
14 | MAST-MGF latch release 1st |  | 60 | 0 | 20 | XDOR_BJXR_C175_NECP_M091401_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C176_NECP_M091402_00003.BC | 4
[6 empty] | XDOR_BJXR_C177_NECP_M091403_00002.BC | 1
| MAST-MGF latch release 2nd |  |  |  |  | XDOR_BJXR_C178_NECP_M091404_00002.BC | 3
[6 empty] | XDOR_BJXR_C179_NECP_M091405_00003.BC | 4
[6 empty] | XDOR_BJXR_C180_NECP_M091406_00002.BC | 1
| MAST-MGF latch release 3rd |  |  |  |  | XDOR_BJXR_C181_NECP_M091407_00002.BC | 3
[6 empty] | XDOR_BJXR_C182_NECP_M091408_00003.BC | 4
[6 empty] | XDOR_BJXR_C183_NECP_M091409_00002.BC | 1
| MAST-MGF strap storage |  |  |  |  | XDOR_BJXR_C184_NECP_M091410_00002.BC | 3
[6 empty] | XDOR_BJXR_C185_NECP_M091411_00003.BC | 4
[6 empty] | XDOR_BJXR_C186_NECP_M091412_00002.BC | 1
15 | Control parameter clear and MWE OFF |  | 20 | 0 | 20 | XDOR_BJXR_C187_NECP_M091501_00002.BC | 5 | TC by TC
16 | PME OFF |  | 10 | 0 | 20 | XDOR_BJXR_C188_NECP_M091601_00002.BC | 3 | TC by TC
contingency
97 | MAST_STBY contingency |  |  | 0 |  | XDOR_BJXR_C198_NECP_M099701_00001.BC | 11 | TC by TC | [5 empty] | main2-MAST_STBY_XDOR_M09_001.cps
98 | contingency_SC |  |  | 0 |  | XDOR_BJXR_C199_NECP_M099801_00002.BC | 4 | TC by TC | [5 empty] | main2-MAST_NECP_contingency_SC_002_M09.cps
99 | contingency_MGF |  |  |  |  | XDOR_BJXR_C200_NECP_M099901_00002.BC | 4 | [6 empty] | main2-MAST_NECP_contingency_MGF_002_M09.cps

## M10 WPT-S
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cps file name
M10 | PWI WPT-S (latch release operations) | As part of PWI, a pair of Wire antenna (WPT-S) needs its latch release operation in this activity. | [6 empty] | Constraints: - As soon as possible after launch, whereas around 25 days after launch is still acceptable. - Schedule after DMC, MDP and PWI commissioning - Schedule together with MAST latch release operations | Can this be scheduled in same pass as PWI, without PWI out of pass operation being executed?
1 | PME ON |  | 10 | 0 | 20 | XDOR_BJXR_C201_NECP_M100101_00002.BC | 3 | TC by TC | [5 empty] | main2-WPT-S_NECP_LV_XDOR_004_M10.cps
2 | PWI ON |  | 25 |  |  | XDOR_BJXR_C202_NECP_M100201_00002.BC | 19 | TC by TC
3 | MWE ON |  | 10 | 0 | 20 | XDOR_BJXR_C203_NECP_M100301_00002.BC | 2 | Relative
4 | HRM open control command |  | 20 | 0 | 20 | XDOR_BJXR_C204_NECP_M100401_00004.BC | 6 | TC by TC
5 | WPT-S1 HRM open operation 1st |  | 60 | 0 | 20 | XDOR_BJXR_C205_NECP_M100501_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C206_NECP_M100502_00003.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C207_NECP_M100503_00002.BC | 1 | TC by TC
| WPT-S1 HRM open operation 2nd |  |  |  |  | XDOR_BJXR_C208_NECP_M100504_00004.BC | 4 | TC by TC
[6 empty] | XDOR_BJXR_C209_NECP_M100505_00003.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C210_NECP_M100506_00002.BC | 1 | TC by TC
6 | WPT-S2 HRM open operation 1st |  | 60 | 0 | 20 | XDOR_BJXR_C211_NECP_M100601_00004.BC | 4 | TC by TC
[6 empty] | XDOR_BJXR_C212_NECP_M100602_00003.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C213_NECP_M100603_00002.BC | 1 | TC by TC
| WPT-S2 HRM open operation 2nd |  |  |  |  | XDOR_BJXR_C214_NECP_M100604_00004.BC | 4 | TC by TC
[6 empty] | XDOR_BJXR_C215_NECP_M100605_00003.BC | 4 | Relative
[6 empty] | XDOR_BJXR_C216_NECP_M100606_00002.BC | 1 | TC by TC
7 | Control parameter clear and MWE OFF |  | 20 | 0 | 20 | XDOR_BJXR_C217_NECP_M100701_00002.BC | 6 | TC by TC
8 | PWI CAL | Check the latch release result | 25 | 0 | 20 | XDOR_BJXR_C218_NECP_M100801_00002.BC | TBD | TC by TC | This includes commands, not just a TM check | should not include a PWI off at the end (MTL ops outside pass)
9 | PME OFF |  | 10 | 0 | 20 | XDOR_BJXR_C219_NECP_M100901_00002.BC | TBD | TC by TC
contingency
98 | contingency_WPTS1 |  |  | 0 |  | XDOR_BJXR_C249_NECP_M109801_00002.BC | TBD | TC by TC | [5 empty] | main2-WPT-S_NECP_contingency_WPTS1_002_M10.cps
99 | contingency_WPTS2 |  |  |  |  | XDOR_BJXR_C250_NECP_M109901_00002.BC | [7 empty] | main2-WPT-S_NECP_contingency_WPTS2_002_M10.cps

## M11 PWI
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M11 | PWI Commissioning | [7 empty] | Constraints: The PWI activities and the WPT-S latch release need to be grouped together (PWI activities first, then WPT-S latch release).
1 | EWO ON |  | 20 | 0 | 18 | XDOR_BJXR_C251_NECP_M110101_00002.BC | 10 | TC by TC | [5 empty] | main2-PWI_NECP_XDOR_002_M11.cps
2 | SORBET/AM2P/WPT-PRE/DBS-PA |  | 30 | 0 | 18 | XDOR_BJXR_C252_NECP_M110201_00002.BC | 10 | TC by TC |  |  |  | Can be split before this step | PWI is kept ON after this step
3 | MEFISTO ON |  | 60 | 0 | 19 | XDOR_BJXR_C253_NECP_M110301_00002.BC | 24 | TC by TC |  |  |  | Can be split before this step | PWI is kept ON before this step
[6 empty] | XDOR_BJXR_C254_NECP_M110302_00002.BC | 543 | Relative
4 | PWI Function test (all ON) |  | 80 | 0 | 19 | XDOR_BJXR_C255_NECP_M110401_00002.BC | 18 | TC by TC
[6 empty] | XDOR_BJXR_C256_NECP_M110402_00002.BC | 2 | Relative
[6 empty] | XDOR_BJXR_C257_NECP_M110403_00002.BC | 43 | TC by TC
5 | PWI OFF |  | 80 | 0 | 19 | XDOR_BJXR_C258_NECP_M110501_00002.BC | 6 | TC by TC
Mission Timeline operation
6 | OFA/EFD command/HK |  | 0 | 120 | 18 | XOR__BJXR_C251_NECP_M110601_00003.BC | 137 | MTL | TL activity can be scheduled between day 35 and 36 |  |  |  | PWI is kept ON before TL activity | main2-PWI_NECP_XOR_003_M11.cps

## M12 MGF
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M12 | MGF commissioning
1 | MGF-I Initial power ON, HK check and parameter set |  | 30 | 0 | 18 | XDOR_BJXR_C301_NECP_M120101_00002.BC | 8 | TC by TC | [5 empty] | main2-MGF_NECP_LV_XDOR_002_M12.cps
2 | MGF-O Initial power ON, HK check and parameter set |  | 30 | 0 | 18 | XDOR_BJXR_C302_NECP_M120201_00002.BC | 5 | TC by TC
[6 empty] | XDOR_BJXR_C303_NECP_M120202_00002.BC | 2 | Relative
3 | Power OFF by MACRO |  | 10 | 0 | 18 | XDOR_BJXR_C304_NECP_M120301_00002.BC | 1 | TC by TC
4 | Power ON and OFF by MACRO |  | 10 | 0 | 18 | XDOR_BJXR_C305_NECP_M120401_00002.BC | 5 | TC by TC |  |  |  |  | MGF is OFF after this step
Mission Timeline operation
5 | Power ON by MACRO |  | 0 | 10 | 19 | XOR_BJXR_C301_NECP_M120501_00003.BC | 49 | MTL | Only one XDOR file for MTL operations is needed |  |  |  | MGF is turned ON in this step | main2-MGF_NECP_LV_XOR_003_M12.cps
6 | MGF-I Observation sequence (get mission data) |  | 0 | 10 | 19
7 | MGF-O Observation sequence (get mission data) |  |  | 30 | 19
8 | Repeat observation sequence (get mission data) | includes 1 hour of wait time | 0 | 100 | 19
9 | Power OFF |  | 0 | 10 | 19
Cruise CheckOut
80 | Cruise CheckOut |  |  |  |  | XDOR_BJXR_C306_CRCO_M128001_00001.BC | 4 | [6 empty] | main2-MGF_CRCO_XDOR_001_M12.cps
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C350_NECP_M129901_00002.BC | 4 | [6 empty] | main2-MGF_NECP_contingency_LV_XDOR_002_M12.cps

## M13 MDM
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M13 | MDM commissioning
1 | Initial power ON |  | 20 | 0 | 34 | XDOR_BJXR_C351_NECP_M130101_00001.BC | 6 | TC by TC | [5 empty] | main2-MDM_NECP_LV_XDOR_001_M13.cps
2 | HK check |  | 10 | 0 | 34 |  |  |  | Status monitoring
3 | Observation mode check |  | 30 | 0 | 34 |  |  |  | Status monitoring |  |  |  | MDM is kept ON after this step
Mission Timeline operation
4 | Initial check |  | 0 | 20 | 34 | XOR__BJXR_C351_NECP_M130401_00003.BC | 33 | MTL | Only one XDOR file for MTL operations is needed |  |  |  | MDM is kept ON before TL activity | main2-MDM_NECP_LV_XOR_003_M13.cps
5 | Function check |  | 0 | 60 | 34
6 | Observation mode check |  | 0 | 40 | 34
7 | Repeat observation mode check | includes 1 hour of wait time | 0 | 100 | 34
8 | MDM OFF |  | 0 | 10 | 34
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C400_NECP_M139901_00002.BC | 4 | [6 empty] | main2-MDM_NECP_LV_XDOR_contingency_002_M13.cps

## M14 MSASI
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M14 | MSASI commissioning | This activity is including the HV checkout of the MSASI, in which the stepwise HV increase approach is necessary. | [6 empty] | Constraints: Typically not earlier than 2 months after launch HV increase rate: < 1 kV/day Assumption: user-HK telemetry rate = 16 sec -> Wait_sec: 1min
LV operation
0 | TLM mode change and cruise mode |  | 5 | 0 | 33 | XDOR_BJXR_C401_NECP_M140001_00002.BC | 2 | TC by TC | [5 empty] | main2-MSASI_NECP_LV_XDOR_002_M14.cps
1 | Initial power ON |  | 20 | 0 | 33 | XDOR_BJXR_C402_NECP_M140101_00002.BC | 5 | TC by TC |  |  |  |  | MSASI ON
2 | HT check |  | 30 | 0 | 33 | XDOR_BJXR_C403_NECP_M140201_00002.BC | 2 | TC by TC |  |  | HT OFF procedure
[6 empty] | XDOR_BJXR_C404_NECP_M140202_00002.BC | 2
[6 empty] | XDOR_BJXR_C405_NECP_M140203_00002.BC | 1
[6 empty] | XDOR_BJXR_C406_NECP_M140204_00002.BC | 2
[6 empty] | XDOR_BJXR_C407_NECP_M140205_00002.BC | 3
3 | G check |  | 40 | 0 | 33 | XDOR_BJXR_C408_NECP_M140301_00002.BC | 9 | TC by TC
4 | HV check (without HV ON) |  | 20 | 0 | 33 | XDOR_BJXR_C409_NECP_M140401_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C410_NECP_M140402_00002.BC | 2
[6 empty] | XDOR_BJXR_C411_NECP_M140403_00002.BC | 2
[6 empty] | XDOR_BJXR_C412_NECP_M140404_00002.BC | 2
5 | MSASI OFF |  | 10 | 0 | 33 | XDOR_BJXR_C413_NECP_M140501_00002.BC | 1 | TC by TC |  |  |  |  | MSASI OFF
[6 empty] | XDOR_BJXR_C414_NECP_M140502_00002.BC | 3
Mission Timeline operation (without HV)
6 | MSASI ON | 5TCs | 0 | 5 | 33 | XOR__BJXR_C401_NECP_M140601_00003.BC | 92 | MTL | Only one XDOR file for MTL operations is needed |  |  |  | Includes MSASI ON and OFF at end | main2-MSASI_NECP_LV_XOR_003_M14.cps
7 | Initial setup | 20 TCs | 0 | 20 | 33
8 | CMOS check | 34 TCs | 0 | 34 | 33
9 | Observation sequence (get mission data, HV OFF): 13 min (13 CMDs) + 150 min (waiting output of mission data from MDP to DMC) | 13 TCs | 0 | 173 | 33
10 | Repeat observation sequence | includes 1 hour of wait time, 13 TCs | 0 | 233 | 33
11 | Change dummy flag | 3 TCs | 0 | 5 | 33
12 | MSASI OFF | 4 TCs | 0 | 5 | 33
HV increase: +6 kV procedure (nominal: +5.6 kV)
0 | TLM mode change and cruise mode |  | 5 | 0 | 38 |  | 2 | TC by TC
13 | MSASI ON |  | 25 | 0 | 64 | XDOR_BJXR_C415_NECP_M141301_00001.BC | 5 | TC by TC |  |  |  |  | MSASI ON
14 | Initial HV ON |  | 30 | 0 | 64 | XDOR_BJXR_C416_NECP_M141401_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
15 | Increase HV (+1 kV) |  | 60 | 0 | 64 | XDOR_BJXR_C417_NECP_M141501_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
16 | Keep HV at +1 kV |  | 20 | 0 | 64 | [5 empty] | HV OFF procedure
17 | Increase HV (+2 kV) |  | 60 | 0 | 64 | XDOR_BJXR_C418_NECP_M141701_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
18 | Keep HV at +2 kV |  | 20 | 0 | 64 | [5 empty] | HV OFF procedure
19 | HV OFF |  | 10 | 0 | 64 | XDOR_BJXR_C419_NECP_M141901_00001.BC | TBD | TC by TC |  |  |  |  | MSASI is kept ON after this step
20 | Increase HV (+3kV) |  | 60 | 0 | 65 | XDOR_BJXR_C420_NECP_M142001_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step | MSASI is kept ON before this step
21 | Keep HV at +3 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
22 | Increasse HV (+4kV) |  | 60 | 0 | 65 | XDOR_BJXR_C421_NECP_M142201_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
23 | Keep HV at +4 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
24 | Increase HV (+5 kV) |  | 60 | 0 | 65 | XDOR_BJXR_C422_NECP_M142401_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
25 | Keep HV at +5 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
26 | Increase HV (+5.6 kV: nominal) |  | 40 | 0 | 65 | XDOR_BJXR_C423_NECP_M142601_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
27 | Keep HV at +5.6 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
28 | 0-5.6 kV (quickly) |  | 20 | 0 | 65 | XDOR_BJXR_C424_NECP_M142801_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
HV increase: -4 kV procedure (nominal: -1.4 kV)
29 | 0-1 kV (step by step ) |  | 60 | 0 | 65 | XDOR_BJXR_C425_NECP_M142901_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
30 | Keep HV at -1 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
31 | 0-1 kV (quickly) and 1.0-1.4 kV (step by step) |  | 30 | 0 | 65 | XDOR_BJXR_C426_NECP_M143101_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
32 | Keep HV at -1.4 kV |  | 20 | 0 | 65 | [5 empty] | HV OFF procedure
33 | 0-1.4 kV (quickly) |  | 20 | 0 | 65 | XDOR_BJXR_C427_NECP_M143301_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
34 | HV OFF |  | 10 | 0 | 65 | XDOR_BJXR_C428_NECP_M143401_00001.BC | TBD | TC by TC |  |  |  |  | MSASI is kept ON after this step
35 | Both P6K and N4K up to nominal |  | 30 | 0 | 66 | XDOR_BJXR_C429_NECP_M143501_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step | MSASI is kept ON before this step
HV operation (mission data check and observation sequence)
36 | Mission data check with HV (CAL mode) |  | 120 | 0 | 66 | XDOR_BJXR_C430_NECP_M143601_00001.BC | TBD | TC by TC |  | How is repetition of observation considered? | HV OFF procedure
37 | Observation sequence with HV (macro commands) |  | 150 | 0 | 66 | [5 empty] | HV OFF procedure
38 | MSASI OFF | 4 TCs | 10 | 0 | 66 | [7 empty] | MSASI OFF
contingency
99 | contingency |  |  |  | - | XDOR_BJXR_C448_NECP_M149901_00002.BC | 1 | TC by TC | [5 empty] | main2-MSASI_NECP_contingency_002_M14.cps

## M15 MPPE_MEA1
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M15 | MPPE MEA1 commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MEA1 Nominal operation
1 | Initial Power ON |  | 10 | 0 | 33 | XDOR_BJXR_C451_NECP_M150101_00002.BC | 4 | TC by TC | [5 empty] | main2-MEA_NECP_LV_XDOR_002_M15.cps
2 | MEM DUMP |  | 40 | 0 | 33 | XDOR_BJXR_C452_NECP_M150201_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C453_NECP_M150202_00002.BC | 3
[6 empty] | XDOR_BJXR_C454_NECP_M150203_00002.BC | 18
3 | SWITCH ON SCAN |  | 10 | 0 | 33 | XDOR_BJXR_C455_NECP_M150301_00002.BC | 3 | TC by TC
4 | TEST MODE ON |  | 15 | 0 | 33 | XDOR_BJXR_C456_NECP_M150401_00002.BC | 1 | TC by TC
5 | TEST MODE OFF |  | 10 | 0 | 33 | XDOR_BJXR_C457_NECP_M150501_00002.BC | 1 | TC by TC
6 | SWITCH OFF SCAN |  | 5 | 0 | 33 | XDOR_BJXR_C458_NECP_M150601_00002.BC | 1 | TC by TC
7 | MEA1 OFF |  | 5 | 0 | 33 | XDOR_BJXR_C459_NECP_M150701_00002.BC | 4 | TC by TC
MEA1 HV operation
8 | MEA1 Power ON |  | 10 | 0 | 72 | XDOR_BJXR_C460_NECP_M150801_00001.BC | TBD | TC by TC | [5 empty] | main2-MEA1_NECP_HV_RC_XDOR_001_M15.cps
| MEM DUMP |  | 30 | 0 | 72 |  | TBD | TC by TC
9 | SECURITY OFF |  | 15 | 0 | 72 | XDOR_BJXR_C461_NECP_M150901_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
10 | SWITCH ON MCP |  | 60 | 0 | 72 | XDOR_BJXR_C462_NECP_M151001_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH ON SCAN |  | 20 | 0 | 72 |  | TBD | TC by TC |  |  | HV OFF procedure
11 | TEST MODE ON |  | 15 | 0 | 72 | XDOR_BJXR_C463_NECP_M151101_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
| TEST MODE OFF |  | 10 | 0 | 72 |  | TBD | TC by TC |  |  | HV OFF procedure
12 | ENABLE OF HV ANALYZER |  | 25 | 0 | 72 | XDOR_BJXR_C464_NECP_M151201_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
13 | SWITCH ON MCP |  | 150 | 0 | 72 | XDOR_BJXR_C465_NECP_M151301_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
| SET GEOMETRIC FACTOR |  | 20 | 0 | 72 |  | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH OFF MCP |  | 75 | 0 | 72 |  | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH OFF SCAN |  | 10 | 0 | 72 |  | TBD | TC by TC |  |  | HV OFF procedure
14 | MEA1 OFF |  | 5 | 0 | 72 | XDOR_BJXR_C466_NECP_M151401_00001.BC | TBD | TC by TC
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C500_NECP_M159901_00002.BC | 5 | [6 empty] | main2-MEA_NECP_contingency_LV_XDOR_002_M15.cps

## M16 MPPE_MEA2
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M16 | MPPE MEA2 commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MEA2 Nominal operation
1 | Initial Power ON |  | 10 | 0 | 33 | XDOR_BJXR_C501_NECP_M160101_00002.BC | 4 | TC by TC | [5 empty] | main2-MEA_NECP_LV_XDOR_002_M16.cps
2 | MEM DUMP |  | 40 | 0 | 33 | XDOR_BJXR_C502_NECP_M160201_00002.BC | 3 | TC by TC
[6 empty] | XDOR_BJXR_C503_NECP_M160202_00002.BC | 3
[6 empty] | XDOR_BJXR_C504_NECP_M160203_00002.BC | 18
3 | SWITCH ON SCAN |  | 10 | 0 | 33 | XDOR_BJXR_C505_NECP_M160301_00002.BC | 3 | TC by TC
4 | TEST MODE ON |  | 15 | 0 | 33 | XDOR_BJXR_C506_NECP_M160401_00002.BC | 1 | TC by TC
5 | TEST MODE OFF |  | 10 | 0 | 33 | XDOR_BJXR_C507_NECP_M160501_00002.BC | 1 | TC by TC
6 | SWITCH OFF SCAN |  | 5 | 0 | 33 | XDOR_BJXR_C508_NECP_M160601_00002.BC | 1 | TC by TC
7 | MEA2 OFF |  | 5 | 0 | 33 | XDOR_BJXR_C509_NECP_M160701_00002.BC | 4 | TC by TC
MEA2 HV operation
8 | Power ON |  | 10 | 0 | 73 | XDOR_BJXR_C510_NECP_M160801_00001.BC | TBD | TC by TC | [5 empty] | main2-MEA2_NECP_HV_RC_XDOR_001_M16.cps
| MEM DUMP |  | 30 | 0 | 73 |  | TBD | TC by TC
9 | SECURITY OFF |  | 15 | 0 | 73 | XDOR_BJXR_C511_NECP_M160901_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
10 | SWITCH ON MCP |  | 60 | 0 | 73 | XDOR_BJXR_C512_NECP_M161001_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH ON SCAN |  | 20 | 0 | 73 |  | TBD | TC by TC |  |  | HV OFF procedure
11 | TEST MODE ON |  | 15 | 0 | 73 | XDOR_BJXR_C513_NECP_M161101_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
| TEST MODE OFF |  | 10 | 0 | 73 |  | TBD | TC by TC |  |  | HV OFF procedure
12 | ENABLE OF HV ANALYZER |  | 25 | 0 | 73 | XDOR_BJXR_C514_NECP_M161201_00001.BC | TBD | TC by TC |  |  | HV OFF procedure
13 | SWITCH ON MCP |  | 150 | 0 | 73 | XDOR_BJXR_C515_NECP_M161301_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
| SET GEOMETRIC FACTOR |  | 20 | 0 | 73 |  | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH OFF MCP |  | 75 | 0 | 73 |  | TBD | TC by TC |  |  | HV OFF procedure
| SWITCH OFF SCAN |  | 10 | 0 | 73 |  | TBD | TC by TC |  |  | HV OFF procedure
14 | MEA2 OFF |  | 5 | 0 | 73 | XDOR_BJXR_C516_NECP_M161401_00001.BC | TBD | TC by TC
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C550_NECP_M169901_00002.BC | 5 | [6 empty] | main2-MEA_NECP_contingency_LV_XDOR_002_M16.cps

## M17 MPPE_MIA
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M17 | MPPE MIA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MIA Nominal operation
1 | Initial Power ON |  | 15 | 0 | 33 | XDOR_BJXR_C551_NECP_M170101_00002.BC | 6 | TC by TC | [5 empty] | main2-MIA_NECP_LV_XDOR_002_M17.cps
2 | DATA MODE CHECK |  | 25 | 0 | 33 | XDOR_BJXR_C552_NECP_M170201_00002.BC | 4 | TC by TC
3 | ASIC CHECK |  | 5 | 0 | 33 | XDOR_BJXR_C553_NECP_M170301_00002.BC | 3 | TC by TC
|  |  | 5 |  |  | XDOR_BJXR_C554_NECP_M170302_00002.BC | 3
|  |  | 3 |  |  | XDOR_BJXR_C555_NECP_M170303_00002.BC | 1
|  |  | 4 |  |  | XDOR_BJXR_C556_NECP_M170304_00002.BC | 4
|  |  | 4 |  |  | XDOR_BJXR_C557_NECP_M170305_00002.BC | 3
|  |  | 4 |  |  | XDOR_BJXR_C558_NECP_M170306_00002.BC | 3
|  |  | 4 |  |  | XDOR_BJXR_C559_NECP_M170307_00002.BC | 5
|  |  | 3 |  |  | XDOR_BJXR_C560_NECP_M170308_00002.BC | 3
|  |  | 3 |  |  | XDOR_BJXR_C561_NECP_M170309_00002.BC | 4
|  |  | 3 |  |  | XDOR_BJXR_C562_NECP_M170310_00002.BC | 3
|  |  | 3 |  |  | XDOR_BJXR_C563_NECP_M170311_00002.BC | 2
|  |  | 3 |  |  | XDOR_BJXR_C564_NECP_M170312_00002.BC | 4
|  |  | 3 |  |  | XDOR_BJXR_C565_NECP_M170313_00002.BC | 3
4 | DEAD TIME CHECK |  | 3 |  |  | XDOR_BJXR_C566_NECP_M170401_00002.BC | 2
|  |  | 3 |  |  | XDOR_BJXR_C567_NECP_M170402_00002.BC | 1
5 | PHSCAN CHECK |  | 5 |  |  | XDOR_BJXR_C568_NECP_M170501_00002.BC | 4
|  |  | 10 |  |  | XDOR_BJXR_C569_NECP_M170502_00002.BC | 4
6 | OTHER CHECK |  | 15 | 0 | 33 | XDOR_BJXR_C570_NECP_M170601_00002.BC | 4 | TC by TC
7 | MIA OFF |  | 15 |  |  | XDOR_BJXR_C571_NECP_M170701_00002.BC | 5
MIA HV operation
8 | Power ON |  | TBD | 0 |  | XDOR_BJXR_C572_NECP_M170801_00001.BC | TBD | TC by TC | Duration of pass is 8.33h+1h for data loss - fits only marginally - risk accepted by JAXA |  |  |  |  | main2-MIA_NECP_HV_S_RC_XDOR_001_M17.cps | ３７５コマンド | ３７．５時間
9 | Cal Check |  | TBD | 0 |  | XDOR_BJXR_C573_NECP_M170901_00001.BC | TBD | TC by TC
10 | SAFETY ON HV check |  | TBD | 0 |  | XDOR_BJXR_C574_NECP_M171001_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
XDOR_BJXR_C575_NECP_M171002_00001.BC
XDOR_BJXR_C576_NECP_M171003_00001.BC
XDOR_BJXR_C577_NECP_M171004_00001.BC
XDOR_BJXR_C578_NECP_M171005_00001.BC
XDOR_BJXR_C579_NECP_M171006_00001.BC
XDOR_BJXR_C580_NECP_M171007_00001.BC
XDOR_BJXR_C581_NECP_M171008_00001.BC
11 | SAFETY OFF SAFETY OFF HV check |  | TBD | 0 |  | XDOR_BJXR_C582_NECP_M171101_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
12 | SVG HV LEVEL UP |  | TBD | 0 |  | XDOR_BJXR_C583_NECP_M171201_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
| SVS HV LEVEL UP |  | TBD | 0 |  |  | TBD | TC by TC |  |  | HV OFF procedure | Before this step
| MHV HV LEVEL UP |  | TBD | 0 |  |  | TBD | TC by TC |  |  | HV OFF procedure | Before this step | MIA is kept ON after this step
| SWEEP CHECK |  | TBD | 0 |  |  | TBD | TC by TC |  |  | HV OFF procedure | Before this step | MIA is kept ON before this step
| HV SCAN & PH SCAN check |  | TBD | 0 |  | XDOR_BJXR_C584_NECP_M171202_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step
XDOR_BJXR_C585_NECP_M171203_00001.BC
XDOR_BJXR_C586_NECP_M171204_00001.BC
| HV SCAN & PH SCAN check with macro commands |  | TBD | 0 |  |  | TBD | TC by TC |  |  | HV OFF procedure | Before this step
13 | MIA OFF |  | TBD | 0 |  | XDOR_BJXR_C587_NECP_M171301_00001.BC | TBD | TC by TC | If data loss happens, the activity can be holded and restarted after 1h waiting
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C600_NECP_M179901_00002.BC | 5 | [6 empty] | main2-MIA_NECP_contingency_LV_XDOR_002_M17.cps

## M18 MPPE_MSA
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M18 | MPPE MSA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
MSA Nominal operation
1 | Initial Power ON |  | 10 | 0 | 34 | XDOR_BJXR_C601_NECP_M180101_00002.BC | 5 | TC by TC | [5 empty] | main2-MSA_NECP_LV_XDOR_002_M18.cps
2 | Cal Check |  | 15 | 0 | 34 | XDOR_BJXR_C602_NECP_M180201_00002.BC | 5 | TC by TC
|  |  | 45 |  |  | XDOR_BJXR_C603_NECP_M180202_00002.BC | 10
3 | Power OFF |  | 10 | 0 | 34 | XDOR_BJXR_C604_NECP_M180301_00002.BC | 3 | TC by TC
MSA HV operation (max 8V)
4 | Power ON with HV |  | 10 | 0 | 74 | XDOR_BJXR_C607_NECP_M180401_00001.BC | TBD | TC by TC | Duration of pass is 8.66h+1h for data loss - fits only marginally - risk accepted by JAXA |  |  |  |  | main2-MSA_NECP_HV_CO_D1_XDOR_001_M18.cps
XDOR_BJXR_C608_NECP_M180402_00001.BC
| Cal Check |  | 30 | 0 | 74 | XDOR_BJXR_C609_NECP_M180403_00001.BC | TBD | TC by TC
5 | SAFETY ON HV CHECK |  | 100 | 0 | 74 | XDOR_BJXR_C610_NECP_M180501_00001.BC | TBD | TC by TC
| SAFETY OFF |  | 10 | 0 | 74 | XDOR_BJXR_C611_NECP_M180502_00001.BC | TBD | TC by TC
| Poweroff |  |  |  |  | XDOR_BJXR_C612_NECP_M180503_00001.BC
6 | SAFETY OFF HV CHECK |  | 120 | 0 | 74 | XDOR_BJXR_C613_NECP_M180601_00001.BC | TBD | TC by TC | [5 empty] | main2-MSA_NECP_HV_CO_D2_XDOR_001_M18.cps
7 | Set HV1 |  | 60 | 0 | 74 | XDOR_BJXR_C614_NECP_M180701_00001.BC | TBD | TC by TC
8 | Set HV2 |  | 60 | 0 | 74 | XDOR_BJXR_C615_NECP_M180801_00001.BC | TBD | TC by TC
9 | Set VHV1 and VHV2 (upto 3kV) |  | 120 | 0 | 74 | XDOR_BJXR_C616_NECP_M180901_00001.BC | TBD | TC by TC
XDOR_BJXR_C617_NECP_M180902_00001.BC
| VHV3 Check |  |  |  |  | XDOR_BJXR_C618_NECP_M180903_00001.BC
| switch OFF MSA HV from 6kV |  |  |  |  | XDOR_BJXR_C619_NECP_M180904_00001.BC
| VHV3 check |  |  |  |  | XDOR_BJXR_C620_NECP_M180905_00001.BC
10 | SAFETY ON HV check |  |  |  |  | XDOR_BJXR_C621_NECP_M181001_00001.BC | [7 empty] | main2-MSA_NECP_HV_CO_D3_XDOR_001_M18.cps
| SAFETY "OFF" HV check |  |  |  |  | XDOR_BJXR_C622_NECP_M181002_00001.BC
| Set VHV1 and VHV2 (from 6 to 8 kV) |  |  |  |  | XDOR_BJXR_C623_NECP_M181003_00001.BC
| VHV3 sweep on |  |  |  |  | XDOR_BJXR_C624_NECP_M181004_00001.BC
11 | switch OFF MSA HV from 8kV |  |  |  |  | XDOR_BJXR_C625_NECP_M181101_00001.BC
MSA Mission Timeline operation
21 | Initial setup |  | 0 | 10 | 75 | XOR__BJXR_C601NECP_M182101_00001.BC | TBD | MTL | Only one XDOR file for MTL operations is needed MSA is kept ON before TL activity |  |  |  | MSA is kept ON before TL activity
22 | CAL check |  | 0 | 60 | 75
23 | Regenerate mission data again: 60 min operation plus 1 h wait time |  | 0 | 120 | 75
24 | MDP SW check |  | 0 | 10 | 75
24 | Power OFF |  | 0 | 10 | 75
MSA Delta commissioning (LV)
30 | Initial setup->Cal Check |  |  |  |  | XDOR_BJXR_C605_NECP_M183001_00001.BC | 48 | TC by TC | [5 empty] | main2-MSA_NECP_LV_Delta_C_XDOR_M18.cps | Toatl=165コマンド
31 | Mission data check with AMP Discriminator |  |  |  |  | XDOR_BJXR_C606_NECP_M183101_00001.BC | 117 | TC by TC
contingency
99 | contingency |  |  |  |  | XDOR_BJXR_C650_NECP_M189901_00002.BC | 7 | [6 empty] | main2-MSA_NECP_LV_Delta_C_XDOR_M18.cps

## M19 MPPE_ENA
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M19 | MPPE ENA commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
ENA Nominal operation
1 | Initial power ON |  | 20 | 0 | 34 | XDOR_BJXR_C651_NECP_M190101_00002.BC | 4 | TC by TC | [5 empty] | main2-ENA_NECP_LV_XDOR_002_M19.cps
2 | Health check |  | 30 | 0 | 34 | XDOR_BJXR_C652_NECP_M190201_00002.BC | 2 | TC by TC
[6 empty] | XDOR_BJXR_C653_NECP_M190202_00002.BC | 8
3 | Discrimination control (auto/manual) |  | 40 | 0 | 34 | XDOR_BJXR_C654_NECP_M190301_00002.BC | 14 | TC by TC
[6 empty] | XDOR_BJXR_C655_NECP_M190302_00002.BC | 1
[6 empty] | XDOR_BJXR_C656_NECP_M190303_00002.BC | 27
[6 empty] | XDOR_BJXR_C657_NECP_M190304_00002.BC | 16
4 | ENA OFF |  | 10 | 0 | 34 | XDOR_BJXR_C658_NECP_M190401_00002.BC | 3 | TC by TC
ENA HV operation
5 | Power ON |  |  | 0 |  | XDOR_BJXR_C659_NECP_M190501_00001.BC | TBD | TC by TC | [5 empty] | main2-ENA_NECP_HV_SON_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF1_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF2_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF3_XDOR_001_M19.cps | ６６２コマンド
XDOR_BJXR_C660_NECP_M190502_00001.BC
6 | OBSERVATION MODE SET #1 |  |  | 0 |  | XDOR_BJXR_C661_NECP_M190601_00001.BC | TBD | TC by TC | 本手順実行前に「Power ON」、実行後に「Power OFF」を行うこと |  |  |  |  | main2-ENA_NECP_HV_SON_XDOR_001_M19.cps
XDOR_BJXR_C662_NECP_M190602_00001.BC
XDOR_BJXR_C663_NECP_M190603_00001.BC
XDOR_BJXR_C664_NECP_M190604_00001.BC
XDOR_BJXR_C665_NECP_M190605_00001.BC
XDOR_BJXR_C666_NECP_M190606_00001.BC
XDOR_BJXR_C667_NECP_M190607_00001.BC
XDOR_BJXR_C668_NECP_M190608_00001.BC
XDOR_BJXR_C669_NECP_M190609_00001.BC
XDOR_BJXR_C670_NECP_M190610_00001.BC
XDOR_BJXR_C671_NECP_M190611_00001.BC
XDOR_BJXR_C672_NECP_M190612_00001.BC
XDOR_BJXR_C673_NECP_M190613_00001.BC
7 | OBSERVATION MODE SET #2 |  |  | 0 |  | XDOR_BJXR_C674_NECP_M190701_00001.BC | TBD | TC by TC | 本手順実行前に「Power ON」、実行後に「Power OFF」を行うこと |  |  |  |  | main2-ENA_NECP_HV_SOF1_XDOR_001_M19.cps
XDOR_BJXR_C675_NECP_M190702_00001.BC
XDOR_BJXR_C676_NECP_M190703_00001.BC
XDOR_BJXR_C677_NECP_M190704_00001.BC
XDOR_BJXR_C678_NECP_M190705_00001.BC
XDOR_BJXR_C679_NECP_M190706_00001.BC
XDOR_BJXR_C680_NECP_M190707_00001.BC
XDOR_BJXR_C681_NECP_M190708_00001.BC
XDOR_BJXR_C682_NECP_M190709_00001.BC
XDOR_BJXR_C683_NECP_M190710_00001.BC
XDOR_BJXR_C684_NECP_M190711_00001.BC
XDOR_BJXR_C685_NECP_M190712_00001.BC
XDOR_BJXR_C686_NECP_M190713_00001.BC
XDOR_BJXR_C687_NECP_M190714_00001.BC
XDOR_BJXR_C688_NECP_M190715_00001.BC
XDOR_BJXR_C689_NECP_M190716_00001.BC
XDOR_BJXR_C690_NECP_M190717_00001.BC
XDOR_BJXR_C691_NECP_M190718_00001.BC
XDOR_BJXR_C692_NECP_M190719_00001.BC
XDOR_BJXR_C693_NECP_M190720_00001.BC
XDOR_BJXR_C694_NECP_M190721_00001.BC
XDOR_BJXR_C695_NECP_M190722_00001.BC
XDOR_BJXR_C696_NECP_M190723_00001.BC
XDOR_BJXR_C697_NECP_M190724_00001.BC
XDOR_BJXR_C833_NECP_M190725_00001.BC
XDOR_BJXR_C834_NECP_M190726_00001.BC
XDOR_BJXR_C835_NECP_M190727_00001.BC
XDOR_BJXR_C836_NECP_M190728_00001.BC
XDOR_BJXR_C837_NECP_M190729_00001.BC
8 | OBSERVATION MODE SET #3 |  |  | 0 |  | XDOR_BJXR_C838_NECP_M190801_00001.BC | TBD | TC by TC | 本手順実行前に「Power ON」、実行後に「Power OFF」を行うこと |  |  |  |  | main2-ENA_NECP_HV_SOF2_XDOR_001_M19.cps
XDOR_BJXR_C839_NECP_M190802_00001.BC
XDOR_BJXR_C840_NECP_M190803_00001.BC
9 | OBSERVATION MODE SET #4 |  |  | 0 |  | XDOR_BJXR_C841_NECP_M190901_00001.BC | TBD | TC by TC | 本手順実行前に「Power ON」、実行後に「Power OFF」を行うこと |  |  |  |  | main2-ENA_NECP_HV_SOF3_XDOR_001_M19.cps
XDOR_BJXR_C842_NECP_M190902_00001.BC
XDOR_BJXR_C843_NECP_M190903_00001.BC
XDOR_BJXR_C844_NECP_M190904_00001.BC
XDOR_BJXR_C845_NECP_M190905_00001.BC
XDOR_BJXR_C846_NECP_M190906_00001.BC
XDOR_BJXR_C847_NECP_M190907_00001.BC
XDOR_BJXR_C848_NECP_M190908_00001.BC
XDOR_BJXR_C849_NECP_M190909_00001.BC
XDOR_BJXR_C850_NECP_M190910_00001.BC
XDOR_BJXR_C851_NECP_M190911_00001.BC
10 | Power OFF |  |  | 0 |  | XDOR_BJXR_C852_NECP_M191001_00001.BC | TBD | TC by TC | [5 empty] | main2-ENA_NECP_HV_SON_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF1_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF2_XDOR_001_M19.cps main2-ENA_NECP_HV_SOF3_XDOR_001_M19.cps
ENA Mission Timeline operation
18 | Initial setup |  | 0 | 10 | 68 | XOR_BJXR_C651_NECP_M191801_00001.BC | TBD | MTL | Only one XDOR file for MTL operations is needed
19 | function check |  | 0 | 30 | 68
20 | function check (HV operation) |  | 0 | 20 | 68
21 | Macro command check (mission data are generated) |  | 0 | 120 | 68
22 | Observation sequence (mission data production) |  | 0 | 120 | 68
23 | Regenerate mission data again: 120 min operation plus 1 h wait time | includes 1 hour of wait time | 0 | 180 | 68
contingency
97 | contingency HV #1 |  |  |  |  | XDOR_BJXR_C698_NECP_M199701_00001.BC
98 | contingency #1 |  |  |  |  | XDOR_BJXR_C699_NECP_M199801_00002.BC | 6 | [6 empty] | main2-ENA_NECP_contingency_quick_002_M19.cps
99 | contingency #2 |  |  |  |  | XDOR_BJXR_C700_NECP_M199901_00002.BC | 6 | [6 empty] | main2-ENA_NECP_contingency2_normal_002_M19.cps

## M20 MPPE_HEP
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | NECP day | XDOR name | Number of TCs | Release Mode | Comments | Open Points | Contingency XDOR | Split point | Power ON status | cpa file name
M20 | MPPE HEP-e/-l commissioning | MPPE consists of 7 instruments (MEA1, MEA2, MSA, MIA, HEP-ele, HEP-ion, ENA). All of the instruments feature HV circuits. | [6 empty] | Constraints: Typically not earlier than 2 months after launch The HV checkout of each instrument should be also executed based on the stepwise HV increase approach.
HEP-e Nominal operation
1 | Initial Power ON Sequence (HEPe) |  | 20 | 0 | 34 | XDOR_BJXR_C701_NECP_M200101_00002.BC | 4 | TC by TC | [5 empty] | main2-HEP_NECP_LV_XDOR_002_M20.cps
2 | ASIC Initial Register set |  | 30 | 0 | 34 | XDOR_BJXR_C702_NECP_M200201_00002.BC | 3 | TC by TC
| ASIC Initial Parameter set and Load |  |  |  |  | XDOR_BJXR_C703_NECP_M200202_00002.BC | 5
| Temp Table Parameter set |  |  |  |  | XDOR_BJXR_C704_NECP_M200203_00002.BC | 7
| Temp Table change and Bit erroe Clear |  |  |  |  | XDOR_BJXR_C705_NECP_M200204_00002.BC | 5
3 | ASIC CAL Check Sequence |  | 30 | 0 | 34 | XDOR_BJXR_C706_NECP_M200301_00002.BC | 12 | TC by TC
4 | Initial Power OFF Sequence (HEPe) |  | 10 | 0 | 34 | XDOR_BJXR_C707_NECP_M200401_00002.BC | 4 | TC by TC
HEP-l Nominal operation
5 | Initial Power ON Sequence (HEPi) |  | 20 | 0 | 34 | XDOR_BJXR_C708_NECP_M200501_00002.BC | 4 | TC by TC
6 | ASIC Initial Register set |  | 30 | 0 | 34 | XDOR_BJXR_C709_NECP_M200601_00002.BC | 9 | TC by TC
| Temp Table Parameter set |  |  |  |  | XDOR_BJXR_C710_NECP_M200602_00002.BC | 7
| Temp Table change and Bit erroe Clear |  |  |  |  | XDOR_BJXR_C711_NECP_M200603_00002.BC | 5
7 | ASIC CAL Check Sequence |  | 30 | 0 | 34 | XDOR_BJXR_C712_NECP_M200701_00002.BC | 8 | TC by TC
| Mode SSD and TOF check |  |  |  |  | XDOR_BJXR_C713_NECP_M200702_00002.BC | 15
8 | Initial Power OFF Sequence (HEPi) |  | 10 | 0 | 34 | XDOR_BJXR_C714_NECP_M200801_00002.BC | 4 | TC by TC
HEP-e HV operation
9 | Power ON |  | 20 | 0 | 70 | XDOR_BJXR_C715_NECP_M200901_00001.BC | TBD | TC by TC | [5 empty] | main2-HEPE_NECP_HV_ONSTART_XDOR_001_M20.cps | TOTAL=149コマンド
10 | initial set |  | 30 | 0 | 70 | XDOR_BJXR_C716_NECP_M201001_00001.BC | TBD | TC by TC
11 | HV CHECK |  | 60 | 0 | 70 | XDOR_BJXR_C717_NECP_M201101_00001.BC | 22 | TC by TC | [5 empty] | main2-HEPE_NECP_HV_CHK_XDOR_001_M20.cps
12 | HV OFF |  | 60 | 0 | 70 | XDOR_BJXR_C718_NECP_M201201_00001.BC | TBD | TC by TC |  |  | HV OFF procedure |  | HEP-e is turned OFF in this step | main2-HEPE_NECP_HV_ONSTART_XDOR_001_M20.cps
HEP-l HV operation
13 | Power ON |  | 20 | 0 | 71 | XDOR_BJXR_C719_NECP_M201301_00001.BC | TBD | TC by TC |  |  |  | Before this step |  | main2-HEPI_NECP_HV_ONSTART_XDOR_001_M20.cps
14 | Setup |  | 30 | 0 | 71 | XDOR_BJXR_C720_NECP_M201401_00001.BC | TBD | TC by TC
15 | HEP-ion SSD HV CHECK |  | 60 | 0 | 71 | XDOR_BJXR_C721_NECP_M201501_00001.BC | 20 | TC by TC | [5 empty] | main2-HEPI_NECP_HV_SSD_CHK_XDOR_001_M20.cps
16 | HEP-ion MCP HV CHECK |  | 30 | 0 | 71 | XDOR_BJXR_C722_NECP_M201601_00001.BC | 54 | TC by TC | [5 empty] | main2-HEPI_NECP_HV_MCP_CHK_XDOR_001_M20.cps
17 | HEP-i OFF |  | 240 | 0 | 71 | XDOR_BJXR_C723_NECP_M201701_00001.BC | TBD | TC by TC |  |  | HV OFF procedure | Before this step |  | main2-HEPI_NECP_HV_ONSTART_XDOR_001_M20.cps
HEP-e/HEP-l Mission Timeline operation (at the same time)
23 | Power ON |  | 0 | 10 | 71 | XOR__BJXR_C701_NECP_M202301_00001.BC | TBD | MTL | Only one XDOR file for MTL operations is needed |  |  |  | HEP-e and HEP-I are OFF until this step
24 | Initial setup |  | 0 | 30 | 71
25 | ASIC check |  | 0 | 30 | 71
26 | CAL check |  | 0 | 60 | 71
27 | ASIC parameter scan check |  | 0 | 60 | 71
28 | Regenerate mission data of Cal Check again: 60 min operation | 1 h wait time satisfied | 0 | 60 | 71
contingency
96 | contingency HEP-e HV OFF |  |  |  |  | XDOR_BJXR_C747_NECP_M209601_00001.BC | 3 | TC by TC | [5 empty] | main2-HEPE_NECP_contingency_HV_XDOR_001_M20.cps
97 | contingency HEP-i HV OFF |  |  |  |  | XDOR_BJXR_C748_NECP_M209701_00001.BC | 3 | TC by TC | [5 empty] | main2-HEPI_NECP_contingency_HV_XDOR_001_M20.cps
98 | contingency HEP-e POWER OFF |  |  |  | - | XDOR_BJXR_C749_NECP_M209801_00002.BC | 3 | TC by TC | [5 empty] | main2-HEP_NECP_contingency_HEP-e_POWEROFF_002_M20.cps
99 | contingency HEP-i POWER OFF |  |  |  |  | XDOR_BJXR_C750_NECP_M209901_00002.BC | 3 | [6 empty] | main2-HEP_NECP_contingency_HEP-i_POWEROFF_002_M20.cps

## M80 Cruise CheckOut
Step | Activity | Scope | Duration Interactive [min] | Duration MTL [min] | DOY | XDOR name | Number of TCs | Release Mode | Comments | Open Points | cpa file name | cps Chapter | comment
M80 | Cruise CheckOut
1 | Cruise CheckOut xor |  | 0 | 527 | 135 | XOR__BJXR_C800_CRCO_M800101_00003.BC |  |  |  |  | main2-CRCO_PART1_XOR_001_M80.cps main2-CRCO_PART2_XOR_001_M80.cps |  | main2-CRCO_PART1_XOR_002_M80.cps ※次回以降の修正版 MDM ON追加 ENA WAIT_SEC変更 ERR_CLR 追加 2019.5.16
2 | Cruise CheckOut xdor |  | 0 | 527 | 135 | XDOR_BJXR_C831_CRCO_M800201_00002.BC |  |  |  |  | main2-CRCO_PART1_XDOR_001_M80.cps main2-CRCO_PART2_XDOR_001_M80.cps |  | main2-CRCO_PART1_XDOR_002_M80.cps ※次回以降の修正版 MDM ON追加 ENA WAIT_SEC変更 ERR_CLR 追加
3] | Cruise CheckOut PWI |  | 0 | 527 | 135 | XDOR_BJXR_C832_CRCO_M800301_00001.BC |  |  |  |  | main2-CRCO_PWI_XDOR_001_M80.cps

## Sheet1
C
001-100 | M1-M5,M31 | BUS
101-150 | M08 | MDP | > ・TimeLineのファイル名は
151-200 | M09 | MAST | > XOR__BJXR_T003_SVT_1c_PWI_Step_00001.BC ： 例
201-250 | M10 | WPT-S | > 本番 XOR__BJXR_C000_comment_00000.BC
251-300 | M11 | PWI | > という形になると思うのでファイル名修正しないとです。
301-350 | M12 | MGF | > ・Realのファイル名も
351-400 | M13 | MDM | > XDOR_BJXR_C000_comment_00000.BC T->Cに変更
401-450 | M14 | MSASI | > になります。
451-500 | M15 | MEA1
501-550 | M16 | MEA2
551-600 | M17 | MIA
601-650 | M18 | MSA
651-700 | M19 | ENA
701-750 | M20 | HEP
800 | M80 | Cruise CheckOut
751-999 | 予備