## 確認事項
NO. | 確認事項 | 回答 | CLOSE

## List
|  | Duration (sec) | source filename | filename |  | cmdcount
BUS ON | BUS_SETUP | 577 | main2-BUS_NECP_HV_MONI_ON_XDOR_001_M60.cps | dcsm-EF_BUS_MONI_ON.cps |  | 20
MDP ON | MDP_SETUP | 509 | main2-MDP_NECP_HV_ON_XDOR_001_M55.cps | dcsm-EF_MDP_ON.cps |  | 11
| MDP_CRUISE_SET | 42 | main2-MDP_CRUISE_SET.cps | dcsm-EF_MDP_CRUISE_SET.cps |  | 2
SI Power ON | MSA_ON_SETUP | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON.cps |  | 15
| PME_ON | 80 | main2-PME_ON.cps | dcsm-EF_PME_ON.cps |  | 2
| PWI_ON_SETUP | 868 | dcsm-EF_PWI_ON_CRUSE.cps | dcsm-EF_PWI_ON_CRUISE.cps |  | 27 | 520 | 180 | 868
| MGF_ON_SETUP | 14 | 20200410_Earth-fly-by_MGF_ON_20200221.cps | dcsm-EF_MGF_ON.cps |  | 3 |  | 168
| MEA_ON_SETUP_SW | 386 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA_ON_SW.cps |  | 21
| MEA1_ON_SETUP_SW | 292 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA1_ON_SW.cps |  | 12
| MEA_ON_SETUP_MAG | 386 | MEA_Earth_Flyby_4_ON_HVOFF.cps | dcsm-EF_MEA_ON_MAG.cps |  | 21
| ENA_ON_SETUP | 564 | ENA_power_ON.cps | dcsm-EF_ENA_power_ON.cps |  | 7
| MIA_ON_SETUP | 382 | main2-MIA_ON.cps | dcsm-EF_MIA_ON.cps |  | 6
| HEP_ON_SETUP | 1230 | main2-HEP_ON_START_for_TL.cps | dcsm-EF_HEP_ON_START_for_TL.cps |  | 34
| MDM_ON_SETUP | 202 | クルーズ観測手順.txt | dcsm-EF_MDM_ON.cps | 暫定的に600sec入れてある | 6
SI HV ON | MEA_HV_ON | 1756 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA_HV_ON.cps |  | 54
| MEA1_HV_ON | 1702 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA1_HV_ON.cps |  | 27
| MIA_HV_ON | 240 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON.cps |  | 6
| MIA_HV_ON_MAG | 142 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG.cps |  | 4
| MIA_HV_ON_SW | 102 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW.cps |  | 3
| MIA_HV_ON_RC | 280 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON_RC.cps |  | 7
| MIA_HV_ON_MAG_RC | 262 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG_RC.cps |  | 7
| MIA_HV_ON_SW_RC | 262 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW_RC.cps |  | 7
| MSA_HV_ON | 10954 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1.cps,dcsm-EF_MSA_HV_ON_2.cps |  | 232
| MSA_HV_ON_VFB | 6144 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps |  | 232
| ENA_HV_ON | 344 | ENA_HV_ON.cps | dcsm-EF_ENA_HV_ON.cps |  | 18
| ENA_HV_ON_H | 344 | ENA_HV_ON_H.cps | dcsm-EF_ENA_HV_ON_H.cps |  | 18
| HEP_HV_ON | 270 | main2-HEPE_HV_ON_OBS_START.cps | dcsm-EF_HEPE_HV_ON_OBS_START.cps |  | 6
TLM mode change (MODE_5) | TLM_MODE_5 | 42 | main2-BUS_TLM_MODE_5.cps | dcsm-EF_BUS_TLM_MODE_5.cps |  | 2
TLM mode change (MODE_10) | TLM_MODE_10 | 42 | main2-BUS_TLM_MODE_10.cps | dcsm-EF_BUS_TLM_MODE_10.cps |  | 2
SI HV OFF | HEP_HV_OFF | 190 | main2-HEPE_HV_OFF_OBS_OFF.cps | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps |  | 5
| ENA_HV_OFF | 198 | ENA_HV_OFF.cps | dcsm-EF_ENA_HV_OFF.cps |  | 4
| MSA_HV_OFF | 714 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF.cps |  | 24
| MSA_HV_OFF_VFB | 774 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF_VFB.cps |  | 25
| MIA_HV_OFF | 60 | main2-MIA_HV_OFF.cps | dcsm-EF_MIA_HV_OFF.cps |  | 1
| MEA_HV_SCAN_OFF | 210 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA_HV_SCAN_OFF.cps |  | 24
| MEA1_HV_SCAN_OFF | 186 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA1_HV_SCAN_OFF.cps |  | 12
| MEA_HV_OFF | 202 | MEA_Earth_Flyby_6_ON_HVOFF.cps | dcsm-EF_MEA_HV_OFF.cps |  | 20
| MEA1_HV_OFF | 182 | dcsm-EF_MEA1_HV_OFF.cps | dcsm-EF_MEA1_HV_OFF.cps |  | 10
SI Power OFF | HEP_OFF | 70 | main2-HEPE_OFF_STOP.cps | dcsm-EF_HEPE_OFF_STOP.cps |  | 4
| MIA_OFF | 160 | main2-MIA_OFF.cps | dcsm-EF_MIA_OFF.cps |  | 4
| ENA_OFF | 88 | ENA_power_OFF.cps | dcsm-EF_ENA_power_OFF.cps |  | 4
| MEA_OFF | 164 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA_OFF.cps |  | 6
| MEA1_OFF | 160 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA1_OFF.cps |  | 4
| MGF_OFF | 8 | 20200410_Earth-fly-by_MGF_OFF_20200221.cps | dcsm-EF_MGF_OFF.cps |  | 1
| PWI_OFF | 80 | main2-PWI_OFF.cps | dcsm-EF_PWI_OFF.cps |  | 2
| PME_OFF | 40 | main2-PME_OFF.cps | dcsm-EF_PME_OFF.cps |  | 1
| MSA_OFF | 380 | main2-MSA_OFF.cps | dcsm-EF_MSA_OFF.cps |  | 25
| MDM_OFF | 160 | クルーズ観測手順.txt | dcsm-EF_MDM_OFF.cps | 暫定的に600sec入れてある | 4
MDP OFF | MDP_OFF | 120 | main2-MDP_NECP_HV_POWEROFF_XDOR_001_M56.cps | dcsm-EF_MDP_POWEROFF.cps |  | 3
BUS OFF | BUS_OFF | 220 | main2-BUS_NECP_HV_MONI_OFF_XDOR_001_M61.cps | dcsm-EF_BUS_MONI_OFF.cps |  | 4
| MEA_OFF | 0
MDP ERR DUMP | MDP_DUMP | 9080 | main2-MDP_ERR_LOG_DUMP_TL_XDOR_001_M08.cps | dcsm-EF_MDP_ERR_DUMP.cps |  | 6
MDP AP9 DUMP | MDP_AP9_DUMP | 1880 | main2-MDP_AP09_LOG_DUMP_001_M08.cps | dcsm-MDP_AP09_LOG_DUMP.cps |  | 4
MACRO COMMAND ENA | MC_ENA | 246 | main2-MC_ENA_MDP_XDOR_001_M58.cps | dcsm-MC_ENA_MDP.cps |  | 21
| MSA_HV_ON_N | 0
| MSA_HV_OFF_N | 0

## wheel offloading
|  | CA time | 2020-10-15 03:58
Time to CA [h] | ID |  | date time excel | duration(s)
-51.5 | WOLS |  | 2020-10-13 00:28 | 1200
| WOLE |  | 2020-10-13 00:48 | 0
-36 | WOLS |  | 2020-10-13 15:58 | 1200
| WOLE |  | 2020-10-13 16:18 | 0
-23.5 | WOLS |  | 2020-10-14 04:28 | 1200 | WOL#1
| WOLE |  | 2020-10-14 04:48 | 0
-14.5 | WOLS |  | 2020-10-14 13:28 | 1200 | WOL#2
| WOLE |  | 2020-10-14 13:48 | 0
-4.5 | WOLS |  | 2020-10-14 23:28 | 1200 | WOL#3 | Power cycle
| WOLE |  | 2020-10-14 23:48 | 0
6.5 | WOLS |  | 2020-10-15 10:28 | 1200 | WOL#4
| WOLE |  | 2020-10-15 10:48 | 0
24.5 | WOLS |  | 2020-10-16 04:28 | 1200 | WOL#5
| WOLE |  | 2020-10-16 04:48 | 0
42.5 | WOLS |  | 2020-10-16 22:28 | 1200
| WOLE |  | 2020-10-16 22:48 | 0
Formulas:
date time excel = D1+[Time to CA [h]]/24
date time excel = [date time excel, row above]+[duration(s), row above]/3600/24

## Venus_flyby
# 2020/07/28 | [9 empty] | 5days
# WOL#1 |  | 2020-10-14 04:28 | [7 empty] | 2390
# WOL#2 |  | 2020-10-14 13:28 | [7 empty] | sum
# WOL#3 |  | 2020-10-14 23:28
# WOL#4 |  | 2020-10-15 10:28
# WOL#5 |  | 2020-10-16 04:28
Relative time (h) |  | Absolute time (UTC) | [7 empty] | 956
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | cmd count
|  | 2020-10-14 02:51 | 2020-10-14 03:01 |  | BUS ON | BUS_SETUP | 577 |  | dcsm-EF_BUS_MONI_ON.cps | 20
|  | 2020-10-14 03:01 | 2020-10-14 03:09 |  | MDP ON | MDP_SETUP | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2020-10-14 03:09 | 2020-10-14 03:10 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2020-10-14 03:10 | 2020-10-14 03:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-14 03:11 | 2020-10-14 03:29 |  | SI Power ON | MSA_ON_SETUP | 1092 |  | dcsm-EF_MSA_ON.cps | 15
|  | 2020-10-14 03:29 | 2020-10-14 03:30 |  |  | PME_ON | 80 |  | dcsm-EF_PME_ON.cps | 2
|  | 2020-10-14 03:30 | 2020-10-14 03:45 |  |  | PWI_ON_SETUP | 868 | Same as dust trail observation !! Conrimation needed !! | dcsm-EF_PWI_ON_CRUISE.cps | 27
|  | 2020-10-14 03:45 | 2020-10-14 03:45 |  |  | MGF_ON_SETUP | 14 |  | dcsm-EF_MGF_ON.cps | 3
|  | 2020-10-14 03:45 | 2020-10-14 03:52 |  |  | MEA_ON_SETUP_SW | 386 | Solar wind mode !! Confirmation needed !! | dcsm-EF_MEA_ON_SW.cps | 21
|  | 2020-10-14 03:52 | 2020-10-14 04:01 |  |  | ENA_ON_SETUP | 564 |  | dcsm-EF_ENA_power_ON.cps | 7
|  | 2020-10-14 04:01 | 2020-10-14 04:07 |  |  | MIA_ON_SETUP | 382 |  | dcsm-EF_MIA_ON.cps | 6
|  | 2020-10-14 04:07 | 2020-10-14 04:28 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2020-10-14 04:28 | 2020-10-14 04:48 | WOL #1 |  | 1800 | 1200 |  | #N/A | 0
|  | 2020-10-14 04:58 | 2020-10-14 05:02 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2020-10-14 05:02 | 2020-10-14 05:08 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H.cps | 18
|  | 2020-10-14 05:08 | 2020-10-14 05:13 |  |  | MIA_HV_ON_RC | 280 | With SAFETY OFF, solar wind mode !! Confirmation needed !! | dcsm-EF_MIA_HV_ON_RC.cps | 7
|  | 2020-10-14 05:13 | 2020-10-14 05:42 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON.cps | 54
|  | 2020-10-14 05:42 | 2020-10-14 07:24 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps | 232
|  | 2020-10-14 07:24 | 2020-10-14 07:25 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2020-10-14 07:25 | 2020-10-14 12:53 | Observation A |  |  | 19698 | 5.4717 |  | 0
|  | 2020-10-14 12:53 | 2020-10-14 12:54 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-14 12:54 | 2020-10-14 12:57 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2020-10-14 12:57 | 2020-10-14 13:01 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF.cps | 4
|  | 2020-10-14 13:01 | 2020-10-14 13:13 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB.cps | 25
|  | 2020-10-14 13:13 | 2020-10-14 13:14 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF.cps | 1
|  | 2020-10-14 13:14 | 2020-10-14 13:18 |  |  | MEA_HV_OFF | 202 | HV_OFF and SCAN kept ON !! Confirmation needed !! | dcsm-EF_MEA_HV_OFF.cps | 20
|  | 2020-10-14 13:28 | 2020-10-14 13:48 | WOL #2 |  | 2400 | 1200 |  | #N/A | 0
|  | 2020-10-14 13:58 | 2020-10-14 14:02 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2020-10-14 14:02 | 2020-10-14 14:08 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H.cps | 18
|  | 2020-10-14 14:08 | 2020-10-14 14:12 |  |  | MIA_HV_ON_SW_RC | 262 | With SAFETY OFF, solar wind mode !! Confirmation needed !! | dcsm-EF_MIA_HV_ON_SW_RC.cps | 7
|  | 2020-10-14 14:12 | 2020-10-14 14:42 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON.cps | 54
|  | 2020-10-14 14:42 | 2020-10-14 16:24 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps | 232
|  | 2020-10-14 16:24 | 2020-10-14 16:25 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2020-10-14 16:25 | 2020-10-14 21:44 | Observation B |  |  | 19143 | 5.3175 |  | 0
|  | 2020-10-14 21:44 | 2020-10-14 21:45 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-14 21:45 | 2020-10-14 21:48 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2020-10-14 21:48 | 2020-10-14 21:51 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF.cps | 4
|  | 2020-10-14 21:51 | 2020-10-14 22:04 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB.cps | 25
|  | 2020-10-14 22:04 | 2020-10-14 22:05 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF.cps | 1
|  | 2020-10-14 22:05 | 2020-10-14 22:08 |  |  | MEA_HV_SCAN_OFF | 210 | HV_OFF and SCAN OFF !! Confirmation needed !! | dcsm-EF_MEA_HV_SCAN_OFF.cps | 24
|  | 2020-10-14 22:08 | 2020-10-14 22:10 |  | SI Power OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2020-10-14 22:10 | 2020-10-14 22:12 |  |  | MIA_OFF | 160 |  | dcsm-EF_MIA_OFF.cps | 4
|  | 2020-10-14 22:12 | 2020-10-14 22:14 |  |  | ENA_OFF | 88 |  | dcsm-EF_ENA_power_OFF.cps | 4
|  | 2020-10-14 22:14 | 2020-10-14 22:16 |  |  | MEA_OFF | 164 |  | dcsm-EF_MEA_OFF.cps | 6
|  | 2020-10-14 22:16 | 2020-10-14 22:17 |  |  | MGF_OFF | 8 |  | dcsm-EF_MGF_OFF.cps | 1
|  | 2020-10-14 22:17 | 2020-10-14 22:18 |  |  | PWI_OFF | 80 |  | dcsm-EF_PWI_OFF.cps | 2
|  | 2020-10-14 22:18 | 2020-10-14 22:19 |  |  | PME_OFF | 40 |  | dcsm-EF_PME_OFF.cps | 1
|  | 2020-10-14 22:19 | 2020-10-14 22:25 |  |  | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF.cps | 25
|  | 2020-10-14 22:25 | 2020-10-14 22:27 |  | MDP OFF | MDP_OFF | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2020-10-14 22:27 | 2020-10-14 22:31 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP.cps | 21
|  | 2020-10-14 22:31 | 2020-10-14 22:39 |  | MDP ON | MDP_SETUP | 509 |  | dcsm-EF_MDP_ON.cps | 11
|  | 2020-10-14 22:39 | 2020-10-14 22:40 |  |  | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET.cps | 2
|  | 2020-10-14 22:40 | 2020-10-14 22:41 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-14 22:41 | 2020-10-14 22:59 |  | SI Power ON | MSA_ON_SETUP | 1092 |  | dcsm-EF_MSA_ON.cps | 15
|  | 2020-10-14 22:59 | 2020-10-14 23:00 |  |  | PME_ON | 80 |  | dcsm-EF_PME_ON.cps | 2
|  | 2020-10-14 23:00 | 2020-10-14 23:15 |  |  | PWI_ON_SETUP | 868 |  | dcsm-EF_PWI_ON_CRUISE.cps | 27
|  | 2020-10-14 23:15 | 2020-10-14 23:15 |  |  | MGF_ON_SETUP | 14 |  | dcsm-EF_MGF_ON.cps | 3
|  | 2020-10-14 23:15 | 2020-10-14 23:22 |  |  | MEA_ON_SETUP_SW | 386 | Solar wind mode !! Confirmation needed !! | dcsm-EF_MEA_ON_SW.cps | 21
|  | 2020-10-14 23:22 | 2020-10-14 23:31 | (During WOL#3) |  | ENA_ON_SETUP | 564 |  | dcsm-EF_ENA_power_ON.cps | 7
|  | 2020-10-14 23:31 | 2020-10-14 23:37 | (During WOL#3) |  | MIA_ON_SETUP | 382 |  | dcsm-EF_MIA_ON.cps | 6
|  | 2020-10-14 23:37 | 2020-10-14 23:58 | (During WOL#3) |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL.cps | 34
|  | 2020-10-14 23:28 | 2020-10-14 23:48 | WOL #3 |  | 0 | 1200 |  | #N/A | 0
|  | 2020-10-14 23:58 | 2020-10-15 00:02 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2020-10-15 00:02 | 2020-10-15 00:08 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H.cps | 18
|  | 2020-10-15 00:08 | 2020-10-15 00:12 |  |  | MIA_HV_ON_MAG_RC | 262 | With SAFETY OFF, solar wind mode !! Confirmation needed !! | dcsm-EF_MIA_HV_ON_MAG_RC.cps | 7
|  | 2020-10-15 00:12 | 2020-10-15 00:42 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON.cps | 54
|  | 2020-10-15 00:42 | 2020-10-15 02:24 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps | 232
|  | 2020-10-15 02:24 | 2020-10-15 02:25 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2020-10-15 02:25 | 2020-10-15 09:53 | Observation C |  |  | 26916 | 7.4767 |  | 0
|  | 2020-10-15 09:53 | 2020-10-15 09:54 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-15 09:54 | 2020-10-15 09:57 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2020-10-15 09:57 | 2020-10-15 10:01 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF.cps | 4
|  | 2020-10-15 10:01 | 2020-10-15 10:13 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB.cps | 25
|  | 2020-10-15 10:13 | 2020-10-15 10:14 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF.cps | 1
|  | 2020-10-15 10:14 | 2020-10-15 10:18 |  |  | MEA_HV_OFF | 202 | HV_OFF and SCAN kept ON !! Confirmation needed !! | dcsm-EF_MEA_HV_OFF.cps | 20
|  | 2020-10-15 10:28 | 2020-10-15 10:48 | WOL #4 |  | 2400 | 1200 |  | #N/A | 0
|  | 2020-10-15 10:58 | 2020-10-15 11:02 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START.cps | 6
|  | 2020-10-15 11:02 | 2020-10-15 11:08 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H.cps | 18
|  | 2020-10-15 11:08 | 2020-10-15 11:12 |  |  | MIA_HV_ON_SW_RC | 262 | With SAFETY OFF, solar wind mode !! Confirmation needed !! | dcsm-EF_MIA_HV_ON_SW_RC.cps | 7
|  | 2020-10-15 11:12 | 2020-10-15 11:42 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON.cps | 54
|  | 2020-10-15 11:42 | 2020-10-15 13:24 |  |  | MSA_HV_ON_VFB | 6144 |  | dcsm-EF_MSA_HV_ON_1_VFB.cps,dcsm-EF_MSA_HV_ON_2_VFB.cps | 232
|  | 2020-10-15 13:24 | 2020-10-15 13:25 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 | Mission: 7kbps, without user HK | dcsm-EF_BUS_TLM_MODE_5.cps | 2
|  | 2020-10-15 13:25 | 2020-10-16 03:53 | Observation D |  |  | 52108 | 14.4744 |  | 0
|  | 2020-10-16 03:53 | 2020-10-16 03:54 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 | Mission: 4kbps, with user HK | dcsm-EF_BUS_TLM_MODE_10.cps | 2
|  | 2020-10-16 03:54 | 2020-10-16 03:57 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF.cps | 5
|  | 2020-10-16 03:57 | 2020-10-16 04:00 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF.cps | 4
|  | 2020-10-16 04:00 | 2020-10-16 04:13 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB.cps | 25
|  | 2020-10-16 04:13 | 2020-10-16 04:14 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF.cps | 1
|  | 2020-10-16 04:14 | 2020-10-16 04:18 |  |  | MEA_HV_SCAN_OFF | 210 | HV_OFF and SCAN OFF !! Confirmation needed !! | dcsm-EF_MEA_HV_SCAN_OFF.cps | 24
|  | 2020-10-16 04:28 | 2020-10-16 04:48 | WOL #5 |  | 0 | 1200 |  | #N/A | 0
|  | 2020-10-16 04:18 | 2020-10-16 04:19 |  | SI Power OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP.cps | 4
|  | 2020-10-16 04:19 | 2020-10-16 04:22 |  |  | MIA_OFF | 160 |  | dcsm-EF_MIA_OFF.cps | 4
|  | 2020-10-16 04:22 | 2020-10-16 04:23 |  |  | ENA_OFF | 88 |  | dcsm-EF_ENA_power_OFF.cps | 4
|  | 2020-10-16 04:23 | 2020-10-16 04:26 |  |  | MEA_OFF | 164 |  | dcsm-EF_MEA_OFF.cps | 6
|  | 2020-10-16 04:26 | 2020-10-16 04:26 |  |  | MGF_OFF | 8 |  | dcsm-EF_MGF_OFF.cps | 1
|  | 2020-10-16 04:26 | 2020-10-16 04:27 |  |  | PWI_OFF | 80 |  | dcsm-EF_PWI_OFF.cps | 2
|  | 2020-10-16 04:27 | 2020-10-16 04:28 |  |  | PME_OFF | 40 |  | dcsm-EF_PME_OFF.cps | 1
|  | 2020-10-16 04:28 | 2020-10-16 04:34 |  |  | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF.cps | 25
|  | 2020-10-16 04:34 | 2020-10-16 04:36 |  | MDP OFF | MDP_OFF | 120 |  | dcsm-EF_MDP_POWEROFF.cps | 3
|  | 2020-10-16 04:36 | 2020-10-16 04:40 |  | BUS OFF | BUS_OFF | 220 |  | dcsm-EF_BUS_MONI_OFF.cps | 4
Formulas:
Start = [End]-[Duration (sec)]/3600/24
Start = [End, row above]+10/60/24
End = [Start, row below]
End = [Start]+[Duration (sec)]/3600/24