## 確認事項
NO. | 確認事項 | 回答 | CLOSE

## チェック表 (hidden)
コマンド作成時注意項目
NO. | 項目 | チェック
1 | 観測期間開始時に「dcsm-EF_BUS_MONI_ON」手順が入っていることを確認する。 ただし、前回の観測終了時に「dcsm-EF_BUS_MONI_OFF」を実行していない場合は確認不要。 | □
2 | 観測期間開始日に、観測する機器の”ON”手順が入っていることを確認する。 ただし、PWI、MGF、MAST、WPTを"ON"にする場合は、PWI、MGF、MAST、WPTよりも先にPMEが"ON"となっていること。 ※クルーズ観測中は、MEA1,HEPE,MGFのみ”ON” | □
3 | TLM MODEが観測前に「５」 観測終了後は「１０」 となっていることを確認する | □
4 | 観測時間が”86400”を超えるていないか確認する。 超えていた場合は、main計画作成時に途中ダミーコマンドを挿入すること
5 | WOLの開始時刻が正しいことを確認する | □
6 | WOLの時間を確認 HV OFFになっていることを確認する ↓ クルーズ観測を行っている機器(HEPE、ENA、MIA、MEA、MSAのみ) フライバイを行っている機器(MSA,PWI,MGF,MEA,ENA,MIA,HEPE,MDM) | □
7 | WOL終了時刻＋10以降にのHVがONになっていることを確認する。 クルーズ観測を行っている機器(HEPE、ENA、MIA、MEA、MSAのみ) フライバイを行っている機器(MSA,PWI,MGF,MEA,ENA,MIA,HEPE,MDM) | □
8 | 観測期間最終日に、観測を行った機器の”OFF”手順が入っていることを確認する。 ただし、PWI,MGF,MAST,WPT-OFF手順の後にPME-OFF手順が入っていることを確認する。 | □
9 | MDP_POWEROFFのあとにdcsm-MC_ENA_MDPが入っていることを確認する。 | □
10 | CELのMONI ONは長時間(1h以上の場合は、山下さんと要相談)しないこと BUSにはCELのみのもあるので注意 dcsm-BUS_CEL_MONI_ON dcsm-BUS_CEL_MONI_OFF | □
11 | MEA1の SCAN ON は dcsm-EF_MEA1_ON_SW.cpsに入っているので 順番は MDP ONして dcsm-EF_MEA1_ON_SW.cps dcsm-EF_MEA1_HV_ON.cps dcsm-EF_MEA1_HV_OFF.cps dcsm-EF_MEA1_HV_ON.cps dcsm-EF_MEA1_HV_SCAN_OFF.cps dcsm-EF_MEA1_OFF.cps MDP OFF dcsm-EF_MEA_ON_SW.cps dcsm-EF_MEA_HV_ON.cps dcsm-EF_MEA_HV_OFF.cps dcsm-EF_MEA_HV_ON.cps dcsm-EF_MEA_HV_SCAN_OFF.cps dcsm-EF_MEA_OFF.cps になる SCAN OFFにすると データが出てこない HV OFF->ON時は注意する | □
13 | 2021/6/25以降 dcsm-EF_MSA_ON_C が最新 dcsm-EF_MSA_ONは使用しない | □
14 | 2021/6/25以降 dcsm-CRCO_MIA_CHECK_C が最新 dcsm-CRCO_MIA_CHECKは使用しない（クルーズチェックアウトの時） | □
15 | 2021/6/25以降 dcsm-CRCO_MSA_CHECK_C が最新 dcsm-CRCO_MSA_CHECKは使用しない（クルーズチェックアウトの時） | □
16 | フライバイ時、MIAのHV_ON時間帯によって違うので必ず確認する MIA_HV_ON_RC MIA_HV_ON_SW_RC MIA_HV_ON_MAG_RC | □
17 | Excelの時間を確認する 時間通りになっているか | □

## List
|  | Duration (sec) | source filename | filename |  | cmdcount
BUS ON | BUS_SETUP | 687 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 25
BUS ON | BUS_SETUP_D | 577 | main2-BUS_NECP_HV_MONI_ON_XDOR_001_M60.cps | dcsm-EF_BUS_MONI_ON |  | 20
MDP ON | MDP_SETUP | 509 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 11
| MDP_ON_D | 509 | dcsm-EF_MDP_ON | dcsm-EF_MDP_ON |  | 11
| MDP_CRUISE_SET | 42 | main2-MDP_CRUISE_SET.cps | dcsm-EF_MDP_CRUISE_SET |  | 2
SI Check | PWI_CHECK | 2672 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 56 |  | 180 | 348
| MGF_CHECK | 4179 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 52 |  | 168
| MASTWPT_CHECK | 2108 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 46
| MDM_CHECK | 1252 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 19
| ENA_CHECK | 1134 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 17
| MEA_CHECK | 4620 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 51
| MSA_CHECK | 1102 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 18
| MIA_CHECK | 1562 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 16
| HEP_CHECK | 4936 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART1_XOR_002_M80 |  | 82
| MSASI_CHECK | 6688 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80 |  | 22
MDP OFF | MDP_OFF | 120 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART2_XOR_002_M80 |  | 3
| MDP_OFF_D | 120 | dcsm-EF_MDP_POWEROFF | dcsm-EF_MDP_POWEROFF |  | 3
BUS OFF | BUS_OFF | 220 | main2-CRCO_PART1_XOR_002_M80 | main2-CRCO_PART4_XOR_002_M80 |  | 5
| BUS_OFF_D | 220 | dcsm-EF_BUS_MONI_OFF | dcsm-EF_BUS_MONI_OFF |  | 5
| TCSF_MSASI | 345 | dcsm-tcfs_tbl1_msasi_set.cps | dcsm-tcfs_tbl1_msasi_set |  | 13
SI Power ON | MSA_ON_SETUP | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON |  | 15
| PME_ON | 80 | main2-PME_ON.cps | dcsm-EF_PME_ON |  | 2
| PWI_ON_SETUP | 868 | dcsm-EF_PWI_ON_CRUSE.cps | dcsm-EF_PWI_ON_CRUISE |  | 27 | 520
| MGF_ON_SETUP | 14 | 20200410_Earth-fly-by_MGF_ON_20200221.cps | dcsm-EF_MGF_ON |  | 3
| MEA_ON_SETUP_SW | 386 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA_ON_SW |  | 21
| MEA1_ON_SETUP_SW | 292 | MEA_Earth_Flyby_1_ON_HVOFF.cps, | dcsm-EF_MEA1_ON_SW |  | 12
| MEA_ON_SETUP_MAG | 386 | MEA_Earth_Flyby_4_ON_HVOFF.cps | dcsm-EF_MEA_ON_MAG |  | 21
| ENA_ON_SETUP | 564 | ENA_power_ON.cps | dcsm-EF_ENA_power_ON |  | 7
| MIA_ON_SETUP | 382 | main2-MIA_ON.cps | dcsm-EF_MIA_ON |  | 6
| HEP_ON_SETUP | 1230 | main2-HEP_ON_START_for_TL.cps | dcsm-EF_HEP_ON_START_for_TL |  | 34
| MDM_ON_SETUP | 202 | クルーズ観測手順.txt | dcsm-EF_MDM_ON | 暫定的に600sec入れてある | 6
SI HV ON | MEA_HV_ON | 1756 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA_HV_ON |  | 54
| MEA1_HV_ON | 1702 | MEA_Earth_Flyby_2_ON_HVON.cps, MEA_Earth_Flyby_5_ON_HVON.cps, MEA_Earth_Flyby_7_ON_HVON.cps | dcsm-EF_MEA1_HV_ON |  | 27
| MIA_HV_ON | 240 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON |  | 6
| MIA_HV_ON_MAG | 142 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG |  | 4
| MIA_HV_ON_SW | 102 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW |  | 3
| MIA_HV_ON_RC | 280 | main2-MIA_HV_ON.cps | dcsm-EF_MIA_HV_ON_RC |  | 7
| MIA_HV_ON_MAG_RC | 262 | main2-MIA_HV_ON_MAG.cps | dcsm-EF_MIA_HV_ON_MAG_RC |  | 7
| MIA_HV_ON_SW_RC | 262 | main2-MIA_HV_ON_SW.cps | dcsm-EF_MIA_HV_ON_SW_RC |  | 7
| MSA_HV_ON | 10954 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1,dcsm-EF_MSA_HV_ON_2 |  | 232
| MSA_HV_ON_VFB | 6144 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB,dcsm-EF_MSA_HV_ON_2_VFB |  | 232
| MSA_HV_ON_VFB1 | 2882 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_1_VFB |  | 108
| MSA_HV_ON_VFB2 | 3262 | main2-MSA_HV_ON.cps | dcsm-EF_MSA_HV_ON_2_VFB |  | 124
| ENA_HV_ON | 344 | ENA_HV_ON.cps | dcsm-EF_ENA_HV_ON |  | 18
| ENA_HV_ON_H | 344 | ENA_HV_ON_H.cps | dcsm-EF_ENA_HV_ON_H |  | 18
| HEP_HV_ON | 270 | main2-HEPE_HV_ON_OBS_START.cps | dcsm-EF_HEPE_HV_ON_OBS_START |  | 6
TLM mode change (MODE_5) | TLM_MODE_5 | 42 | main2-BUS_TLM_MODE_5.cps | dcsm-EF_BUS_TLM_MODE_5 |  | 2
TLM mode change (MODE_10) | TLM_MODE_10 | 42 | main2-BUS_TLM_MODE_10.cps | dcsm-EF_BUS_TLM_MODE_10 |  | 2
SI HV OFF | HEP_HV_OFF | 190 | main2-HEPE_HV_OFF_OBS_OFF.cps | dcsm-EF_HEPE_HV_OFF_OBS_OFF |  | 5
| ENA_HV_OFF | 198 | ENA_HV_OFF.cps | dcsm-EF_ENA_HV_OFF |  | 4
| MSA_HV_OFF | 714 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF |  | 24
| MSA_HV_OFF_VFB | 774 | main2-MSA_HV_OFF.cps | dcsm-EF_MSA_HV_OFF_VFB |  | 25
| MIA_HV_OFF | 60 | main2-MIA_HV_OFF.cps | dcsm-EF_MIA_HV_OFF |  | 1
| MEA_HV_SCAN_OFF | 210 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA_HV_SCAN_OFF |  | 24
| MEA1_HV_SCAN_OFF | 186 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdownなし） | dcsm-EF_MEA1_HV_SCAN_OFF |  | 12
| MEA_HV_OFF | 202 | MEA_Earth_Flyby_6_ON_HVOFF.cps | dcsm-EF_MEA_HV_OFF |  | 20
| MEA1_HV_OFF | 182 | dcsm-EF_MEA1_HV_OFF.cps | dcsm-EF_MEA1_HV_OFF |  | 10
SI Power OFF | HEP_OFF | 70 | main2-HEPE_OFF_STOP.cps | dcsm-EF_HEPE_OFF_STOP |  | 4
| MIA_OFF | 160 | main2-MIA_OFF.cps | dcsm-EF_MIA_OFF |  | 4
| ENA_OFF | 88 | ENA_power_OFF.cps | dcsm-EF_ENA_power_OFF |  | 4
| MEA_OFF | 164 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA_OFF |  | 6
| MEA1_OFF | 160 | MEA_Earth_Flyby_3_OFF.cps,MEA_Earth_Flyby_8_OFF.cps(shutdown)のみ | dcsm-EF_MEA1_OFF |  | 4
| MGF_OFF | 8 | 20200410_Earth-fly-by_MGF_OFF_20200221.cps | dcsm-EF_MGF_OFF |  | 1
| PWI_OFF | 80 | main2-PWI_OFF.cps | dcsm-EF_PWI_OFF |  | 2
| PME_OFF | 40 | main2-PME_OFF.cps | dcsm-EF_PME_OFF |  | 1
| MSA_OFF | 380 | main2-MSA_OFF.cps | dcsm-EF_MSA_OFF |  | 25
| MDM_OFF | 160 | クルーズ観測手順.txt | dcsm-EF_MDM_OFF | 暫定的に600sec入れてある | 4
MSA SOFT RESET | MSA_SOFT_RESET2 | 100 | dcsm-EF_MSA_SOFT_RESET2.cps | dcsm-EF_MSA_SOFT_RESET2 |  | 5
MACRO COMMAND ENA | MC_ENA | 246 | main2-MC_ENA_MDP_XDOR_001_M58.cps | dcsm-MC_ENA_MDP |  | 21
| WAIT3600 | 3600
| WAIT3500 | 3500
| MSASI_DARK_1 | 768 | dcsm-MSASI_dark_CO_sequence1.cps | dcsm-MSASI_dark_CO_sequence1 |  | 11 | 19307
| MSASI_DARK_2 | 19498 | dcsm-MSASI_dark_CO_sequence2.cps | dcsm-MSASI_dark_CO_sequence2 |  | 55 | 19307
| MEA2_MEM_DMP | 2550 | dcsm-MEA2_MEM_DMP.cps | dcsm-MEA2_MEM_DMP |  | 36
| WAIT19357 | 19357
| WAIT1800 | 1800 |  | WAIT_SEC 1800
| MDP_ERR_LOG_DUMP | 9080 | main2-MDP_ERR_LOG_DUMP_TL_XDOR_001_M08 | dcsm-MDP_ERR_LOG_DUMP |  | 6
CrouseCheckOut | CRCO_BUS_MONI_ON | 310 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_BUS_MONI_ON
| CRCO_ENA | 1134 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_ENA_CHECK
| CRCO_HEPE | 2206 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPE_CHECK
| CRCO_HEPI | 2730 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_HEPI_CHECK
| CRCO_MASTWPT | 1848 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MASTWPT_CHECK
| CRCO_MDM | 2332 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDM_CHECK
| CRCO_MDP_OFF | 120 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_OFF
| CRCO_MDP_ON | 509 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MDP_ON
| CRCO_MEA | 4620 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MEA_CHECK
| CRCO_MGF | 4019 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MGF_CHECK
| CRCO_MIA | 1562 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MIA_CHECK
| CRCO_MSASI | 6688 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSASI_CHECK
| CRCO_MSA | 1102 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_MSA_CHECK
| CRCO_PME_OFF | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_OFF
| CRCO_PME_ON | 160 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PME_ON
| CRCO_PWI | 2512 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_PWI_CHECK
| CRCO_SI_READY | 377 | main2-CRCO_PART1_XOR_003_M80 | dcsm-CRCO_SI_READY
| MSA_ON_SETUP_C | 1092 | main2-MSA_ON.cps | dcsm-EF_MSA_ON_C |  | 15

## wheel offloading
|  | CA time | 2021-10-01 23:35
Time to CA [h] | ID |  | date time excel | duration(s)
-36 | WOLS |  | 2021-09-30 11:35 | 1200 | WOL#0 | x
| WOLE |  | 2021-09-30 11:55 | 0
-24 | WOLS |  | 2021-09-30 23:35 | 1200 | WOL#1
| WOLE |  | 2021-09-30 23:55 | 0
-12 | WOLS |  | 2021-10-01 11:35 | 1200 | WOL#2
| WOLE |  | 2021-10-01 11:55 | 0
-5.5 | WOLS |  | 2021-10-01 18:05 | 1200 | WOL#3
| WOLE |  | 2021-10-01 18:25 | 0
-1.9166 | WOLS |  | 2021-10-01 21:40 | 1200 | WOL#4
| WOLE |  | 2021-10-01 22:00 | 0
2 | WOLS |  | 2021-10-02 01:35 | 1200 | WOL#5
| WOLE |  | 2021-10-02 01:55 | 0
12 | WOLS |  | 2021-10-02 11:35 | 1200 | WOL#6
| WOLE |  | 2021-10-02 11:55 | 0
24 | WOLS |  | 2021-10-02 23:35 | 1200 | WOL#7
| WOLE |  | 2021-10-02 23:55 | 0
Formulas:
date time excel = D1+[Time to CA [h]]/24
date time excel = [date time excel, row above]+[duration(s), row above]/3600/24

## MercuryFlyby1
START |  | 2021-09-30 09:00 | OBCP START | 2021-09-29 21:00 | [5 empty] | 5days
END |  | 2021-10-02 23:43 | OBCP END | 2021-10-02 23:54 | CMD END | 2021-10-02 23:41
Relative time (h) |  | Absolute time (UTC) | [7 empty] | #N/A
Start | End | Start | End | Event | Activity | Procedure | Duration (sec) |  |  | cmd count | XOR Time | cmd count
|  | 2021-09-30 09:00 | 2021-09-30 09:10 |  | BUS_ON | BUS_SETUP_D | 577 |  | dcsm-EF_BUS_MONI_ON | 20 | 2021-09-30 08:55 | 0000 CALL dcsm-EF_BUS_MONI_ON -Run | dcsm-EF_BUS_MONI_ON
|  | 2021-09-30 09:10 | 2021-09-30 09:18 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON | 11 | 2021-09-30 09:04 | 0000 CALL dcsm-EF_MDP_ON -Run | dcsm-EF_MDP_ON
|  | 2021-09-30 09:18 | 2021-09-30 09:19 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-09-30 09:13 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-09-30 09:19 | 2021-09-30 09:37 |  | MSA ON | MSA_ON_SETUP_C | 1092 |  | dcsm-EF_MSA_ON_C | 15 | 2021-09-30 09:14 | 0000 CALL dcsm-EF_MSA_ON_C -Run | dcsm-EF_MSA_ON_C
|  | 2021-09-30 09:37 | 2021-09-30 10:37 |  | WAIT_3600 | WAIT3600 | 3600 |  | 0 | 0 | 2021-09-30 09:32 | 0000 WAIT_SEC 3600 | 3600 | x
|  | 2021-09-30 10:37 | 2021-09-30 10:43 |  | MSA OFF | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF | 25 | 2021-09-30 10:32 | 0000 CALL dcsm-EF_MSA_OFF -Run | dcsm-EF_MSA_OFF
|  | 2021-09-30 10:43 | 2021-09-30 10:45 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF | 3 | 2021-09-30 10:38 | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | dcsm-EF_MDP_POWEROFF
|  | 2021-09-30 10:45 | 2021-09-30 10:54 |  | MDP ON | MDP_ON_D | 509 |  | dcsm-EF_MDP_ON | 11 | 2021-09-30 10:40 | 0000 CALL dcsm-EF_MDP_ON -Run | dcsm-EF_MDP_ON
|  | 2021-09-30 10:54 | 2021-09-30 11:12 |  | MSA ON | MSA_ON_SETUP_C | 1092 |  | dcsm-EF_MSA_ON_C | 15 | 2021-09-30 10:49 | 0000 CALL dcsm-EF_MSA_ON_C -Run | dcsm-EF_MSA_ON_C
|  | 2021-09-30 11:12 | 2021-09-30 11:13 |  | MDP CRUSE SET | MDP_CRUISE_SET | 42 |  | dcsm-EF_MDP_CRUISE_SET | 2 | 2021-09-30 11:07 | 0000 CALL dcsm-EF_MDP_CRUISE_SET -Run | dcsm-EF_MDP_CRUISE_SET
|  | 2021-09-30 11:13 | 2021-09-30 22:33 | WAIT |  |  | 40793 | 11.3314 | #N/A | #N/A | 2021-09-30 11:07 | 0000 WAIT_SEC 40793 | 41291 | #N/A |  | #N/A
|  | 2021-09-30 22:33 | 2021-09-30 22:34 |  | SI Power ON | PME_ON | 80 |  | dcsm-EF_PME_ON | 2 | 2021-09-30 22:27 | 0000 CALL dcsm-EF_PME_ON -Run | dcsm-EF_PME_ON
|  | 2021-09-30 22:34 | 2021-09-30 22:48 |  |  | PWI_ON_SETUP | 868 |  | dcsm-EF_PWI_ON_CRUISE | 27 | 2021-09-30 22:29 | 0000 CALL dcsm-EF_PWI_ON_CRUISE -Run | dcsm-EF_PWI_ON_CRUISE
|  | 2021-09-30 22:48 | 2021-09-30 22:49 |  |  | MGF_ON_SETUP | 14 |  | dcsm-EF_MGF_ON | 3 | 2021-09-30 22:43 | 0000 CALL dcsm-EF_MGF_ON -Run | dcsm-EF_MGF_ON
|  | 2021-09-30 22:49 | 2021-09-30 22:55 |  |  | MEA_ON_SETUP_SW | 386 |  | dcsm-EF_MEA_ON_SW | 21 | 2021-09-30 22:43 | 0000 CALL dcsm-EF_MEA_ON_SW -Run | dcsm-EF_MEA_ON_SW
|  | 2021-09-30 22:55 | 2021-09-30 23:04 |  |  | ENA_ON_SETUP | 564 |  | dcsm-EF_ENA_power_ON | 7 | 2021-09-30 22:50 | 0000 CALL dcsm-EF_ENA_power_ON -Run | dcsm-EF_ENA_power_ON
|  | 2021-09-30 23:04 | 2021-09-30 23:11 |  |  | MIA_ON_SETUP | 382 |  | dcsm-EF_MIA_ON | 6 | 2021-09-30 22:59 | 0000 CALL dcsm-EF_MIA_ON -Run | dcsm-EF_MIA_ON
|  | 2021-09-30 23:11 | 2021-09-30 23:31 |  |  | HEP_ON_SETUP | 1230 |  | dcsm-EF_HEP_ON_START_for_TL | 34 | 2021-09-30 23:06 | 0000 CALL dcsm-EF_HEP_ON_START_for_TL -Run | dcsm-EF_HEP_ON_START_for_TL
|  | 2021-09-30 23:31 | 2021-09-30 23:35 |  |  | MDM_ON_SETUP | 202 |  | dcsm-EF_MDM_ON | 6 | 2021-09-30 23:26 | 0000 CALL dcsm-EF_MDM_ON -Run | dcsm-EF_MDM_ON
|  | 2021-09-30 23:35 | 2021-09-30 23:55 | WOL#1 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-09-30 23:29 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-01 00:05 | 2021-10-01 00:09 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-09-30 23:59 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-01 00:09 | 2021-10-01 00:15 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-01 00:04 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-01 00:15 | 2021-10-01 00:20 |  |  | MIA_HV_ON_RC | 280 | Safety ON | dcsm-EF_MIA_HV_ON_RC | 7 | 2021-10-01 00:10 | 0000 CALL dcsm-EF_MIA_HV_ON_RC -Run | dcsm-EF_MIA_HV_ON_RC
|  | 2021-10-01 00:20 | 2021-10-01 00:49 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-01 00:14 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-01 00:49 | 2021-10-01 01:37 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-01 00:44 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-01 01:37 | 2021-10-01 02:31 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-01 01:32 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-01 02:31 | 2021-10-01 02:32 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-01 02:26 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5
|  | 2021-10-01 02:32 | 2021-10-01 11:10 | Observation A |  |  | 31098 | 8.6383 | #N/A | #N/A | 2021-10-01 02:27 | 0000 WAIT_SEC 31098 | 31098 | #N/A |  | #N/A
|  | 2021-10-01 11:10 | 2021-10-01 11:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-01 11:05 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-01 11:11 | 2021-10-01 11:14 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-01 11:06 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-01 11:14 | 2021-10-01 11:17 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-01 11:09 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-01 11:17 | 2021-10-01 11:30 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-01 11:12 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB
|  | 2021-10-01 11:30 | 2021-10-01 11:31 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-01 11:25 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-01 11:31 | 2021-10-01 11:35 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 | 2021-10-01 11:26 | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | dcsm-EF_MEA_HV_OFF
|  | 2021-10-01 11:35 | 2021-10-01 11:55 | WOL#2 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-10-01 11:29 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-01 12:05 | 2021-10-01 12:09 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-10-01 11:59 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-01 12:09 | 2021-10-01 12:15 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-01 12:04 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-01 12:15 | 2021-10-01 12:19 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 | 2021-10-01 12:10 | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | dcsm-EF_MIA_HV_ON_SW_RC
|  | 2021-10-01 12:19 | 2021-10-01 12:49 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-01 12:14 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-01 12:49 | 2021-10-01 13:37 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-01 12:43 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-01 13:37 | 2021-10-01 14:31 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-01 13:31 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-01 14:31 | 2021-10-01 14:32 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-01 14:26 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5
|  | 2021-10-01 14:32 | 2021-10-01 17:40 | Observation B |  |  | 11316 | 3.1433 | #N/A | #N/A | 2021-10-01 14:26 | 0000 WAIT_SEC 11316 | 11316 | #N/A |  | #N/A
|  | 2021-10-01 17:40 | 2021-10-01 17:41 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-01 17:35 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-01 17:41 | 2021-10-01 17:44 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-01 17:36 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-01 17:44 | 2021-10-01 17:47 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-01 17:39 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-01 17:47 | 2021-10-01 18:00 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-01 17:42 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB
|  | 2021-10-01 18:00 | 2021-10-01 18:01 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-01 17:55 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-01 18:01 | 2021-10-01 18:05 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 | 2021-10-01 17:56 | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | dcsm-EF_MEA_HV_OFF
|  | 2021-10-01 18:05 | 2021-10-01 18:25 | WOL#3 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-10-01 17:59 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-01 18:35 | 2021-10-01 18:39 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-10-01 18:29 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-01 18:39 | 2021-10-01 18:45 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-01 18:34 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-01 18:45 | 2021-10-01 18:49 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 | 2021-10-01 18:40 | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | dcsm-EF_MIA_HV_ON_SW_RC
|  | 2021-10-01 18:49 | 2021-10-01 19:19 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-01 18:44 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-01 19:19 | 2021-10-01 20:07 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-01 19:13 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-01 20:07 | 2021-10-01 21:01 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-01 20:01 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-01 21:01 | 2021-10-01 21:02 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-01 20:56 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5
|  | 2021-10-01 21:02 | 2021-10-01 21:15 | Observation C |  |  | 816 | 0.22667 | #N/A | #N/A | 2021-10-01 20:56 | 0000 WAIT_SEC 816 | 816 | #N/A |  | #N/A
|  | 2021-10-01 21:15 | 2021-10-01 21:16 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-01 21:10 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-01 21:16 | 2021-10-01 21:19 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-01 21:11 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-01 21:19 | 2021-10-01 21:22 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-01 21:14 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-01 21:22 | 2021-10-01 21:35 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-01 21:17 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB
|  | 2021-10-01 21:35 | 2021-10-01 21:36 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-01 21:30 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-01 21:36 | 2021-10-01 21:40 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 | 2021-10-01 21:31 | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | dcsm-EF_MEA_HV_OFF
|  | 2021-10-01 21:40 | 2021-10-01 22:00 | WOL#4 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-10-01 21:34 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-01 22:10 | 2021-10-01 22:14 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-10-01 22:04 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-01 22:14 | 2021-10-01 22:20 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-01 22:09 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-01 22:20 | 2021-10-01 22:24 |  |  | MIA_HV_ON_MAG_RC | 262 | Safety OFF 磁気圏モード | dcsm-EF_MIA_HV_ON_MAG_RC | 7 | 2021-10-01 22:15 | 0000 CALL dcsm-EF_MIA_HV_ON_MAG_RC -Run | dcsm-EF_MIA_HV_ON_MAG_RC
|  | 2021-10-01 22:24 | 2021-10-01 22:54 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-01 22:19 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-01 22:54 | 2021-10-01 23:42 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-01 22:48 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-01 23:42 | 2021-10-02 00:36 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-01 23:36 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-02 00:36 | 2021-10-02 00:37 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-02 00:31 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5
|  | 2021-10-02 00:37 | 2021-10-02 01:10 | Observation D |  |  | 2016 | 0.56 | #N/A | #N/A | 2021-10-02 00:31 | 0000 WAIT_SEC 2016 | 2016 | #N/A |  | #N/A
|  | 2021-10-02 01:10 | 2021-10-02 01:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-02 01:05 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-02 01:11 | 2021-10-02 01:14 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-02 01:06 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-02 01:14 | 2021-10-02 01:17 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-02 01:09 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-02 01:17 | 2021-10-02 01:30 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-02 01:12 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB
|  | 2021-10-02 01:30 | 2021-10-02 01:31 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-02 01:25 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-02 01:31 | 2021-10-02 01:35 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 | 2021-10-02 01:26 | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | dcsm-EF_MEA_HV_OFF
|  | 2021-10-02 01:35 | 2021-10-02 01:55 | WOL#5 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-10-02 01:29 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-02 02:05 | 2021-10-02 02:09 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-10-02 01:59 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-02 02:09 | 2021-10-02 02:15 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-02 02:04 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-02 02:15 | 2021-10-02 02:19 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 | 2021-10-02 02:10 | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | dcsm-EF_MIA_HV_ON_SW_RC
|  | 2021-10-02 02:19 | 2021-10-02 02:49 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-02 02:14 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-02 02:49 | 2021-10-02 03:37 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-02 02:43 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-02 03:37 | 2021-10-02 04:31 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-02 03:31 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-02 04:31 | 2021-10-02 04:32 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-02 04:26 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5
|  | 2021-10-02 04:32 | 2021-10-02 11:10 | Observation E |  |  | 23916 | 6.6433 | #N/A | #N/A | 2021-10-02 04:26 | 0000 WAIT_SEC 23916 | 23916 | #N/A |  | #N/A
|  | 2021-10-02 11:10 | 2021-10-02 11:11 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-02 11:05 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-02 11:11 | 2021-10-02 11:14 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-02 11:06 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-02 11:14 | 2021-10-02 11:17 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-02 11:09 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-02 11:17 | 2021-10-02 11:30 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-02 11:12 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB |  | 17513
|  | 2021-10-02 11:30 | 2021-10-02 11:31 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-02 11:25 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-02 11:31 | 2021-10-02 11:35 |  |  | MEA_HV_OFF | 202 |  | dcsm-EF_MEA_HV_OFF | 20 | 2021-10-02 11:26 | 0000 CALL dcsm-EF_MEA_HV_OFF -Run | dcsm-EF_MEA_HV_OFF
|  | 2021-10-02 11:35 | 2021-10-02 11:55 | WOL#6 |  | 1800 | 1200 |  | #N/A | #N/A | 2021-10-02 11:29 | 0000 WAIT_SEC 1800 | 1200 | #N/A |  | #N/A
|  | 2021-10-02 12:05 | 2021-10-02 12:09 |  | SI HV ON | HEP_HV_ON | 270 |  | dcsm-EF_HEPE_HV_ON_OBS_START | 6 | 2021-10-02 11:59 | 0000 CALL dcsm-EF_HEPE_HV_ON_OBS_START -Run | dcsm-EF_HEPE_HV_ON_OBS_START
|  | 2021-10-02 12:09 | 2021-10-02 12:15 |  |  | ENA_HV_ON_H | 344 |  | dcsm-EF_ENA_HV_ON_H | 18 | 2021-10-02 12:04 | 0000 CALL dcsm-EF_ENA_HV_ON_H -Run | dcsm-EF_ENA_HV_ON_H
|  | 2021-10-02 12:15 | 2021-10-02 12:19 |  |  | MIA_HV_ON_SW_RC | 262 | Safety OFF 太陽風モード | dcsm-EF_MIA_HV_ON_SW_RC | 7 | 2021-10-02 12:10 | 0000 CALL dcsm-EF_MIA_HV_ON_SW_RC -Run | dcsm-EF_MIA_HV_ON_SW_RC
|  | 2021-10-02 12:19 | 2021-10-02 12:49 |  |  | MEA_HV_ON | 1756 |  | dcsm-EF_MEA_HV_ON | 54 | 2021-10-02 12:14 | 0000 CALL dcsm-EF_MEA_HV_ON -Run | dcsm-EF_MEA_HV_ON
|  | 2021-10-02 12:49 | 2021-10-02 13:37 |  |  | MSA_HV_ON_VFB1 | 2882 |  | dcsm-EF_MSA_HV_ON_1_VFB | 108 | 2021-10-02 12:43 | 0000 CALL dcsm-EF_MSA_HV_ON_1_VFB -Run | dcsm-EF_MSA_HV_ON_1_VFB
|  | 2021-10-02 13:37 | 2021-10-02 14:31 |  |  | MSA_HV_ON_VFB2 | 3262 |  | dcsm-EF_MSA_HV_ON_2_VFB | 124 | 2021-10-02 13:31 | 0000 CALL dcsm-EF_MSA_HV_ON_2_VFB -Run | dcsm-EF_MSA_HV_ON_2_VFB
|  | 2021-10-02 14:31 | 2021-10-02 14:32 |  | TLM mode change (MODE_5) | TLM_MODE_5 | 42 |  | dcsm-EF_BUS_TLM_MODE_5 | 2 | 2021-10-02 14:26 | 0000 CALL dcsm-EF_BUS_TLM_MODE_5 -Run | dcsm-EF_BUS_TLM_MODE_5 |  |  | x
|  | 2021-10-02 14:32 | 2021-10-02 22:50 | Observation F |  |  | 29870 | 8.2972 | #N/A | #N/A | 2021-10-02 14:26 | 0000 WAIT_SEC 29870 | 29372 | #N/A
|  | 2021-10-02 22:50 | 2021-10-02 22:50 |  | TLM mode change (MODE_10) | TLM_MODE_10 | 42 |  | dcsm-EF_BUS_TLM_MODE_10 | 2 | 2021-10-02 22:44 | 0000 CALL dcsm-EF_BUS_TLM_MODE_10 -Run | dcsm-EF_BUS_TLM_MODE_10
|  | 2021-10-02 22:50 | 2021-10-02 22:53 |  | SI HV OFF | HEP_HV_OFF | 190 |  | dcsm-EF_HEPE_HV_OFF_OBS_OFF | 5 | 2021-10-02 22:45 | 0000 CALL dcsm-EF_HEPE_HV_OFF_OBS_OFF -Run | dcsm-EF_HEPE_HV_OFF_OBS_OFF
|  | 2021-10-02 22:53 | 2021-10-02 22:57 |  |  | ENA_HV_OFF | 198 |  | dcsm-EF_ENA_HV_OFF | 4 | 2021-10-02 22:48 | 0000 CALL dcsm-EF_ENA_HV_OFF -Run | dcsm-EF_ENA_HV_OFF
|  | 2021-10-02 22:57 | 2021-10-02 23:10 |  |  | MSA_HV_OFF_VFB | 774 |  | dcsm-EF_MSA_HV_OFF_VFB | 25 | 2021-10-02 22:51 | 0000 CALL dcsm-EF_MSA_HV_OFF_VFB -Run | dcsm-EF_MSA_HV_OFF_VFB
|  | 2021-10-02 23:10 | 2021-10-02 23:11 |  |  | MIA_HV_OFF | 60 |  | dcsm-EF_MIA_HV_OFF | 1 | 2021-10-02 23:04 | 0000 CALL dcsm-EF_MIA_HV_OFF -Run | dcsm-EF_MIA_HV_OFF
|  | 2021-10-02 23:11 | 2021-10-02 23:14 |  |  | MEA_HV_SCAN_OFF | 210 |  | dcsm-EF_MEA_HV_SCAN_OFF | 24 | 2021-10-02 23:05 | 0000 CALL dcsm-EF_MEA_HV_SCAN_OFF -Run | dcsm-EF_MEA_HV_SCAN_OFF
|  | 2021-10-02 23:14 | 2021-10-02 23:15 |  | SI Power OFF | HEP_OFF | 70 |  | dcsm-EF_HEPE_OFF_STOP | 4 | 2021-10-02 23:09 | 0000 CALL dcsm-EF_HEPE_OFF_STOP -Run | dcsm-EF_HEPE_OFF_STOP
|  | 2021-10-02 23:15 | 2021-10-02 23:18 |  |  | MIA_OFF | 160 |  | dcsm-EF_MIA_OFF | 4 | 2021-10-02 23:10 | 0000 CALL dcsm-EF_MIA_OFF -Run | dcsm-EF_MIA_OFF
|  | 2021-10-02 23:18 | 2021-10-02 23:19 |  |  | ENA_OFF | 88 |  | dcsm-EF_ENA_power_OFF | 4 | 2021-10-02 23:13 | 0000 CALL dcsm-EF_ENA_power_OFF -Run | dcsm-EF_ENA_power_OFF
|  | 2021-10-02 23:19 | 2021-10-02 23:22 |  |  | MEA_OFF | 164 |  | dcsm-EF_MEA_OFF | 6 | 2021-10-02 23:14 | 0000 CALL dcsm-EF_MEA_OFF -Run | dcsm-EF_MEA_OFF
|  | 2021-10-02 23:22 | 2021-10-02 23:22 |  |  | MGF_OFF | 8 |  | dcsm-EF_MGF_OFF | 1 | 2021-10-02 23:17 | 0000 CALL dcsm-EF_MGF_OFF -Run | dcsm-EF_MGF_OFF
|  | 2021-10-02 23:22 | 2021-10-02 23:24 |  |  | PWI_OFF | 80 |  | dcsm-EF_PWI_OFF | 2 | 2021-10-02 23:17 | 0000 CALL dcsm-EF_PWI_OFF -Run | dcsm-EF_PWI_OFF
|  | 2021-10-02 23:24 | 2021-10-02 23:24 |  |  | PME_OFF | 40 |  | dcsm-EF_PME_OFF | 1 | 2021-10-02 23:18 | 0000 CALL dcsm-EF_PME_OFF -Run | dcsm-EF_PME_OFF
|  | 2021-10-02 23:24 | 2021-10-02 23:31 |  |  | MSA_OFF | 380 |  | dcsm-EF_MSA_OFF | 25 | 2021-10-02 23:19 | 0000 CALL dcsm-EF_MSA_OFF -Run | dcsm-EF_MSA_OFF
|  | 2021-10-02 23:31 | 2021-10-02 23:33 |  |  | MDM_OFF | 160 |  | dcsm-EF_MDM_OFF | 4 | 2021-10-02 23:25 | 0000 CALL dcsm-EF_MDM_OFF -Run | dcsm-EF_MDM_OFF
|  | 2021-10-02 23:33 | 2021-10-02 23:35 |  | MDP OFF | MDP_OFF_D | 120 |  | dcsm-EF_MDP_POWEROFF | 3 | 2021-10-02 23:28 | 0000 CALL dcsm-EF_MDP_POWEROFF -Run | dcsm-EF_MDP_POWEROFF
|  | 2021-10-02 23:35 | 2021-10-02 23:39 |  | MACRO ENA | MC_ENA | 246 |  | dcsm-MC_ENA_MDP | 21 | 2021-10-02 23:30 | 0000 CALL dcsm-MC_ENA_MDP -Run | dcsm-MC_ENA_MDP
|  | 2021-10-02 23:39 | 2021-10-02 23:43 |  | BUS OFF | BUS_OFF_D | 220 |  | dcsm-EF_BUS_MONI_OFF | 5 | 2021-10-02 23:34 | 0000 CALL dcsm-EF_BUS_MONI_OFF -Run | dcsm-EF_BUS_MONI_OFF
|  | 2021-10-02 23:43 | 2021-10-03 00:03 |  | main_end | END | 1200 |  |  | #N/A | 2021-10-02 23:36
Formulas:
End = [Start]+[Duration (sec)]/3600/24
End = [Start, row below]
XOR Time = [Start]-317/3600/24
Start = [End, row above]
Start = [End]-[Duration (sec)]/3600/24