## TIMELINE
Date | [5 empty] | Geometrical info |  |  |  |  | Ground Station |  |  |  | Bitrate |  |  |  | Activities during pass | [19 empty] | Activities outside pass | [6 empty] | Parallel PL ops |  |  |  |  | Data Volume | [6 empty] | FD coordinator on-call
Date | [MJD2000] | Week day | DOY | Mission Day | NECP day | ¦r¦ in [AU] | ¦r_e¦ in [AU] | SESC [deg] | SSCE [deg] | OWLT [sec] | G/S | AOS10 [hh:mm:ss] | LOS10 [hh:mm:ss] | Dump Duration [h] | X LGA | X MGA | X HGA | BR [kbps] | Unit | Start Time (italic = MTL) | ID / Activity | Duration [h] | Science DV [Gbit] | EM | CS | AD | SM | EB | ALAL | TC | Project on-site | Industry support in DCR | Industry support on site (PISA) or on-call | Product deadline | TC uplink | Attitude profile | Antenna | FD | Unit | Start Time | ID / Activity | Duration [h] | Science DV [Gbit] | Attitude profile | FD | MAG | ISA | MGNS | SIXS | MIXS | VC0 [Gbit] | VC1 [Gbit] | Pass DV [Gbit] | Dump DV [Gbit] | II ops DV [Gbit] | Science ops DV [Gbit] | SUM Science DV [Gbit]
2018-10-22 | 6053.518 | Mon | 295 | 3 | 0 | 0.99038 | 0.0053537 | 8.031 | 171.925 | 2.6715 | MLG | 10:48 | 21:27 | 9.6478 |  |  |  |  | CPS PHE | e | LEOP handover S12 MTM CPS B-side commiss. S49 Enable VC0 routing of PL HK P28 PHE Launch Lock removal S40 Update of gyro-solar estimator innovation threshold | 3.00 0.10 1.00 0.10 |  |  | S | S |  |  |  |  | CPS: D. Stramaccioni or P. Fernando DMS: J. Windsor AOCS: None | Team leader: TS/RE AOCS: AP CPS: RB PHE: UH | JP, BW, KK, FB, AG | FD_MTL_02 | FD_MTL_01: S13 MTM Transverse Test Manoeuvre S05 STR APS background checks FD attitude, SA, WOL (until S02) MTL_01: Stop dumps until DOY 301 | Specific | MGA | X | CPS | AOS10-3.25h | S13 MTM Transverse Test Manoeuvre (WOL and large slew before pass) | 3.25 |  | Specific | X | [5 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0 | 0
2018-10-23 | 6054.518 | Tue | 296 | 4 | 1 | 0.98838 | 0.0074306 | 8.607 | 171.329 | 3.7079 | MLG | 10:45 | 21:25 | 9.6569 | 2.039 | 348.1204 | 348.1204 | 348.1204 | CPS | AOS10 AOS10+1h AOS10+1h30 AOS10+2h AOS10+9h | 2h of AOS activities and Acc. Bias calibr. S46 STR power, TEC current check S52 MGA/HGA cold start RAM settings S13 MTM Transverse Test Manoeuvre - start of firing phase Start of slew after test [Process and uplink FD_MTL_02 and MTL_02] LGA-X commanding test and change of preferred LGA in SGM to LGA-X (SY-FCP-024) | 2.00 0.50 0.30 6.50 1.50 |  | R | S | R | R | R | S | R | CPS: D. Stramaccioni or P. Fernando DMS: J. Windsor AOCS: M. Casasco or P. Espeillac | Team leader: SF/AH AOCS: PE CPS: PF | FS, CH, JS RC, MF, (UH) |  | FD_MTL_02: S02 IMU gyro commissioning S51 Update of Earth Ephemerides in RAM FD attitude, SA, WOL MTL_02: S02 IMU gyro commissioning (swap to FCE IMU) | Specific | MGA | X | CPS AOCS | LOS10 LOS10+2h | S13 MTM Transverse Test Manoeuvre - slew after test S05 STR APS background checks | 1.00 0.30 |  | Specific (Slew) y-Sun&XGA | X | [5 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0 | 0
2018-10-24 | 6055.518 | Wed | 297 | 5 | 2 | 0.98656 | 0.009496 | 9.266 | 170.645 | 4.7386 | MLG | 10:42 | 21:19 | 9.6117 | 2.039 | 348.1204 | 348.1204 | 348.1204 | Power DMS MAG | AOS10+1h AOS10+2h AOS10+3h AOS10+8h LOS10-7h19m | S30 MTM power commissioning S31 MPO power commissioning S01 DMS commissioning P11 MAG before deployment S02 IMU gyro commissioning (swap to FCE IMU) | 1.00 1.00 3.00 1.00 7.40 | 0.01 | S | R | R | R | S | R | S | System/Power: K. Geelen DMS: J. Windsor AOCS: M. Casasco or P. Espeillac | Team leader: TS/RE for activity duration PWR: KK, US DMS: JP, RE AOCS: AP, FB MAG: UH | BW, KK, US, JP, RE, AP, FB, UH, AG, RB | FD_MTL_03 |  | y-Sun&XGA | MGA |  | AOCS MAG | LOS10+1h LOS10 | S02 FCE IMU gyro commissioning P11 MAG before deployment | 12.25 (14.00) | 0.01 | Specific | X | [5 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0 | 0
2018-10-25 | 6056.518 | Thu | 298 | 6 | 3 | 0.98492 | 0.011558 | 9.978 | 169.905 | 5.7677 | MLG | 10:38 | 21:19 | 9.6692 | 2.039 | 348.1204 | 348.1204 | 348.1204 | MAG BERM | AOS10+1h AOS10+1h AOS10+3h AOS10+6h AOS10+7h AOS1+7h30 LOS10-2h | P12 MAG during deployment S07 MAG boom deployment P13 MAG after deployment S35 BERM commissioning CAM#2 operations AC-FCP-416 and 421 (LEOP timeline step 40.4) S51 Update of Earth Ephemerides in RAM Configure MPOMAG in background science mode Uplink FD_MTL_03 | (2.00) 2.00 3.00 1.00 0.50 1.00 0.50 | 0.01 0.09 0.01 | S | R | S | D | R | P (FD_MTL_03 processing) | S | System/CAM (for MAG): K. Geelen DMS: J. Windsor AOCS: M. Casasco or P. Espeillac P/L: L. d'Arcio | Team leader: SF MEC: CH PHE: UH | UP, TS on-call |  | MTL_03: S07 MAG boom deployment | y-Sun&XGA | MGA |  | MAG | LOS10 | P13 MAG after deployment | (14.00) | 0.01 | y-Sun&XGA |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-10-26 | 6057.518 | Fri | 299 | 7 | 4 | 0.98063 | 0.013622 | 10.729 | 169.123 | 6.7975 | MLG | 10:35 | 21:12 | 9.6172 | 2.039 | 348.1204 | 348.1204 | 348.1204 | MAG TTC | AOS10 AOS10+1h | P13 MAG after deployment S27 TTC Commissioning part 1 Prepare and uplink CAM#1 imaging of SA repositioning on DOY300 | (5.00) 9.00 | 0.01 | S | R | P | P | S | R | S | System/CAM (for MAG): K. Geelen TT&C: P. Pablos or R. Heinze DMS: J. Windsor P/L: L. d'Arcio | Team leader: SF TTC: RC PHE: UH | RH: on-call | FD_MTL_04 | FD_MTL_03: S06 SA Flexible Modes Characterisation FD attitude, SA, WOL | y-Sun&XGA | LGA+X/ MGA/ HGA |  | AOCS | LOS10+1h | S02 IMU gyro commissioning MTM SA repositioning | 8 |  | Specific | X | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-10-27 | 6058.518 | Sat | 300 | 8 | 5 | 0.97806 | 0.01569 | 11.508 | 168.309 | 7.8295 | CEB | 6:40 | 16:24 | 8.7272 | 2.039 | 348.1204 | 348.1204 | 348.1204 | AOCS SEPS | AOS10+1h AOS10+1h AOS10+4h | S06 SA flexible modes charact. S15 TPPRE HPR Heater check Repeat CPS-B thruster commissioning Check MTM SA repositioning and process CAM images [Process FD_MTL_04 and MTL_04, update corresponding pass sheets] | 6.66 0.25 3.00 |  | S | R | R | R | R | S | R | System/CAM: K. Geelen TT&C: P. Pablos or R. Heinze | Team leader: SF AOCS: PE MEPS: FS MEC: CH? | PE on-call? |  |  | y-Sun&XGA | HGA | X | [5 empty] | y-Sun&XGA |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0.02 | 0.03 | Frank Budnik
2018-10-28 | 6059.518 | Sun | 301 | 9 | 6 | 0.97573 | 0.017765 | 12.308 | 167.47 | 8.8648 | MLG | 10:27 | 21:08 | 9.6822 | 2.039 | 348.1204 | 348.1204 | 348.1204 | TTC | AOS10+1h | S27 TTC Commissioning part 2 | 9 |  | S | R | R | R | S | R | R | SA: J. Aroca | Team leader: SF TTC: RC | RH: on-call |  | FD_MTL_04: S09 MTM SA Drive Run-in S19 HPRS and feed system initialisation FD attitude, SA, WOL | y-Sun&XGA | LGA+X/ MGA/ HGA | [6 empty] | y-Sun&XGA |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 8.26 | 8.27 | Frank Budnik
2018-10-29 | 6060.518 | Mon | 302 | 10 | 7 | 0.97365 | 0.019848 | 13.123 | 166.612 | 9.9042 | MLG | 10:24 | 21:05 | 9.6875 | 2.039 | 348.1204 | 348.1204 | 348.1204 | AOCS SEPS | AOS10+1h AOS10+4h AOS10+4.1h AOS10+4.2h | S09 MTM SA Drive Run In S38 Set SASM SA Guidance flag Adjust MEPS HK rates S16 TPA release | 3.00 0.10 0.10 4.00 |  | S | D | L | S |  | D |  | SA: J. Aroca DMS: J. Windsor | Team leader: SF MEPS: FS MEC: CH, AG? AOCS: PE |  |  |  | y-Sun&XGA | HGA | X | AOCS | LOS | MGA switch off / stop of APMM | 0.1 |  | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 5.65 | 5.66
2018-10-30 | 6061.518 | Tue | 303 | 11 | 8 | 0.97182 | 0.02194 | 13.95 | 165.739 | 10.9484 | MLG | 10:20 | 21:01 | 9.6917 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S17 PPU relay setting and TPM movement checks+V12 | 7 |  | R | S | D | S |  |  |  | DMS: J. Windsor | Team leader: TS MEPS: FS MEC: CH |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 12.5 | 12.51
2018-10-31 | 6062.518 | Wed | 304 | 12 | 9 | 0.97024 | 0.024044 | 14.785 | 164.853 | 11.9979 | MLG | 10:16 | 20:58 | 9.6967 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S18 Check of FCU relays | 8 |  | R | S | D | S |  |  |  | DMS: J. Windsor | Team leader: TS MEPS: FS |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 3 | 3.01
2018-11-01 | 6063.518 | Thu | 305 | 13 | 10 | 0.96783 | 0.026159 | 15.626 | 163.957 | 13.0533 | MLG | 10:12 | 20:54 | 9.7019 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S19 HPRS and feed system init - venting [Target EEOP] | 7 |  | R | S | D | S |  |  |  |  | Team leader: TS MEPS: FS |  | FD_MTL_05 |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-02 | 6064.518 | Fri | 306 | 14 | 11 | 0.9644 | 0.028286 | 16.471 | 163.053 | 14.1149 | MLG | 10:08 | 20:47 | 9.6475 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S19 HPRS and feed system init - venting [Target EEOP] | 7.00 |  | D | S | P |  | P | S | P |  | Team leader: TS MEPS: FS |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-03 | 6065.518 | Sat | 307 | 15 | 12 | 0.96128 | 0.030427 | 17.319 | 162.142 | 15.1833 | CEB | 6:15 | 15:58 | 8.7125 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S19 HPRS and feed system init - purging | 8 |  | R | S | R | S | R | R | R |  | Team leader: TS MEPS: FS |  |  | FD_MTL_05: S41 Focal Length Calibration S42 STR APS Calibration S47 SGM Guidance Update MTM SA Drive Run-in FD attitude, SA, WOL | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01 | Michael Mueller
2018-11-04 | 6066.518 | Sun | 308 | 16 | 13 | 0.95847 | 0.032582 | 18.169 | 161.226 | 16.2587 | MLG | 10:01 | 20:44 | 9.7183 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MAG AOCS Thermal | AOS10+1.5h AOS10+5h AOS10+5h | S21 Cold outgassing MTM SA Drive Run-in (revised) P14 MAG Functional Test S42 STR APS calibration, if needed S33 Thermal Commissioning | (10.00) 4.00 3.50 3.00 |  | S | R | R | R | S | R | S | AOCS: M. Casasco or P. Espeillac P/L: L. d'Arcio | Team leader: TS MEPS: FS TCS: JS | PE/AP? |  | MTL_05: P14 MAG Functional Test | Flip-A | HGA |  | MAG SEPS | LOS10+2h LOS | P14 MAG Functional Test S21 Cold outgassing | 2.00 (14.00) |  | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01 | Michael Mueller
2018-11-05 | 6067.518 | Mon | 309 | 17 | 14 | 0.95598 | 0.034753 | 19.019 | 160.304 | 17.3418 | MLG | 9:57 | 20:41 | 9.7244 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS Power | AOS10+1h AOS10+5h AOS10+8h | S20 Magnet and Heater relay check S32 MPO Battery SoC Adjust MMO thermal settings [Target EEOP] | 4.00 3.00 0.50 |  | S | R | D | S | S |  |  | System: K. Geelen SA: J. Aroca | Team leader: TS MEPS/PWR: FS TCS: JS |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-06 | 6068.518 | Tue | 310 | 18 | 15 | 0.9538 | 0.036939 | 19.87 | 159.378 | 18.4328 | MLG | 9:53 | 20:34 | 9.6725 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MMO | AOS AOS10+1h AOS10+1h | Change MMO PS priority to 7 S20 Magnet and Heater relay check 1h extra margin for MMO data loss MMO to Cruise standby mode M51 HK mode change M01 PCS commissioning M02 ACS commissioning M03 DMC commissioning | 0.10 4.00 1.00 0.10 0.10 1.50 4.20 1.00 |  | S | R | S |  |  | S |  | System: K. Geelen | Team leader: SF MMO: UH AOCS: PE or AP? |  |  |  | Flip-A | HGA |  | AOCS | LOS10 | S41 STR focal length calibration | 9.4 |  | Specific | X | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-07 | 6069.518 | Wed | 311 | 19 | 16 | 0.95193 | 0.039143 | 20.72 | 158.449 | 19.5324 | MLG | 9:50 | 20:34 | 9.7372 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MMO | AOS10+1h AOS10+1h | S22 Cathode and Neutraliser Outgassing config 1h extra margin for MMO data loss M52 Preparation for MMO mission commissioning M08 MDP commissioning (1-2) | 3.00 (6.00) 1.00 1.00 3.20 | 0.25 | S | D | S | S |  |  |  | MMO: C. Scharmberg | Team leader: SF MMO: UH | BW, JS? |  | MTL_06: M04 TCS commissioning | y-Sun&XGA | HGA |  | MMO SEPS | LOS10 LOS10+2h | S22 Cathode and Neutraliser Outgassing M04 TCS commissioning | (14.00) 0.80 | 0.42 | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-08 | 6070.518 | Thu | 312 | 20 | 17 | 0.95039 | 0.041364 | 21.569 | 157.516 | 20.6411 | MLG | 9:46 | 20:30 | 9.7442 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MMO | AOS10+1h AOS10+1h | S22 Cathode and Neutraliser Outgassing 1h extra margin for MMO data loss M08 MDP commissioning (3-4) | 2.00 (7.00) 1.00 5.13 | 0.25 | S | D | S | S |  |  |  | MMO: C. Scharmberg | Team leader: SF MEPS: FS MMO: UH |  |  |  | Flip-A | HGA |  | MMO SEPS | LOS10 | S22 Cathode and Neutraliser Outgassing | (14.00) | 0.42 | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | 0 | 0.01
2018-11-09 | 6071.518 | Fri | 313 | 21 | 18 | 0.94917 | 0.043605 | 22.416 | 156.581 | 21.7594 | MLG | 9:42 | 20:27 | 9.7517 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS AOCS MMO | AOS10+1h AOS10+1h AOS10+1h | S22 Cathode and Neutraliser Outgassing S47 SGM Guidance Update 1h extra margin for MMO data loss M08 MDP commissioning (5-6) M54 MDP ON M12 MGF commissioning M11 PWI commissioning (1-2) | 2.00 (7.00) 1.00 1.00 1.66 0.50 1.30 0.83 | 0.25 | S | D | S |  |  | S |  | MMO: C. Scharmberg | MEPS: FS MMO: UH |  |  | MTL_07: M11 PWI commissioning | Flip-A | HGA |  | MMO SEPS | LOS10 LOS10+2h | S22 Cathode and Neutraliser Outgassing M11 PWI commissioning | (14.00) 2.00 | 0.42 | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | #REF! | #REF!
2018-11-10 | 6072.518 | Sat | 314 | 22 | 19 | 0.94828 | 0.045867 | 23.261 | 155.645 | 22.8877 | CEB | 5:51 | 15:31 | 8.6647 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MMO | AOS10+1h AOS10+1h | S22 Cathode and Neutraliser Outgassing 1h extra margin for MMO data loss M11 PWI commissioning (3-5) M09 MAST latch release (MWE comissioning) | 2.00 (7.00) 1.00 3.66 3.00 | 0.25 | R | S | S | R | R | S | R | MMO: C. Scharmberg | MEPS: FS MMO: UH |  |  | MTL_08: M12 MGF commissioning | Flip-A | HGA |  | MMO SEPS | LOS10 LOS10+2h | S22 Cathode and Neutraliser Outgassing M12 MGF commissioning | (14.00) 2.70 | 0.42 | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | #REF! | #REF! | Vicente Companys
2018-11-11 | 6073.518 | Sun | 315 | 23 | 20 | 0.9477 | 0.048149 | 24.102 | 154.708 | 24.0268 | MLG | 9:35 | 20:21 | 9.7669 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MMO | AOS10+1h AOS10+1h | S22 Cathode and Neutraliser Outgassing 1h extra margin for MMO data loss M09 MAST latch release M10 PWI WPT-S latch release Switch off MPO-MAG at end of MMO commissioning | 2.00 (7.00) 1.00 3.00 4.00 | 0.25 | R | S | S | R | R | S | R | MMO: C. Scharmberg | MEPS: FS MMO: UH |  |  | MTL_09: M55 MDP off MMO to dormant mode Adjust MMO thermal settings | Flip-A | HGA |  | MMO SEPS | LOS10 LOS10+2h LOS10+3h | S22 Cathode and Neutraliser Outgassing M55 MDP off MMO to dormant mode Adjust MMO thermal settings | (14.00) 0.30 0.10 0.50 | 0.42 | Flip-B |  | 0.01 |  |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.01 | #REF! | #REF! | Vicente Companys
2018-11-12 | 6074.518 | Mon | 316 | 24 | 21 | 0.9444 | 0.050454 | 24.939 | 153.77 | 25.1769 | MLG | 9:31 | 20:17 | 9.7753 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS AOS10+1h | Change MMO PS priority to 8 S45 SEPT Cathode Heater Cycles | 0.10 7.00 |  | D | S | R | S |  |  |  | P/L: F. Giannini | MEPS: FS |  |  |  | Flip-A | HGA | [6 empty] | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-13 | 6075.518 | Tue | 317 | 25 | 22 | 0.94142 | 0.052783 | 25.772 | 152.833 | 26.3388 | MLG | 9:27 | 20:14 | 9.7839 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MRT | AOS10 AOS10+1h AOS10+8h | Change MERTIS PS priority to 7+ Adjust MERTIS thermal settings S45 SEPT Cathode Heater Cycles P16 MERTIS Functional test: switch-on and warm-up | 0.50 7.00 1.00 |  | D | S | R | S |  |  | S | P/L: F. Giannini | PL: UH |  |  |  | Flip-A | HGA |  | MRT | LOS10 | P16 MERTIS Functional test: warm-up | (14.00) |  | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-14 | 6076.518 | Wed | 318 | 26 | 23 | 0.93878 | 0.055135 | 26.599 | 151.897 | 27.5128 | MLG | 9:23 | 20:11 | 9.7925 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MRT | AOS10+1h AOS10+7h AOS10+2h | P16 MERTIS Functional test Adjust MERTIS thermal settings S45 SEPT Cathode Heater Cycles | 6.00 0.50 7.00 |  | D | S | D |  |  | S | S | P/L: F. Giannini | PL: UH |  | FD_MTL_06 |  | Flip-A | HGA | [6 empty] | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-15 | 6077.518 | Thu | 319 | 27 | 24 | 0.93647 | 0.057513 | 27.42 | 150.963 | 28.6994 | CEB | 5:36 | 15:13 | 8.6169 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS MGNS | AOS AOS10+1h AOS10+2h AOS10+2h | Change MERTIS PS priority to 8 Change MGNS PS priority to 7 P17 MGNS Full Checkout P17 MGNS Science Acquisition S45 SEPT Cathode Heater Cycles | 0.10 1.00 (8.00) 7.00 |  | P | S | P | P |  | S |  | MEPS: O. Sutherland P/L: C. Scharmberg | PL: UH |  |  | FD_MTL_06: S23 High Power Discharge S24 Single Thruster Firings S25 Dual Thruster Firings S04 STR Alignment Calibration STR Focal Length Update FD attitude, SA, WOL | Flip-A | HGA | [6 empty] | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-16 | 6078.518 | Fri | 320 | 28 | 25 | 0.93449 | 0.059917 | 28.235 | 150.031 | 29.8989 | MLG | 9:16 | 20:05 | 9.8117 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS AOS10+1h AOS10+6h | Change MGNS PS priority to 8 S23 High power discharges operation FD update slot: STR focal length calibration FCT update slot: APS calibration EEPROM update | 0.10 5.00 0.50 |  | S | R | D | S |  |  |  | MEPS: O. Sutherland | Team leader: SF,TS MEPS: FS AOCS: PE |  |  |  | Flip-A | HGA | [6 empty] | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0 | 0
2018-11-17 | 6079.518 | Sat | 321 | 29 | 26 | 0.93286 | 0.062348 | 29.042 | 149.102 | 31.1118 | MLG | 9:12 | 20:02 | 9.8219 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S23 High power discharges operation | 5 |  | S | R | R | S | R | R | R | MEPS: O. Sutherland | Team leader: SF,TS MEPS: FS AOCS: PE |  |  |  | Flip-A | HGA | [6 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0 | 0 | Mathias Lauer
2018-11-18 | 6080.518 | Sun | 322 | 30 | 27 | 0.93156 | 0.064806 | 29.842 | 148.177 | 32.3384 | MLG | 9:09 | 19:59 | 9.8325 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S24 Single thruster firings S34 Thermal Characterisation | 9.00 (9.00) |  | S | R | R | S | R | R | R | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  |  |  | Specific | HGA | X | [5 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 8 | 8 | Mathias Lauer
2018-11-19 | 6081.518 | Mon | 323 | 31 | 28 | 0.9306 | 0.067292 | 30.634 | 147.256 | 33.579 | MLG | 9:05 | 19:56 | 9.8431 | 2.039 | 348.1204 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S24 Single thruster firings | 9 |  | S | R | D |  |  | S |  | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  |  |  | Specific | HGA | X | [5 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-20 | 6082.518 | Tue | 324 | 32 | 29 | 0.92999 | 0.069806 | 31.416 | 146.339 | 34.8338 | MLG | 9:02 | 19:53 | 9.8547 | 2.039 | 261.0903 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S24 Single thruster firings | 9 |  | R | S | D |  |  | S |  | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  |  |  | Specific | HGA | X | [5 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0.06 | 0.06
2018-11-21 | 6083.518 | Wed | 325 | 33 | 30 | 0.92972 | 0.07235 | 32.19 | 145.428 | 36.103 | MLG | 8:58 | 19:50 | 9.8661 | 2.039 | 261.0903 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S24 Single thruster firings | 9 |  | R | S | D |  |  | S |  | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  |  |  | Specific | HGA | X | [5 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-22 | 6084.518 | Thu | 326 | 34 | 31 | 0.92662 | 0.074923 | 32.954 | 144.523 | 37.3868 | MLG | 8:55 | 19:47 | 9.8783 | 2.039 | 261.0903 | 348.1204 | 348.1204 | SEPS | AOS10+1h | S25 Dual thruster firings | 9 |  | S | D | D | S |  |  |  | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  | FD_MTL_07 |  | Specific | HGA | X | [5 empty] | y-Sun | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-23 | 6085.518 | Fri | 327 | 35 | 32 | 0.92386 | 0.077525 | 33.708 | 143.623 | 38.6852 | MLG | 8:51 | 19:45 | 9.8908 | 2.039 | 261.0903 | 348.1204 | 348.1204 | SEPS | AOS10+1h AOS10+8h AOS10+8.5h | S25 Dual thruster firings Adjust MMO thermal settings Adjust MEPS HK rates | 9.00 0.50 0.10 |  | S | P | P | S |  | P |  | MEPS: O. Sutherland AOCS: M. Casasco or P. Espeillac | Team leader: SF,TS MEPS: FS AOCS: PE TCS: JS |  |  |  | y-Sun&XGA | HGA | X X | AOCS | LOS10 | S04 STR alignment calibration (incl. slews and WOL) | 13 |  | Specific | X | [5 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-11-24 | 6086.518 | Sat | 328 | 36 | 33 | 0.92146 | 0.080156 | 34.452 | 142.73 | 39.9981 | MLG | 8:48 | 19:42 | 9.9039 | 2.039 | 208.8722 | 348.1204 | 348.1204 | MMO | AOS AOS10+1h | Change MMO PS priority to 7 1h extra margin for MMO data loss MMO to Cruise STB mode M53 Preparation for mission comm. M54 MDP ON M15 MPPE MEA1 com. (LV) M16 MPPE MEA2 com. (LV) M18 MPPE MSA com. (LV) M14 MSASI commissioning (LV) | 0.10 1.00 0.10 1.00 0.50 1.60 1.60 1.30 2.00 | 0.25 | R | S | S | R | R | R | R | MMO: C. Scharmberg | MEPS: FS PL: UH |  |  | FD_MTL_07: IMU Gyro Calibration updates FD attitude, SA, WOL MTL_10: M14 MSASI commissioning (LV) | y-Sun&XGA | HGA |  | MMO | LOS10+2h | M14 MSASI commissioning (LV) | 7.9 | 0.42 | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | 0.08 | 0.08 | Frank Budnik
2018-11-25 | 6087.518 | Sun | 329 | 37 | 34 | 0.9194 | 0.082816 | 35.185 | 141.843 | 41.3256 | MLG | 8:44 | 19:39 | 9.9175 | 2.039 | 208.8722 | 348.1204 | 348.1204 | MMO | AOS10+1h AOS10+8h | 1h extra margin for MMO data loss M17 MPPE MIA com.(LV) M19 MPPE ENA com. (LV) M20 MPPE HEP com. (LV) M13 MDM commissioning Adjust BELA thermal settings | 1.00 2.30 1.70 3.00 1.00 0.50 | 0.25 | R | S | S | R | R | R | R | MMO: C. Scharmberg | MEPS: FS PL: UH |  |  | MTL_11: M13 MDM commissioning M55 MDP off MMO to dormant mode Adjust MMO thermal settings Adjust ISA thermal settings P50 BELA EEPROM update TC file | Flip-A | HGA |  | MMO ISA BELA | LOS10+2h LOS10+6h LOS10+6.3h LOS10+6.5h LOS10+7h | M13 MDM commissioning M55 MDP off MMO to dormant mode Adjust MMO thermal settings Adjust ISA thermal settings | 3.80 0.30 0.10 0.50 0.50 | 0.42 | Flip-B | [6 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF! | Frank Budnik
2018-11-26 | 6088.518 | Mon | 330 | 38 | 35 | 0.91636 | 0.085505 | 35.908 | 140.964 | 42.6675 | MLG | 8:41 | 19:37 | 9.9314 | 2.039 | 208.8722 | 348.1204 | 348.1204 | BELA | AOS AOS10+1h AOS10+1h AOS10+4h AOS10+6h AOS10+8h | Change BELA PS priority to 7 Change MMO PS priority to 8 FD update slot: IMU com. RAM P01 BELA functional test P02 BELA test redundant side P50 BELA EEPROM update Adjust BELA thermal settings | 0.10 0.10 2.50 2.50 4.00 0.10 |  | C | R | S |  |  |  |  | P/L: F. Giannini | MEPS: FS PL: UH |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 |  | 0.29 |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.3 | #REF! | #REF!
2018-11-27 | 6089.518 | Tue | 331 | 39 | 36 | 0.91538 | 0.088222 | 36.62 | 140.091 | 44.0234 | MLG | 8:38 | 19:34 | 9.9456 | 2.039 | 208.8722 | 348.1204 | 348.1204 | ISA | AOS AOS10+1h | Change BELA PS priority to 8 P03 ISA Health Check | 0.10 9.00 | 0.046 | C | R | R |  | S |  |  | P/L: F. Giannini | MEPS: FS PL: UH |  |  |  | Flip-A | HGA |  | ISA | LOS10 | P03 ISA Health Check: Thermalisation | (14.00) | 0.08 | Flip-B |  | 0.01 |  | 0.29 |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.3 | #REF! | #REF!
2018-11-28 | 6090.518 | Wed | 332 | 40 | 37 | 0.91476 | 0.090968 | 37.322 | 139.226 | 45.3933 | MLG | 8:34 | 19:32 | 9.9603 | 2.039 | 174.0602 | 348.1204 | 348.1204 | MIXS ISA | AOS10+1h AOS10+2h AOS10+4h | P19 MIXS/SIXS DPU Checkout P20 MIXS-T functional checkout P03 ISA Health Check | 1.00 2.00 (3.00) 6.00 | 0.03 0.03 | C | R | R |  | S | s |  | P/L: F. Giannini, L. d'Arcio | MEPS: FS PL: UH |  |  |  | Flip-A | HGA |  | MIXS | LOS10+2h | P20 MIXS-T functional checkout | (14.00) |  | Flip-B |  | 0.01 | 0.13 | 0.29 |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.43 | #REF! | #REF!
2018-11-29 | 6091.518 | Thu | 333 | 41 | 38 | 0.91449 | 0.09374 | 38.013 | 138.367 | 46.7768 | MLG | 8:31 | 19:30 | 9.9753 | 2.039 | 174.0602 | 348.1204 | 348.1204 | MIXS | AOS10+1h AOS10+4h AOS10+7h | P20 MIXS-T functional checkout P21 MIXS-C Functional checkout S48 LGA beacon test | 3.00 2.00 (3.00) 2.00 | 0.26 | S |  |  |  |  | S |  | P/L: L. d'Arcio | MEPS: FS PL: UH |  | FD_MTL_08 |  | Flip-A | HGA |  | MIXS | LOS10 | P21 MIXS-C Functional checkout | (14.00) | 0.38 | Flip-B |  | 0.01 | 0.13 | 0.29 |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.43 | 2 | 2.43
2018-11-30 | 6092.518 | Fri | 334 | 42 | 39 | 0.91459 | 0.096539 | 38.694 | 137.516 | 48.1736 | MLG | 8:28 | 19:27 | 9.9906 | 2.039 | 174.0602 | 348.1204 | 348.1204 | MIXS | AOS10+1h AOS10+4h AOS10+8h | P21 MIXS-C Functional checkout P22 MIXS Detector checkout Adjust SIXS thermal settings | 3.00 1.00 (5.00) 0.50 | 0.26 | C |  | P |  |  | S | P | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  | MTL_12: P22 MIXS Detector checkout | Flip-A | HGA |  | MIXS | LOS10 | P22 MIXS Detector checkout | 7.00 | 0.12 | Flip-B |  | 0.01 | 0.13 | 0.29 |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.43 | #REF! | #REF!
2018-12-01 | 6093.518 | Sat | 335 | 43 | 40 | 0.91177 | 0.099365 | 39.364 | 136.671 | 49.5835 | MLG | 8:24 | 19:25 | 10.0061 | 2.039 | 174.0602 | 348.1204 | 348.1204 | MIXS SRN | AOS10+1h AOS10+2h AOS10+3h AOS10+4h AOS10+7h | P23 MIXS-C Voltage optimisation P23 MIXS-T Voltage optimisation P33 DPU initial switch-on P40 SRN STROFIO LV checkout P40 STROFIO Macro load/check [Target EEOP] | 1.00 1.00 1.00 3.00 2.00 | 0.06 0.01 | S | R | R | R | S | s | R | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  | FD_MTL_08: P07 ISA Large Movement P06 ISA Small Movement, Part 1 S44 STR FOTO Mode FD attitude, SA, WOL MTL_13: P04 ISA self calibration 1 P40 SRN STROFIO HV checkout | Flip-A | HGA |  | ISA SRN | LOS10+2h LOS10+4h | P04 ISA self calibration 1 P40 SRN STROFIO HV checkout | 2.00 1.00 | 0.01 | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | 3 | 4.2 | Michael Mueller
2018-12-02 | 6094.518 | Sun | 336 | 44 | 41 | 0.90931 | 0.10222 | 40.025 | 135.833 | 51.0063 | MLG | 8:21 | 19:23 | 10.0222 | 2.039 | 174.0602 | 348.1204 | 348.1204 | SIXS MIXS SRN | AOS10+1h AOS10+5h AOS10+6h AOS10+7h AOS10+1h AOS10+3h | P46 SIXS Functional Checkout P19 MIXS/SIXS DPU B-side test P23 MIXS-C Voltage optimisation P23 MIXS-T Voltage optimisation P40 SRN STROFIO MCP comm. P40 SRN STROFIO Cathode 2B conversion | 4.00 1.00 1.00 1.00 2.00 6.50 | 1.20 XXX | S | R | R | R | S | S | R | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  | MTL_14: P47 SIXS Threshold Scan P40 SRN STROFIO Cathode 2B activation Activate ISA thermal control system P05 ISA self calibration 2 ISA chain calibration | Flip-A | HGA |  | SRN | LOS10+2h AOS10-1h | P47 SIXS Threshold Scan P40 SRN STROFIO Cathode 2B activation | 3.00 1.00 | 0.00 XXX | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF! | Michael Mueller
2018-12-03 | 6095.518 | Mon | 337 | 45 | 42 | 0.90721 | 0.10509 | 40.676 | 135.001 | 52.4416 | MLG | 8:18 | 19:20 | 10.0383 | 2.039 | 174.0602 | 348.1204 | 348.1204 | SRN | AOS10 AOS10+1h AOS10+4h | P40 SRN STROFIO Cathode 2B activation P35 SRN ELENA HV ramp (reduced) P34 SRN ELENA General Check (reduced) | (8.00) 3.00 6.00 | 1.20 XXX | R | C |  |  | S |  |  | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  | MTL_15: P40 STROFIO Science Verification | Flip-A | HGA |  | SRN ISA | LOS10+2h LOS10+4h | P40 STROFIO Science Verification Activate ISA thermal control system | 2.00 0.50 | 0.00 XXX | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-04 | 6096.518 | Tue | 338 | 46 | 43 | 0.90549 | 0.10799 | 41.317 | 134.175 | 53.8893 | MLG | 8:15 | 19:18 | 10.0556 | 2.039 | 174.0602 | 348.1204 | 348.1204 | SRN | AOS10+1h AOS10+1h AOS10+3h AOS10+5h | FD update slot: IMU com. SGM P36 SRN PICAM LV checkout P37 SRN PICAM HV checkout P39 SRN MIPA Checkout | 0.10 2.00 2.00 2.00 | 0 | R | C |  |  | S |  |  | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  |  | Flip-A | HGA |  | ISA | LOS10+1h LOS10+3h | P05 ISA self calibration 2 P07 ISA HGA large movement test | 2.00 6.90 | 0 | y-Sun&XGA | X | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-05 | 6097.518 | Wed | 339 | 47 | 44 | 0.90414 | 0.11092 | 41.95 | 133.356 | 55.3492 | MLG | 8:12 | 19:16 | 10.0719 | 2.039 | 130.5451 | 348.1204 | 348.1204 | SRN | AOS10+1h AOS10+8h | P33 SRN DPU initial test - limited test Adjust SIMBIO thermal settings | 9.00 0.50 | 0 |  | C |  |  | S |  |  | P/L: L. d'Arcio | MEPS: FS PL: UH |  |  |  | y-Sun&XGA | HGA |  | ISA | LOS10+2h LOS10+2h | P06 ISA HGA small movement test, part 1 incl. ISA chain calibration | 5.50 0.50 | 0.03 | Flip-B | X | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | 0 | 1.2
2018-12-06 | 6098.518 | Thu | 340 | 48 | 45 | 0.90316 | 0.11387 | 42.573 | 132.542 | 56.8211 | MLG | 8:09 | 19:14 | 10.0894 | 2.039 | 130.5451 | 348.1204 | 348.1204 | SIM | AOS AOS10+1h | Change SIMBIO PS priority to 7 P45 ME functional checkout P42 HRIC commissioning main P43 STC Commissioning main P44 VIHI Commissioning main | 0.10 0.50 2.30 2.30 2.30 | 0.00 0.66 0.25 0.25 |  | C |  | S |  |  |  | P/L: F. Giannini | MEPS: FS PL: UH |  |  | MTL_16: P42 HRIC commissioning - performance test | Flip-A | HGA |  | SIM | LOS10+2h | P42 HRIC commissioning - performance test | 4 | 0.00 7.10 | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | 9.14 | 10.34
2018-12-07 | 6099.518 | Fri | 341 | 49 | 46 | 0.90255 | 0.11684 | 43.188 | 131.735 | 58.3049 | MLG | 8:06 | 19:12 | 10.1069 | 2.039 | 130.5451 | 348.1204 | 348.1204 | SIM PHE | AOS AOS10+1h AOS10+3h | Change PHE PS priority to 7 P42 HRIC commissioning red P43 STC Commissioning red P44 VIHI Commissioning red P29 PHE functional checkout P30 PHE EUV lock release | 0.10 '0.60 1.00 0.60 2.25 0.40 | 1.00 0.31 0.25 0.25 4.84 |  | C | S | S |  |  |  | P/L: F. Giannini, E. Rouvier | MEPS: FS PL: UH |  |  | MTL_17: P43 STC Commissioning - performance test | Flip-A | HGA |  |  | LOS10+2h | P43 STC Commissioning - performance test | 9 |  | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | 6.37 | 7.57
2018-12-08 | 6100.518 | Sat | 342 | 50 | 47 | 0.90232 | 0.11984 | 43.794 | 130.933 | 59.8003 | MLG | 8:03 | 19:10 | 10.1244 | 2.039 | 130.5451 | 348.1204 | 348.1204 | SIM MIXS | AOS AOS10+1h AOS10+2h AOS10+3h AOS10+5h | PHE PS priority to 8 P23 MIXS-C Voltage optimisation P23 MIXS-T Voltage optimisation P45 SIMBIO Performance tests - max stress/max DR P45 SIMBIO Performance tests- orb simulation P44 VIHI Commissioning - Performance tests | 0.10 1.00 1.00 2.00 1.50 1.30 | 2.50 10.00 | R | S | R | S | R | S | R | P/L: F. Giannini | MEPS: FS PL: UH |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | 16 | 17.2 | Mathias Lauer
2018-12-09 | 6101.518 | Sun | 343 | 51 | 48 | 0.90247 | 0.12286 | 44.391 | 130.137 | 61.3072 | MLG | 8:00 | 19:08 | 10.1425 | 2.039 | 130.5451 | 348.1204 | 348.1204 | SIM KAT | AOS AOS10+1h AOS10+2h | Change SIMBIO PS priority to 8 Adjust SIMBIO thermal settings P27 KAT commissioning | 0.10 8.00 | 3 | R | S | R | S | R | R | R | P/L: F. Giannini | MEPS: FS PL: UH |  |  |  | Flip-A | HGA | [6 empty] | Flip-B |  |  | 0.13 |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.13 | 1.41 | 1.54 | Mathias Lauer
2018-12-10 | 6102.518 | Mon | 344 | 52 | 49 | 0.90299 | 0.1259 | 44.979 | 129.347 | 62.8254 | MLG | 7:57 | 19:07 | 10.1606 | 2.039 | 130.5451 | 348.1204 | 348.1204 | KAT | AOS10+1h | P27 KAT commissioning | 8 | 0 | C | R |  | S |  |  |  | P/L: F. Giannini | MEPS: FS PL: UH |  | FD_MTL_09 | MTL_18: P08 ISA Performance Test: KAT S43 STR Defective Pixel Mapping S39 MPO Solar Array Nudging | Flip-A | HGA |  | ISA | LOS10+2h | P08 ISA Performance Test: KAT | 10 | 0 | Flip-B |  |  | 0.13 |  |  |  | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0.13 | #REF! | #REF!
2018-12-11 | 6103.518 | Tue | 345 | 53 | 50 | 0.90052 | 0.12897 | 45.559 | 128.563 | 64.3548 | MLG | 7:54 | 19:05 | 10.1794 | 2.039 | 104.4361 | 348.1204 | 348.1204 | AOCS | AOS10+1h AOS10+5h | S43 STR Defective Pixel Mapping S44 STR FOTO mode, TW, shutter [Target EEOP] | 4.00 3.00 |  | C | R | P |  | P | S |  |  | Team leader: TS,SF AOCS: PE/AP? |  |  |  | Flip-A | HGA | X | ISA | LOS10+2h | P08 ISA Performance Test: KAT | 10 |  | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-12 | 6104.518 | Wed | 346 | 54 | 51 | 0.89842 | 0.13205 | 46.131 | 127.784 | 65.8951 | MLG | 7:51 | 19:03 | 10.1978 | 2.039 | 104.4361 | 348.1204 | 348.1204 | AOCS SIM | AOS10+1h AOS10+5h | S39 MPO Solar Array Nudging SIMBIO-SYS back-up slot [Target EEOP] | 3.40 4.00 |  | C |  |  | S |  | S |  | SA: J. Aroca | Team leader: TS,SF MEC: CH, AG? AOCS: PE/AP? |  |  | FD_MTL_09: P06 ISA Small Movement, Part 2 FD update slot: STR Alignment calibration in RAM and EEPROM FD attitude, SA, WOL MTL_19: P09 ISA Performance Test - Thermal Characterisation | Flip-A | HGA |  | ISA | LOS10+2h LOS10+2h | P06 ISA HGA small movement test, part 2 incl. ISA chain calibration | 4.75 0.50 | XXX | Flip-B | X | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-13 | 6105.518 | Thu | 347 | 55 | 52 | 0.89671 | 0.13516 | 46.695 | 127.011 | 67.446 | MLG | 7:48 | 19:01 | 10.2167 | 2.039 | 104.4361 | 348.1204 | 348.1204 | ISA | AOS10+1h AOS10+2h | P09 ISA Performance Test - Thermal Characterisation FD update slot: STR Alignment calibration RAM | 9.00 0.10 | 0.4 | C |  |  |  | S |  |  | P/L: F. Giannini | PL: UH |  |  |  | Flip-A | HGA |  | ISA | LOS10 | P09 ISA Performance Test - Thermal Characterisation | 14.00 | 0 | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-14 | 6106.518 | Fri | 348 | 56 | 53 | 0.89538 | 0.13829 | 47.25 | 126.245 | 69.0073 | MLG | 7:45 | 19:00 | 10.2361 | 2.039 | 104.4361 | 348.1204 | 348.1204 | ISA | AOS10+1h AOS10+2h | P09 ISA Performance Test - Thermal Characterisation FD update slot: STR Alignment calibration EEPROM | 9.00 0.10 | 0.4 | C |  |  |  | S |  |  | P/L: F. Giannini | PL: UH |  |  | MTL_20: Adjust ISA thermal settings Adjust SIXS thermal settings S50 Disable VC0 routing of PL HK | Flip-A | HGA |  | ISA | LOS10 LOS10+8h LOS10+8.5h LOS10+9h | P09 ISA Performance Test - Thermal Characterisation Adjust ISA thermal settings Adjust SIXS thermal settings S50 Disable VC0 routing of PL HK | 7.00 0.10 0.10 0.10 | 0 | Flip-B |  | 0.01 | 0.13 | 0.29 | 0.05 | 0.72 | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 1.2 | #REF! | #REF!
2018-12-15 | 6107.518 | Sat | 349 | 57 | 54 | 0.89443 | 0.14144 | 47.796 | 125.484 | 70.5787 | MLG | 7:43 | 18:58 | 10.255 | 2.039 | 87.0301 | 348.1204 | 348.1204 |  |  | Start of Thrust Arc 1 | [10 empty] | Team leader: TS,SF MEPS: FS, KK AOCS: PE, AP? | [8 empty] | Start of Thrust Arc 1 | [9 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF! | Vicente Companys
2018-12-16 | 6108.518 | Sun | 350 | 58 | 55 | 0.89387 | 0.14461 | 48.335 | 124.729 | 72.1605 | MLG | 7:40 | 18:56 | 10.2742 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF! | Vicente Companys
2018-12-17 | 6109.518 | Mon | 351 | 59 | 56 | 0.89369 | 0.1478 | 48.866 | 123.979 | 73.7527 | MLG | 7:37 | 18:55 | 10.2939 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-18 | 6110.518 | Tue | 352 | 60 | 57 | 0.8939 | 0.15101 | 49.389 | 123.236 | 75.3549 | MLG | 7:34 | 18:53 | 10.3133 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-19 | 6111.518 | Wed | 353 | 61 | 58 | 0.8945 | 0.15424 | 49.904 | 122.498 | 76.9667 | MLG | 7:32 | 18:52 | 10.3331 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-20 | 6112.518 | Thu | 354 | 62 | 59 | 0.89548 | 0.15749 | 50.411 | 121.766 | 78.5875 | MLG | 7:29 | 18:50 | 10.3531 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-21 | 6113.518 | Fri | 355 | 63 | 60 | 0.89342 | 0.16075 | 50.91 | 121.041 | 80.2169 | CEB | 4:21 | 13:14 | 7.8789 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-22 | 6114.518 | Sat | 356 | 64 | 61 | 0.89175 | 0.16403 | 51.402 | 120.322 | 81.8543 | MLG | 7:24 | 18:47 | 10.3931 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF! | Frank Budnik
2018-12-23 | 6115.518 | Sun | 357 | 65 | 62 | 0.89046 | 0.16733 | 51.886 | 119.608 | 83.499 | MLG | 7:21 | 18:46 | 10.4133 | 2.039 | 87.0301 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-24 | 6116.518 | Mon | 358 | 66 | 63 | 0.88907 | 0.17064 | 52.362 | 118.902 | 85.1504 | MLG | 7:19 | 18:45 | 10.4336 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-25 | 6117.518 | Tue | 359 | 67 | 64 | 0.88896 | 0.17396 | 52.831 | 118.201 | 86.8076 | MLG | 7:16 | 18:43 | 10.4539 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-26 | 6118.518 | Wed | 360 | 68 | 65 | 0.88924 | 0.17729 | 53.292 | 117.507 | 88.4699 | MLG | 7:14 | 18:42 | 10.475 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-27 | 6119.518 | Thu | 361 | 69 | 66 | 0.88992 | 0.18063 | 53.746 | 116.819 | 90.1365 | MLG | 7:11 | 18:41 | 10.495 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-28 | 6120.518 | Fri | 362 | 70 | 67 | 0.89098 | 0.18398 | 54.194 | 116.137 | 91.8066 | MLG | 7:09 | 18:40 | 10.5158 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-29 | 6121.518 | Sat | 363 | 71 | 68 | 0.89244 | 0.18733 | 54.634 | 115.462 | 93.4795 | MLG | 7:07 | 18:39 | 10.5367 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-30 | 6122.518 | Sun | 364 | 72 | 69 | 0.89084 | 0.19069 | 55.069 | 114.792 | 95.1544 | MLG | 7:04 | 18:38 | 10.5569 | 2.039 | 65.2726 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2018-12-31 | 6123.518 | Mon | 365 | 73 | 70 | 0.88962 | 0.19405 | 55.497 | 114.127 | 96.8305 | MLG | 7:02 | 18:37 | 10.5783 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2019-01-01 | 6124.518 | Tue | 1 | 74 | 71 | 0.8888 | 0.19741 | 55.919 | 113.469 | 98.5073 | MLG | 7:00 | 18:36 | 10.5986 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2019-01-02 | 6125.518 | Wed | 2 | 75 | 72 | 0.88838 | 0.20077 | 56.336 | 112.816 | 100.1842 | MLG | 6:57 | 18:35 | 10.6194 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2019-01-03 | 6126.518 | Thu | 3 | 76 | 73 | 0.88834 | 0.20413 | 56.748 | 112.168 | 101.8604 | MLG | 6:55 | 18:34 | 10.64 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2019-01-04 | 6127.518 | Fri | 4 | 77 | 74 | 0.8887 | 0.20748 | 57.154 | 111.526 | 103.5354 | MLG | 6:53 | 18:33 | 10.6606 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
2019-01-05 | 6128.518 | Sat | 5 | 78 | 75 | 0.88945 | 0.21084 | 57.555 | 110.889 | 105.2087 | MLG | 6:51 | 18:32 | 10.6814 | 2.039 | 52.2181 | 348.1204 | 348.1204 | [32 empty] | 0.23164 | 0.54057 | 10.7529 | 9.9807 | 0 | #REF! | #REF!
Note on AE6: Elsa Montagnon: Start at AOS+1hr
Note on AD7: Elsa Montagnon: Including pass sheet update / approval by EM
Note on AA8: Elsa Montagnon: Upcoming pass sheet preparation, to be approved by EM, discuss when to phase in EVFM file
Note on AB8: Elsa Montagnon: Upcoming pass sheet preparation, to be approved by EM, discuss when to phase in EVFM file
Note on A10: Elsa Montagnon: !!! End summer time !!!
Note on AA15: Elsa Montagnon: Planning to be approved by CS
Note on AC18: Elsa Montagnon: Start at AOS+2hr
Note on AA20: Elsa Montagnon: Start at AOS+1hr
Note on AE26: Elsa Montagnon: only for MERTIS activity
Note on AA28: Elsa Montagnon: Planning to be approved by EM
Note on AA36: Elsa Montagnon: Planning to be approved by CS
Note on AD41: Elsa Montagnon: Only for MIXS activities
Note on V42: Elsa Montagnon: OM support requested
Note on Y42: Elsa Montagnon: For LGA beacon test
Note on AI42: Elsa Montagnon: After launch, discuss with FD possibility to phase in this delivery on Monday.
Note on AA43: Elsa Montagnon: Planning to be approved by EM
Note on AC44: Elsa Montagnon: At AOS +1hr
Note on AD44: Elsa Montagnon: Only for MIXS activities
Note on V45: Elsa Montagnon: Double stack day !!
Note on AB51: Elsa Montagnon: Start at AOS+1hr
Note on V52: Elsa Montagnon: OM support requested
Note on V53: Elsa Montagnon: OM support requested
Note on AA54: Elsa Montagnon: Planning to be approved by EM - planning cycle for EPCM1 TBD
Note on AB55: Elsa Montagnon: Start at AOS +2hr

## Outstanding activities
S06 SA flexible modes charact.

## Delayed activities
[5 empty] | HGA |  | AOCS | S10 HGA pattern calibration: slew+WOL | 3 |  | Specific
AOCS | 30m extra margin for AOS activities S10 HGA pattern calibration | 0.50 5.50 |  | Specific | HGA |  | AOCS | S10 HGA pattern calibration: slew+WOL | 3 |  | Specific
AOCS BERM | 30m extra margin for AOS activities S10 HGA pattern calibration | 0.50 1.75 |  | Specific | HGA | [7 empty] | + update slot 10 days afterwards
|  |  |  | Flip-A | HGA |  | AOCS | S11 MGA pattern calibration: slew+WOL | 3 |  | Flip-B Specific (Slew) | X
AOCS | 30m extra margin for AOS activities S11 MGA pattern calibration | 0.50 5.70 |  | Specific | MGA | X | AOCS | S11 MGA pattern calibration: slew+WOL | 3 |  | Specific | X
AOCS | 30m extra margin for AOS activities S11 MGA pattern calibration | 0.50 3.80 |  | Specific | MGA | X |  |  |  |  | y-Sun |  | + update slot 10 days afterwards
[5 empty] | HGA |  | SRN | P38 SRN PICAM MCP/TIMPO - slew | 2.5 |  | Specific (TBC) | X
SRN | P37 PICAM High Voltage Checkout P38 SRN PICAM MCP/TIMPO | 2.00 8.70 |  | Specific (TBC) | HGA | X | SRN | P38 SRN PICAM MCP/TIMPO - slew P40 SRN STROFIO Cathode 1B conversion WOL P40 SRN STROFIO Cathode 1B activation | 3.15 5.00 0.50 4.00 |  | Specific (TBC) | X
SRN | P38 SRN PICAM MCP/TIMPO P40 SRN STROFIO Cathode 1B activation (in parallel to PICAM) | 8.70 (10.00) |  | Specific (TBC) | HGA | X | SRN SIXS | P40 SRN STROFIO Cathode 1B activation WOL P49 SIXS Sun Observation | 2.00 0.50 6.00 |  | Specific (TBC) | X
SRN | P40 STROFIO MCP Commissioning | 2 |  | Flip-A | HGA |  | SRN | P40 SRN STROFIO Cathode 1A conversion P40 SRN STROFIO Cathode 2A conversion | 5.00 5.00 |  | Flip-B
|  |  |  | Flip-A | HGA |  | SRN | P40 SRN STROFIO Cathode 1A activation | 14 |  | Flip-B
SRN | P40 SRN STROFIO Cathode 1A activation | 2 |  | Flip-A | HGA |  | SRN | P40 SRN STROFIO Cathode 2A activation | 14 |  | Flip-B
SRN | P40 SRN STROFIO Cathode 2A activation | 2 |  | Flip-A | HGA | [5 empty] | Flip-B
SRN | P35 SRN ELENA HV ramp P34 SRN ELENA General Check - ASIC test | 7.00 1.00 |  | Flip-A | HGA | [5 empty] | Flip-B
SRN | P34 SRN ELENA General Check - Sector test and data acquisition | 9 |  | Flip-A | HGA | [5 empty] | Flip-B
SRN | P39 MIPA commissioning | 4 |  | Flip-A | HGA | [5 empty] | Flip-B
SRN | P33 SRN DPU initial test - extended test | 9 |  | Flip-A | HGA | [5 empty] | Flip-B
MMO | 1h extra margin for MMO data loss S37 Spacecraft preparation for MMO high voltage test MMO to Cruise standby mode M31 Preparation for MMO mission commissioning M05 COM-TWTA commissioning MDP ON M14 MSASI commissioning (HV) | 1.00 0.10 0.10 1.00 2.00 0.50 3.75 | 0.25 | Flip-A | HGA |  | MMO | M05 COM-TWTA commissioning M06 COM-Other commissioning | 5.00 2.00 2.66 | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M14 MSASI commissioning (HV) | 1.00 8.00 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M14 MSASI commissioning (HV) M19 MPPE ENA com. (HV) | 1.00 5.20 2.33 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M19 MPPE ENA com. (HV) | 1.00 8.26 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M19 MPPE ENA com. (HV) | 1.00 7.20 | 0.25 | Flip-A | HGA |  | MMO | M19 MPPE ENA com. (HV) | 8 | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M17 MPPE MIA com. (HV) | 1.00 8.33 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M17 MPPE MIA com. (HV) M20 MPPE HEP com. (HV) | 1.00 3.20 3.20 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M20 MPPE HEP com. (HV) | 1.00 7.70 | 0.25 | Flip-A | HGA |  | MMO | M20 MPPE HEP com. (HV) | 4.2 | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M15 MPPE MEA1 com. (HV) | 1.00 7.42 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M16 MPPE MEA2 com. (HV) | 1.00 7.42 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M18 MPPE MSA com. (HV) | 1.00 8.70 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
MMO | 1h extra margin for MMO data loss M18 MPPE MSA com. (HV) | 1.00 7.70 | 0.25 | Flip-A | HGA |  | MMO | M18 MPPE MSA com. (HV) | 3.5 | 0.42 | Flip-B
MMO | MMO spare pass MDP OFF MMO to dormant mode S37 Spacecraft preparation for MMO high voltage test - undo | 0.30 0.10 0.10 | 0.25 | Flip-A | HGA |  | MMO |  |  | 0.42 | Flip-B
PHE | P31 PHE High voltage switch-on | 6.5 | 0 | y-Sun&XGA | HGA |  | AOCS | S03 STR Sky Survey - STR1 | 4.4 |  | Specific | X
PHE AOCS | P31 PHE High voltage switch-on S03 STR Sky Survey - swap STR | 5.00 0.10 | 0 | y-Sun&XGA | HGA | X | AOCS | S03 STR Sky Survey - STR3 | 4.4 |  | Specific | X
PHE AOCS | P31 PHE High voltage switch-on S03 STR Sky Survey - swap STR | 5 | 0 | y-Sun&XGA | HGA | X | AOCS | S03 STR Sky Survey - STR2 | 11.25 |  | Specific | X
PHE | P31 PHE High voltage switch-on | 6.5 | 0 | Flip-A | HGA
PHE | P31 PHE High voltage switch-on P32 PHE Nominal Checkout | 4.40 4.00 | 5.6 | Flip-A | HGA
TTC | S28 DST RF power optimization | 9 |  | Flip-A | HGA
TTC | S28 DST RF power optimization (backup) | (9.00) |  | Flip-A | HGA

## GS_VISIBILITY
Date | DOY | Malague (MLG) |  |  |  |  | Cebreros (CEB) |  |  |  |  | New Norcia (NNO)
|  | AOS10 [hh:mm:ss] | LOS10 [hh:mm:ss] | Pass Time [h] | Pass Time [hh:mm:ss] | Dump Time [h] | AOS10 [hh:mm:ss] | LOS10 [hh:mm:ss] | Pass Time [h] | Pass Time [hh:mm:ss] | Dump Time [h] | AOS10 [hh:mm:ss] | LOS10 [hh:mm:ss] | Pass Time [h] | Pass Time [hh:mm:ss] | Dump Time [h]
2018-10-20 | 293 | 10:40 | 21:21 | 10.6814 | 10:41 | 9.6814 | 6:45 | 16:25 | 9.6547 | 9:39 | 8.6547 | 2:25 | 8:32 | 6.125 | 6:08 | 5.125
2018-10-21 | 294 | 10:49 | 21:28 | 10.6361 | 10:38 | 9.6361 | 6:59 | 16:38 | 9.65 | 9:39 | 8.65 | 22:25 | 9:05 | 10.665 | 10:40 | 9.665
2018-10-22 | 295 | 10:48 | 21:27 | 10.6478 | 10:39 | 9.6478 | 6:57 | 16:38 | 9.6847 | 9:41 | 8.6847 | 22:26 | 9:06 | 10.6714 | 10:40 | 9.6714
2018-10-23 | 296 | 10:45 | 21:25 | 10.6569 | 10:39 | 9.6569 | 6:54 | 16:36 | 9.7033 | 9:42 | 8.7033 | 22:24 | 9:04 | 10.6814 | 10:41 | 9.6814
2018-10-24 | 297 | 10:42 | 21:19 | 10.6117 | 10:37 | 9.6117 | 6:51 | 16:34 | 9.7144 | 9:43 | 8.7144 | 22:20 | 9:02 | 10.6883 | 10:41 | 9.6883
2018-10-25 | 298 | 10:38 | 21:19 | 10.6692 | 10:40 | 9.6692 | 6:47 | 16:31 | 9.7208 | 9:43 | 8.7208 | 22:17 | 8:59 | 10.6944 | 10:42 | 9.6944
2018-10-26 | 299 | 10:35 | 21:12 | 10.6172 | 10:37 | 9.6172 | 6:44 | 16:27 | 9.7247 | 9:43 | 8.7247 | 22:14 | 8:55 | 10.6989 | 10:42 | 9.6989
2018-10-27 | 300 | 10:31 | 21:12 | 10.6781 | 10:41 | 9.6781 | 6:40 | 16:24 | 9.7272 | 9:44 | 8.7272 | 22:10 | 8:52 | 10.7031 | 10:42 | 9.7031
2018-10-28 | 301 | 10:27 | 21:08 | 10.6822 | 10:41 | 9.6822 | 6:36 | 16:20 | 9.7281 | 9:44 | 8.7281 | 22:06 | 8:49 | 10.7069 | 10:42 | 9.7069
2018-10-29 | 302 | 10:24 | 21:05 | 10.6875 | 10:41 | 9.6875 | 6:33 | 16:16 | 9.7275 | 9:44 | 8.7275 | 22:02 | 8:45 | 10.7111 | 10:43 | 9.7111
2018-10-30 | 303 | 10:20 | 21:01 | 10.6917 | 10:42 | 9.6917 | 6:29 | 16:13 | 9.7258 | 9:44 | 8.7258 | 21:59 | 8:42 | 10.715 | 10:43 | 9.715
2018-10-31 | 304 | 10:16 | 20:58 | 10.6967 | 10:42 | 9.6967 | 6:26 | 16:09 | 9.7236 | 9:43 | 8.7236 | 21:55 | 8:38 | 10.7194 | 10:43 | 9.7194
2018-11-01 | 305 | 10:12 | 20:54 | 10.7019 | 10:42 | 9.7019 | 6:22 | 16:05 | 9.7203 | 9:43 | 8.7203 | 21:51 | 8:34 | 10.7236 | 10:43 | 9.7236
2018-11-02 | 306 | 10:08 | 20:47 | 10.6475 | 10:39 | 9.6475 | 6:19 | 16:02 | 9.7167 | 9:43 | 8.7167 | 21:47 | 8:31 | 10.7283 | 10:44 | 9.7283
2018-11-03 | 307 | 10:05 | 20:47 | 10.7128 | 10:43 | 9.7128 | 6:15 | 15:58 | 9.7125 | 9:43 | 8.7125 | 21:44 | 8:27 | 10.7325 | 10:44 | 9.7325
2018-11-04 | 308 | 10:01 | 20:44 | 10.7183 | 10:43 | 9.7183 | 6:12 | 15:54 | 9.7069 | 9:42 | 8.7069 | 21:40 | 8:24 | 10.7372 | 10:44 | 9.7372
2018-11-05 | 309 | 9:57 | 20:41 | 10.7244 | 10:43 | 9.7244 | 6:08 | 15:50 | 9.7014 | 9:42 | 8.7014 | 21:36 | 8:21 | 10.7425 | 10:45 | 9.7425
2018-11-06 | 310 | 9:53 | 20:34 | 10.6725 | 10:40 | 9.6725 | 6:05 | 15:46 | 9.695 | 9:42 | 8.695 | 21:32 | 8:17 | 10.7478 | 10:45 | 9.7478
2018-11-07 | 311 | 9:50 | 20:34 | 10.7372 | 10:44 | 9.7372 | 6:01 | 15:43 | 9.6883 | 9:41 | 8.6883 | 21:29 | 8:14 | 10.7533 | 10:45 | 9.7533
2018-11-08 | 312 | 9:46 | 20:30 | 10.7442 | 10:45 | 9.7442 | 5:58 | 15:39 | 9.6811 | 9:41 | 8.6811 | 21:25 | 8:10 | 10.7589 | 10:46 | 9.7589
2018-11-09 | 313 | 9:42 | 20:27 | 10.7517 | 10:45 | 9.7517 | 5:55 | 15:35 | 9.6733 | 9:40 | 8.6733 | 21:21 | 8:07 | 10.765 | 10:46 | 9.765
2018-11-10 | 314 | 9:38 | 20:24 | 10.7594 | 10:46 | 9.7594 | 5:51 | 15:31 | 9.6647 | 9:40 | 8.6647 | 21:17 | 8:04 | 10.7711 | 10:46 | 9.7711
2018-11-11 | 315 | 9:35 | 20:21 | 10.7669 | 10:46 | 9.7669 | 5:48 | 15:28 | 9.6567 | 9:39 | 8.6567 | 21:14 | 8:00 | 10.7778 | 10:47 | 9.7778
2018-11-12 | 316 | 9:31 | 20:17 | 10.7753 | 10:47 | 9.7753 | 5:45 | 15:24 | 9.6469 | 9:39 | 8.6469 | 21:10 | 7:57 | 10.7844 | 10:47 | 9.7844
2018-11-13 | 317 | 9:27 | 20:14 | 10.7839 | 10:47 | 9.7839 | 5:42 | 15:20 | 9.6375 | 9:38 | 8.6375 | 21:06 | 7:54 | 10.7914 | 10:47 | 9.7914
2018-11-14 | 318 | 9:23 | 20:11 | 10.7925 | 10:48 | 9.7925 | 5:39 | 15:16 | 9.6275 | 9:38 | 8.6275 | 21:03 | 7:51 | 10.7986 | 10:48 | 9.7986
2018-11-15 | 319 | 9:20 | 20:08 | 10.8019 | 10:48 | 9.8019 | 5:36 | 15:13 | 9.6169 | 9:37 | 8.6169 | 20:59 | 7:47 | 10.8064 | 10:48 | 9.8064
2018-11-16 | 320 | 9:16 | 20:05 | 10.8117 | 10:49 | 9.8117 | 5:33 | 15:09 | 9.6053 | 9:36 | 8.6053 | 20:55 | 7:44 | 10.8142 | 10:49 | 9.8142
2018-11-17 | 321 | 9:12 | 20:02 | 10.8219 | 10:49 | 9.8219 | 5:30 | 15:05 | 9.5939 | 9:36 | 8.5939 | 20:52 | 7:41 | 10.8231 | 10:49 | 9.8231
2018-11-18 | 322 | 9:09 | 19:59 | 10.8325 | 10:50 | 9.8325 | 5:27 | 15:02 | 9.5814 | 9:35 | 8.5814 | 20:48 | 7:38 | 10.8314 | 10:50 | 9.8314
2018-11-19 | 323 | 9:05 | 19:56 | 10.8431 | 10:51 | 9.8431 | 5:24 | 14:58 | 9.5683 | 9:34 | 8.5683 | 20:45 | 7:35 | 10.8403 | 10:50 | 9.8403
2018-11-20 | 324 | 9:02 | 19:53 | 10.8547 | 10:51 | 9.8547 | 5:21 | 14:54 | 9.555 | 9:33 | 8.555 | 20:41 | 7:32 | 10.8497 | 10:51 | 9.8497
2018-11-21 | 325 | 8:58 | 19:50 | 10.8661 | 10:52 | 9.8661 | 5:18 | 14:51 | 9.5408 | 9:32 | 8.5408 | 20:38 | 7:29 | 10.8594 | 10:52 | 9.8594
2018-11-22 | 326 | 8:55 | 19:47 | 10.8783 | 10:53 | 9.8783 | 5:15 | 14:47 | 9.5264 | 9:32 | 8.5264 | 20:34 | 7:26 | 10.8692 | 10:52 | 9.8692
2018-11-23 | 327 | 8:51 | 19:45 | 10.8908 | 10:53 | 9.8908 | 5:13 | 14:43 | 9.5108 | 9:31 | 8.5108 | 20:31 | 7:24 | 10.8794 | 10:53 | 9.8794
2018-11-24 | 328 | 8:48 | 19:42 | 10.9039 | 10:54 | 9.9039 | 5:10 | 14:40 | 9.4953 | 9:30 | 8.4953 | 20:27 | 7:21 | 10.8903 | 10:53 | 9.8903
2018-11-25 | 329 | 8:44 | 19:39 | 10.9175 | 10:55 | 9.9175 | 5:08 | 14:36 | 9.4789 | 9:29 | 8.4789 | 20:24 | 7:18 | 10.9011 | 10:54 | 9.9011
2018-11-26 | 330 | 8:41 | 19:37 | 10.9314 | 10:56 | 9.9314 | 5:05 | 14:33 | 9.4619 | 9:28 | 8.4619 | 20:21 | 7:15 | 10.9128 | 10:55 | 9.9128
2018-11-27 | 331 | 8:38 | 19:34 | 10.9456 | 10:57 | 9.9456 | 5:03 | 14:29 | 9.4444 | 9:27 | 8.4444 | 20:17 | 7:13 | 10.9244 | 10:55 | 9.9244
2018-11-28 | 332 | 8:34 | 19:32 | 10.9603 | 10:58 | 9.9603 | 5:00 | 14:26 | 9.4261 | 9:26 | 8.4261 | 20:14 | 7:10 | 10.9369 | 10:56 | 9.9369
2018-11-29 | 333 | 8:31 | 19:30 | 10.9753 | 10:59 | 9.9753 | 4:58 | 14:23 | 9.4075 | 9:24 | 8.4075 | 20:11 | 7:08 | 10.9492 | 10:57 | 9.9492
2018-11-30 | 334 | 8:28 | 19:27 | 10.9906 | 10:59 | 9.9906 | 4:56 | 14:19 | 9.3878 | 9:23 | 8.3878 | 20:08 | 7:05 | 10.9617 | 10:58 | 9.9617
2018-12-01 | 335 | 8:24 | 19:25 | 11.0061 | 11:00 | 10.0061 | 4:54 | 14:16 | 9.3681 | 9:22 | 8.3681 | 20:04 | 7:03 | 10.9744 | 10:58 | 9.9744
2018-12-02 | 336 | 8:21 | 19:23 | 11.0222 | 11:01 | 10.0222 | 4:52 | 14:13 | 9.3475 | 9:21 | 8.3475 | 20:01 | 7:01 | 10.9881 | 10:59 | 9.9881
2018-12-03 | 337 | 8:18 | 19:20 | 11.0383 | 11:02 | 10.0383 | 4:50 | 14:09 | 9.3267 | 9:20 | 8.3267 | 19:58 | 6:58 | 11.0014 | 11:00 | 10.0014
2018-12-04 | 338 | 8:15 | 19:18 | 11.0556 | 11:03 | 10.0556 | 4:48 | 14:06 | 9.3053 | 9:18 | 8.3053 | 19:55 | 6:56 | 11.015 | 11:01 | 10.015
2018-12-05 | 339 | 8:12 | 19:16 | 11.0719 | 11:04 | 10.0719 | 4:46 | 14:03 | 9.2833 | 9:17 | 8.2833 | 19:52 | 6:54 | 11.0292 | 11:02 | 10.0292
2018-12-06 | 340 | 8:09 | 19:14 | 11.0894 | 11:05 | 10.0894 | 4:44 | 13:59 | 9.2608 | 9:16 | 8.2608 | 19:49 | 6:52 | 11.0439 | 11:03 | 10.0439
2018-12-07 | 341 | 8:06 | 19:12 | 11.1069 | 11:06 | 10.1069 | 4:42 | 13:56 | 9.2381 | 9:14 | 8.2381 | 19:46 | 6:50 | 11.0581 | 11:03 | 10.0581
2018-12-08 | 342 | 8:03 | 19:10 | 11.1244 | 11:07 | 10.1244 | 4:40 | 13:53 | 9.215 | 9:13 | 8.215 | 19:43 | 6:48 | 11.0725 | 11:04 | 10.0725
2018-12-09 | 343 | 8:00 | 19:08 | 11.1425 | 11:09 | 10.1425 | 4:38 | 13:50 | 9.1911 | 9:11 | 8.1911 | 19:40 | 6:46 | 11.0875 | 11:05 | 10.0875
2018-12-10 | 344 | 7:57 | 19:07 | 11.1606 | 11:10 | 10.1606 | 4:37 | 13:47 | 9.1672 | 9:10 | 8.1672 | 19:37 | 6:44 | 11.1028 | 11:06 | 10.1028
2018-12-11 | 345 | 7:54 | 19:05 | 11.1794 | 11:11 | 10.1794 | 4:35 | 13:44 | 9.1428 | 9:09 | 8.1428 | 19:35 | 6:42 | 11.1181 | 11:07 | 10.1181
2018-12-12 | 346 | 7:51 | 19:03 | 11.1978 | 11:12 | 10.1978 | 4:33 | 13:41 | 9.1175 | 9:07 | 8.1175 | 19:32 | 6:40 | 11.1336 | 11:08 | 10.1336
2018-12-13 | 347 | 7:48 | 19:01 | 11.2167 | 11:13 | 10.2167 | 4:32 | 13:37 | 9.0928 | 9:06 | 8.0928 | 19:29 | 6:38 | 11.1489 | 11:09 | 10.1489
2018-12-14 | 348 | 7:45 | 19:00 | 11.2361 | 11:14 | 10.2361 | 4:30 | 13:34 | 9.0667 | 9:04 | 8.0667 | 19:26 | 6:36 | 11.1647 | 11:10 | 10.1647
2018-12-15 | 349 | 7:43 | 18:58 | 11.255 | 11:15 | 10.255 | 4:29 | 13:31 | 9.0411 | 9:02 | 8.0411 | 19:24 | 6:34 | 11.1806 | 11:11 | 10.1806 | 10.8662
2018-12-16 | 350 | 7:40 | 18:56 | 11.2742 | 11:16 | 10.2742 | 4:28 | 13:28 | 9.0147 | 9:01 | 8.0147 | 19:21 | 6:33 | 11.1964 | 11:12 | 10.1964
2018-12-17 | 351 | 7:37 | 18:55 | 11.2939 | 11:18 | 10.2939 | 4:26 | 13:25 | 8.9881 | 8:59 | 7.9881 | 19:18 | 6:31 | 11.2131 | 11:13 | 10.2131
2018-12-18 | 352 | 7:34 | 18:53 | 11.3133 | 11:19 | 10.3133 | 4:25 | 13:23 | 8.9611 | 8:58 | 7.9611 | 19:16 | 6:29 | 11.2294 | 11:14 | 10.2294
2018-12-19 | 353 | 7:32 | 18:52 | 11.3331 | 11:20 | 10.3331 | 4:24 | 13:20 | 8.9339 | 8:56 | 7.9339 | 19:13 | 6:28 | 11.2453 | 11:15 | 10.2453
2018-12-20 | 354 | 7:29 | 18:50 | 11.3531 | 11:21 | 10.3531 | 4:22 | 13:17 | 8.9069 | 8:54 | 7.9069 | 19:10 | 6:26 | 11.2622 | 11:16 | 10.2622
2018-12-21 | 355 | 7:26 | 18:49 | 11.3731 | 11:22 | 10.3731 | 4:21 | 13:14 | 8.8789 | 8:53 | 7.8789 | 19:08 | 6:25 | 11.2786 | 11:17 | 10.2786
2018-12-22 | 356 | 7:24 | 18:47 | 11.3931 | 11:24 | 10.3931 | 4:20 | 13:11 | 8.8508 | 8:51 | 7.8508 | 19:05 | 6:23 | 11.2953 | 11:18 | 10.2953
2018-12-23 | 357 | 7:21 | 18:46 | 11.4133 | 11:25 | 10.4133 | 4:19 | 13:08 | 8.8225 | 8:49 | 7.8225 | 19:03 | 6:22 | 11.3125 | 11:19 | 10.3125
2018-12-24 | 358 | 7:19 | 18:45 | 11.4336 | 11:26 | 10.4336 | 4:18 | 13:05 | 8.7942 | 8:48 | 7.7942 | 19:00 | 6:20 | 11.3289 | 11:20 | 10.3289
2018-12-25 | 359 | 7:16 | 18:43 | 11.4539 | 11:27 | 10.4539 | 4:17 | 13:03 | 8.7647 | 8:46 | 7.7647 | 18:58 | 6:19 | 11.3461 | 11:21 | 10.3461
2018-12-26 | 360 | 7:14 | 18:42 | 11.475 | 11:28 | 10.475 | 4:16 | 13:00 | 8.7358 | 8:44 | 7.7358 | 18:56 | 6:17 | 11.3631 | 11:22 | 10.3631
2018-12-27 | 361 | 7:11 | 18:41 | 11.495 | 11:30 | 10.495 | 4:15 | 12:57 | 8.7067 | 8:42 | 7.7067 | 18:53 | 6:16 | 11.38 | 11:23 | 10.38
2018-12-28 | 362 | 7:09 | 18:40 | 11.5158 | 11:31 | 10.5158 | 4:14 | 12:55 | 8.6769 | 8:41 | 7.6769 | 18:51 | 6:15 | 11.3969 | 11:24 | 10.3969
2018-12-29 | 363 | 7:07 | 18:39 | 11.5367 | 11:32 | 10.5367 | 4:13 | 12:52 | 8.6472 | 8:39 | 7.6472 | 18:49 | 6:14 | 11.4144 | 11:25 | 10.4144
2018-12-30 | 364 | 7:04 | 18:38 | 11.5569 | 11:33 | 10.5569 | 4:12 | 12:49 | 8.6175 | 8:37 | 7.6175 | 18:46 | 6:12 | 11.4317 | 11:26 | 10.4317
2018-12-31 | 365 | 7:02 | 18:37 | 11.5783 | 11:35 | 10.5783 | 4:12 | 12:47 | 8.5872 | 8:35 | 7.5872 | 18:44 | 6:11 | 11.4486 | 11:27 | 10.4486
2019-01-01 | 1 | 7:00 | 18:36 | 11.5986 | 11:36 | 10.5986 | 4:11 | 12:44 | 8.5569 | 8:33 | 7.5569 | 18:42 | 6:10 | 11.4658 | 11:28 | 10.4658
2019-01-02 | 2 | 6:57 | 18:35 | 11.6194 | 11:37 | 10.6194 | 4:10 | 12:42 | 8.5261 | 8:32 | 7.5261 | 18:40 | 6:09 | 11.4833 | 11:29 | 10.4833
2019-01-03 | 3 | 6:55 | 18:34 | 11.64 | 11:38 | 10.64 | 4:09 | 12:39 | 8.4961 | 8:30 | 7.4961 | 18:38 | 6:08 | 11.5003 | 11:30 | 10.5003
2019-01-04 | 4 | 6:53 | 18:33 | 11.6606 | 11:40 | 10.6606 | 4:09 | 12:37 | 8.4656 | 8:28 | 7.4656 | 18:36 | 6:07 | 11.5178 | 11:31 | 10.5178
2019-01-05 | 5 | 6:51 | 18:32 | 11.6814 | 11:41 | 10.6814 | 4:08 | 12:34 | 8.4344 | 8:26 | 7.4344 | 18:34 | 6:06 | 11.5344 | 11:32 | 10.5344

## Geometry_20Oct2018
Date | DOY | AOS10 [hh:mm:ss] | LOS10 [hh:mm:ss] | Pass Time [h] | Pass Time [hh:mm:ss] | Dump Time [h] | Duration [sec] | Distance | r_e [AU] | OWLT [sec] | RangeRate | SCDeclination | SCHourAngle | SESC | SSCE | SUN_DIS | ¦r¦ in [AU]
2018-10-20 | 293 | 10:40 | 21:21 | 10.6814 | 10:41 | 9.6814 | 38453 | 152093 | 0.0010167 | 0.50733 | 4.127 | -4.246 | 282.186 | 9.752 | 170.238 | 148977949.959 | 0.99586
2018-10-21 | 294 | 10:49 | 21:28 | 10.6361 | 10:38 | 9.6361 | 38290 | 485623 | 0.0032462 | 1.6199 | 3.6996 | -3.886 | 280.438 | 7.661 | 172.314 | 148470071.554 | 0.99246
2018-10-22 | 295 | 10:48 | 21:27 | 10.6478 | 10:39 | 9.6478 | 38332 | 800907 | 0.0053537 | 2.6715 | 3.6197 | -3.814 | 280.135 | 8.031 | 171.925 | 148158162.911 | 0.99038
2018-10-23 | 296 | 10:45 | 21:25 | 10.6569 | 10:39 | 9.6569 | 38365 | 1111596 | 0.0074306 | 3.7079 | 3.5907 | -3.785 | 279.998 | 8.607 | 171.329 | 147859626.279 | 0.98838
2018-10-24 | 297 | 10:42 | 21:22 | 10.6636 | 10:40 | 9.6636 | 38389 | 1420587 | 0.009496 | 4.7386 | 3.5804 | -3.774 | 279.922 | 9.266 | 170.645 | 147587352.609 | 0.98656
2018-10-25 | 298 | 10:38 | 21:19 | 10.6692 | 10:40 | 9.6692 | 38409 | 1729099 | 0.011558 | 5.7677 | 3.5799 | -3.773 | 279.866 | 9.978 | 169.905 | 147341487.498 | 0.98492
2018-10-26 | 299 | 10:35 | 21:15 | 10.6742 | 10:40 | 9.6742 | 38427 | 2037822 | 0.013622 | 6.7975 | 3.5855 | -3.78 | 279.819 | 10.729 | 169.123 | 146700817.752 | 0.98063
2018-10-27 | 300 | 10:31 | 21:12 | 10.6781 | 10:41 | 9.6781 | 38441 | 2347211 | 0.01569 | 7.8295 | 3.5954 | -3.793 | 279.781 | 11.508 | 168.309 | 146315896.256 | 0.97806
2018-10-28 | 301 | 10:27 | 21:08 | 10.6822 | 10:41 | 9.6822 | 38456 | 2657590 | 0.017765 | 8.8648 | 3.6085 | -3.811 | 279.75 | 12.308 | 167.47 | 145967687.012 | 0.97573
2018-10-29 | 302 | 10:24 | 21:05 | 10.6875 | 10:41 | 9.6875 | 38475 | 2969198 | 0.019848 | 9.9042 | 3.6241 | -3.835 | 279.712 | 13.123 | 166.612 | 145656453.314 | 0.97365
2018-10-30 | 303 | 10:20 | 21:01 | 10.6917 | 10:42 | 9.6917 | 38490 | 3282245 | 0.02194 | 10.9484 | 3.6417 | -3.863 | 279.68 | 13.95 | 165.739 | 145382432.633 | 0.97182
2018-10-31 | 304 | 10:16 | 20:58 | 10.6967 | 10:42 | 9.6967 | 38508 | 3596885 | 0.024044 | 11.9979 | 3.6612 | -3.897 | 279.641 | 14.785 | 164.853 | 145145835.734 | 0.97024
2018-11-01 | 305 | 10:12 | 20:54 | 10.7019 | 10:42 | 9.7019 | 38527 | 3913274 | 0.026159 | 13.0533 | 3.6822 | -3.934 | 279.604 | 15.626 | 163.957 | 144785618.121 | 0.96783
2018-11-02 | 306 | 10:08 | 20:51 | 10.7069 | 10:42 | 9.7069 | 38545 | 4231546 | 0.028286 | 14.1149 | 3.7048 | -3.977 | 279.568 | 16.471 | 163.053 | 144272638.58 | 0.9644
2018-11-03 | 307 | 10:05 | 20:47 | 10.7128 | 10:43 | 9.7128 | 38566 | 4551820 | 0.030427 | 15.1833 | 3.7288 | -4.023 | 279.525 | 17.319 | 162.142 | 143805735.973 | 0.96128
2018-11-04 | 308 | 10:01 | 20:44 | 10.7183 | 10:43 | 9.7183 | 38586 | 4874234 | 0.032582 | 16.2587 | 3.7544 | -4.073 | 279.484 | 18.169 | 161.226 | 143385360.418 | 0.95847
2018-11-05 | 309 | 9:57 | 20:41 | 10.7244 | 10:43 | 9.7244 | 38608 | 5198919 | 0.034753 | 17.3418 | 3.7815 | -4.127 | 279.44 | 19.019 | 160.304 | 143011922.207 | 0.95598
2018-11-06 | 310 | 9:53 | 20:37 | 10.7308 | 10:44 | 9.7308 | 38631 | 5526015 | 0.036939 | 18.4328 | 3.8103 | -4.185 | 279.394 | 19.87 | 159.378 | 142685789.874 | 0.9538
2018-11-07 | 311 | 9:50 | 20:34 | 10.7372 | 10:44 | 9.7372 | 38654 | 5855670 | 0.039143 | 19.5324 | 3.8409 | -4.247 | 279.345 | 20.72 | 158.449 | 142407288.431 | 0.95193
2018-11-08 | 312 | 9:46 | 20:30 | 10.7442 | 10:45 | 9.7442 | 38679 | 6188039 | 0.041364 | 20.6411 | 3.8733 | -4.312 | 279.294 | 21.569 | 157.516 | 142176697.781 | 0.95039
2018-11-09 | 313 | 9:42 | 20:27 | 10.7517 | 10:45 | 9.7517 | 38706 | 6523281 | 0.043605 | 21.7594 | 3.9075 | -4.38 | 279.24 | 22.416 | 156.581 | 141994251.34 | 0.94917
2018-11-10 | 314 | 9:38 | 20:24 | 10.7594 | 10:46 | 9.7594 | 38734 | 6861556 | 0.045867 | 22.8877 | 3.9437 | -4.453 | 279.184 | 23.261 | 155.645 | 141860134.86 | 0.94828
2018-11-11 | 315 | 9:35 | 20:21 | 10.7669 | 10:46 | 9.7669 | 38761 | 7203030 | 0.048149 | 24.0268 | 3.9816 | -4.529 | 279.13 | 24.102 | 154.708 | 141774485.502 | 0.9477
2018-11-12 | 316 | 9:31 | 20:17 | 10.7753 | 10:47 | 9.7753 | 38791 | 7547847 | 0.050454 | 25.1769 | 4.0213 | -4.608 | 279.068 | 24.939 | 153.77 | 141280270.787 | 0.9444
2018-11-13 | 317 | 9:27 | 20:14 | 10.7839 | 10:47 | 9.7839 | 38822 | 7896160 | 0.052783 | 26.3388 | 4.0626 | -4.692 | 279.004 | 25.772 | 152.833 | 140835081.147 | 0.94142
2018-11-14 | 318 | 9:23 | 20:11 | 10.7925 | 10:48 | 9.7925 | 38853 | 8248116 | 0.055135 | 27.5128 | 4.1056 | -4.779 | 278.943 | 26.599 | 151.897 | 140439382.807 | 0.93878
2018-11-15 | 319 | 9:20 | 20:08 | 10.8019 | 10:48 | 9.8019 | 38887 | 8603837 | 0.057513 | 28.6994 | 4.15 | -4.871 | 278.873 | 27.42 | 150.963 | 140093595.137 | 0.93647
2018-11-16 | 320 | 9:16 | 20:05 | 10.8117 | 10:49 | 9.8117 | 38922 | 8963454 | 0.059917 | 29.8989 | 4.1958 | -4.967 | 278.806 | 28.235 | 150.031 | 139798088.495 | 0.93449
2018-11-17 | 321 | 9:12 | 20:02 | 10.8219 | 10:49 | 9.8219 | 38959 | 9327069 | 0.062348 | 31.1118 | 4.2428 | -5.066 | 278.731 | 29.042 | 149.102 | 139553182.297 | 0.93286
2018-11-18 | 322 | 9:09 | 19:59 | 10.8325 | 10:50 | 9.8325 | 38997 | 9694788 | 0.064806 | 32.3384 | 4.2909 | -5.171 | 278.652 | 29.842 | 148.177 | 139359143.314 | 0.93156
2018-11-19 | 323 | 9:05 | 19:56 | 10.8431 | 10:51 | 9.8431 | 39035 | 10066705 | 0.067292 | 33.579 | 4.3399 | -5.279 | 278.576 | 30.634 | 147.256 | 139216184.241 | 0.9306
2018-11-20 | 324 | 9:02 | 19:53 | 10.8547 | 10:51 | 9.8547 | 39077 | 10442882 | 0.069806 | 34.8338 | 4.3897 | -5.392 | 278.492 | 31.416 | 146.339 | 139124462.542 | 0.92999
2018-11-21 | 325 | 8:58 | 19:50 | 10.8661 | 10:52 | 9.8661 | 39118 | 10823388 | 0.07235 | 36.103 | 4.44 | -5.509 | 278.41 | 32.19 | 145.428 | 139084079.586 | 0.92972
2018-11-22 | 326 | 8:55 | 19:47 | 10.8783 | 10:53 | 9.8783 | 39162 | 11208252 | 0.074923 | 37.3868 | 4.4907 | -5.631 | 278.319 | 32.954 | 144.523 | 138619965.966 | 0.92662
2018-11-23 | 327 | 8:51 | 19:45 | 10.8908 | 10:53 | 9.8908 | 39207 | 11597502 | 0.077525 | 38.6852 | 4.5414 | -5.757 | 278.231 | 33.708 | 143.623 | 138207716.805 | 0.92386
2018-11-24 | 328 | 8:48 | 19:42 | 10.9039 | 10:54 | 9.9039 | 39254 | 11991122 | 0.080156 | 39.9981 | 4.592 | -5.888 | 278.134 | 34.452 | 142.73 | 137847797.422 | 0.92146
2018-11-25 | 329 | 8:44 | 19:39 | 10.9175 | 10:55 | 9.9175 | 39303 | 12389090 | 0.082816 | 41.3256 | 4.6421 | -6.024 | 278.034 | 35.185 | 141.843 | 137540618.632 | 0.9194
2018-11-26 | 330 | 8:41 | 19:37 | 10.9314 | 10:56 | 9.9314 | 39353 | 12791366 | 0.085505 | 42.6675 | 4.6916 | -6.164 | 277.936 | 35.908 | 140.964 | 137085840.121 | 0.91636
2018-11-27 | 331 | 8:38 | 19:34 | 10.9456 | 10:57 | 9.9456 | 39404 | 13197873 | 0.088222 | 44.0234 | 4.7402 | -6.308 | 277.83 | 36.62 | 140.091 | 136938770.369 | 0.91538
2018-11-28 | 332 | 8:34 | 19:32 | 10.9603 | 10:58 | 9.9603 | 39457 | 13608550 | 0.090968 | 45.3933 | 4.7879 | -6.457 | 277.726 | 37.322 | 139.226 | 136845498.094 | 0.91476
2018-11-29 | 333 | 8:31 | 19:30 | 10.9753 | 10:59 | 9.9753 | 39511 | 14023304 | 0.09374 | 46.7768 | 4.8347 | -6.609 | 277.614 | 38.013 | 138.367 | 136806133.33 | 0.91449
2018-11-30 | 334 | 8:28 | 19:27 | 10.9906 | 10:59 | 9.9906 | 39566 | 14442064 | 0.096539 | 48.1736 | 4.8805 | -6.766 | 277.504 | 38.694 | 137.516 | 136820722.606 | 0.91459
2018-12-01 | 335 | 8:24 | 19:25 | 11.0061 | 11:00 | 10.0061 | 39622 | 14864739 | 0.099365 | 49.5835 | 4.9255 | -6.927 | 277.387 | 39.364 | 136.671 | 136398372.877 | 0.91177
2018-12-02 | 336 | 8:21 | 19:23 | 11.0222 | 11:01 | 10.0222 | 39680 | 15291266 | 0.10222 | 51.0063 | 4.9696 | -7.092 | 277.272 | 40.025 | 135.833 | 136030430.642 | 0.90931
2018-12-03 | 337 | 8:18 | 19:20 | 11.0383 | 11:02 | 10.0383 | 39738 | 15721569 | 0.10509 | 52.4416 | 5.0129 | -7.26 | 277.154 | 40.676 | 135.001 | 135717338.413 | 0.90721
2018-12-04 | 338 | 8:15 | 19:18 | 11.0556 | 11:03 | 10.0556 | 39800 | 16155578 | 0.10799 | 53.8893 | 5.0555 | -7.432 | 277.029 | 41.317 | 134.175 | 135459476.521 | 0.90549
2018-12-05 | 339 | 8:12 | 19:16 | 11.0719 | 11:04 | 10.0719 | 39859 | 16593248 | 0.11092 | 55.3492 | 5.0974 | -7.606 | 276.906 | 41.95 | 133.356 | 135257160.849 | 0.90414
2018-12-06 | 340 | 8:09 | 19:14 | 11.0894 | 11:05 | 10.0894 | 39922 | 17034511 | 0.11387 | 56.8211 | 5.1388 | -7.784 | 276.777 | 42.573 | 132.542 | 135110640.922 | 0.90316
2018-12-07 | 341 | 8:06 | 19:12 | 11.1069 | 11:06 | 10.1069 | 39985 | 17479331 | 0.11684 | 58.3049 | 5.1796 | -7.965 | 276.65 | 43.188 | 131.735 | 135020098.385 | 0.90255
2018-12-08 | 342 | 8:03 | 19:10 | 11.1244 | 11:07 | 10.1244 | 40048 | 17927649 | 0.11984 | 59.8003 | 5.2198 | -8.149 | 276.521 | 43.794 | 130.933 | 134985645.88 | 0.90232
2018-12-09 | 343 | 8:00 | 19:08 | 11.1425 | 11:09 | 10.1425 | 40113 | 18379409 | 0.12286 | 61.3072 | 5.2593 | -8.335 | 276.386 | 44.391 | 130.137 | 135007326.348 | 0.90247
2018-12-10 | 344 | 7:57 | 19:07 | 11.1606 | 11:10 | 10.1606 | 40178 | 18834567 | 0.1259 | 62.8254 | 5.2982 | -8.524 | 276.254 | 44.979 | 129.347 | 135085112.76 | 0.90299
2018-12-11 | 345 | 7:54 | 19:05 | 11.1794 | 11:11 | 10.1794 | 40246 | 19293053 | 0.12897 | 64.3548 | 5.3364 | -8.715 | 276.115 | 45.559 | 128.563 | 134715468.172 | 0.90052
2018-12-12 | 346 | 7:51 | 19:03 | 11.1978 | 11:12 | 10.1978 | 40312 | 19754812 | 0.13205 | 65.8951 | 5.3738 | -8.909 | 275.979 | 46.131 | 127.784 | 134402270.41 | 0.89842
2018-12-13 | 347 | 7:48 | 19:01 | 11.2167 | 11:13 | 10.2167 | 40380 | 20219766 | 0.13516 | 67.446 | 5.4103 | -9.105 | 275.842 | 46.695 | 127.011 | 134145914.844 | 0.89671
2018-12-14 | 348 | 7:45 | 19:00 | 11.2361 | 11:14 | 10.2361 | 40450 | 20687827 | 0.13829 | 69.0073 | 5.4458 | -9.303 | 275.699 | 47.25 | 126.245 | 133946727.838 | 0.89538
2018-12-15 | 349 | 7:43 | 18:58 | 11.255 | 11:15 | 10.255 | 40518 | 21158929 | 0.14144 | 70.5787 | 5.481 | -9.503 | 275.558 | 47.796 | 125.484 | 133804964.703 | 0.89443
2018-12-16 | 350 | 7:40 | 18:56 | 11.2742 | 11:16 | 10.2742 | 40587 | 21633155 | 0.14461 | 72.1605 | 5.5174 | -9.705 | 275.417 | 48.335 | 124.729 | 133720808.071 | 0.89387
2018-12-17 | 351 | 7:37 | 18:55 | 11.2939 | 11:18 | 10.2939 | 40658 | 22110479 | 0.1478 | 73.7527 | 5.5527 | -9.909 | 275.27 | 48.866 | 123.979 | 133694366.726 | 0.89369
2018-12-18 | 352 | 7:34 | 18:53 | 11.3133 | 11:19 | 10.3133 | 40728 | 22590800 | 0.15101 | 75.3549 | 5.5865 | -10.114 | 275.127 | 49.389 | 123.236 | 133725674.906 | 0.8939
2018-12-19 | 353 | 7:32 | 18:52 | 11.3331 | 11:20 | 10.3331 | 40799 | 23073986 | 0.15424 | 76.9667 | 5.6189 | -10.32 | 274.982 | 49.904 | 122.498 | 133814692.074 | 0.8945
2018-12-20 | 354 | 7:29 | 18:50 | 11.3531 | 11:21 | 10.3531 | 40871 | 23559893 | 0.15749 | 78.5875 | 5.6495 | -10.528 | 274.832 | 50.411 | 121.766 | 133961303.19 | 0.89548
2018-12-21 | 355 | 7:26 | 18:49 | 11.3731 | 11:22 | 10.3731 | 40943 | 24048377 | 0.16075 | 80.2169 | 5.6782 | -10.737 | 274.686 | 50.91 | 121.041 | 133653503.568 | 0.89342
2018-12-22 | 356 | 7:24 | 18:47 | 11.3931 | 11:24 | 10.3931 | 41015 | 24539257 | 0.16403 | 81.8543 | 5.7048 | -10.947 | 274.539 | 51.402 | 120.322 | 133403491.824 | 0.89175
2018-12-23 | 357 | 7:21 | 18:46 | 11.4133 | 11:25 | 10.4133 | 41088 | 25032332 | 0.16733 | 83.499 | 5.729 | -11.158 | 274.386 | 51.886 | 119.608 | 133211593.327 | 0.89046
2018-12-24 | 358 | 7:19 | 18:45 | 11.4336 | 11:26 | 10.4336 | 41161 | 25527401 | 0.17064 | 85.1504 | 5.7506 | -11.371 | 274.237 | 52.362 | 118.902 | 133003066.061 | 0.88907
2018-12-25 | 359 | 7:16 | 18:43 | 11.4539 | 11:27 | 10.4539 | 41234 | 26024229 | 0.17396 | 86.8076 | 5.7695 | -11.585 | 274.088 | 52.831 | 118.201 | 132986712.12 | 0.88896
2018-12-26 | 360 | 7:14 | 18:42 | 11.475 | 11:28 | 10.475 | 41310 | 26522575 | 0.17729 | 88.4699 | 5.7857 | -11.799 | 273.933 | 53.292 | 117.507 | 133029019.28 | 0.88924
2018-12-27 | 361 | 7:11 | 18:41 | 11.495 | 11:30 | 10.495 | 41382 | 27022212 | 0.18063 | 90.1365 | 5.7991 | -12.014 | 273.782 | 53.746 | 116.819 | 133129931.614 | 0.88992
2018-12-28 | 362 | 7:09 | 18:40 | 11.5158 | 11:31 | 10.5158 | 41457 | 27522895 | 0.18398 | 91.8066 | 5.8098 | -12.23 | 273.628 | 54.194 | 116.137 | 133289316.015 | 0.89098
2018-12-29 | 363 | 7:07 | 18:39 | 11.5367 | 11:32 | 10.5367 | 41532 | 28024403 | 0.18733 | 93.4795 | 5.8179 | -12.447 | 273.477 | 54.634 | 115.462 | 133506963.065 | 0.89244
2018-12-30 | 364 | 7:04 | 18:38 | 11.5569 | 11:33 | 10.5569 | 41605 | 28526513 | 0.19069 | 95.1544 | 5.8235 | -12.664 | 273.325 | 55.069 | 114.792 | 133267329.653 | 0.89084
2018-12-31 | 365 | 7:02 | 18:37 | 11.5783 | 11:35 | 10.5783 | 41682 | 29029010 | 0.19405 | 96.8305 | 5.8268 | -12.881 | 273.167 | 55.497 | 114.127 | 133085984.589 | 0.88962
2019-01-01 | 1 | 7:00 | 18:36 | 11.5986 | 11:36 | 10.5986 | 41755 | 29531708 | 0.19741 | 98.5073 | 5.8278 | -13.098 | 273.015 | 55.919 | 113.469 | 132963166.367 | 0.8888
2019-01-02 | 2 | 6:57 | 18:35 | 11.6194 | 11:37 | 10.6194 | 41830 | 30034410 | 0.20077 | 100.1842 | 5.8267 | -13.315 | 272.862 | 56.336 | 112.816 | 132899037.25 | 0.88838
2019-01-03 | 3 | 6:55 | 18:34 | 11.64 | 11:38 | 10.64 | 41904 | 30536933 | 0.20413 | 101.8604 | 5.8234 | -13.532 | 272.71 | 56.748 | 112.168 | 132893682.199 | 0.88834
2019-01-04 | 4 | 6:53 | 18:33 | 11.6606 | 11:40 | 10.6606 | 41978 | 31039098 | 0.20748 | 103.5354 | 5.8182 | -13.748 | 272.557 | 57.154 | 111.526 | 132947108.318 | 0.8887
2019-01-05 | 5 | 6:51 | 18:32 | 11.6814 | 11:41 | 10.6814 | 42053 | 31540729 | 0.21084 | 105.2087 | 5.811 | -13.964 | 272.4 | 57.555 | 110.889 | 133059244.801 | 0.88945

## SUPPORT INFO
HGA-X/Cebr./Turbo1/4 |  |  | MGA/Cebr./Turbo1/4 |  |  | HGA-Ka/Cebr./Turbo1/4 |  |  | Swing-by Dates
Bitrate [bps] | Bitrate [kbps] | r_e [AU] | Bitrate [bps] | Bitrate [kbps] | r_e [AU] | Bitrate [bps] | Bitrate [kbps] | r_e [AU] | Planet | Date
348120.375 | 348.1204 | 0.5394 | 348120.375 | 348.1204 | 0.0866 | 348120.375 | 348.1204 | 0.5388 | Earth | 2020-04-06
261090.2656 | 261.0903 | 0.6228 | 261090.2656 | 261.0903 | 0.1 | 261090.2656 | 261.0903 | 0.6221 | Venus 1 | 2020-10-12
208872.2188 | 208.8722 | 0.6964 | 208872.2188 | 208.8722 | 0.1118 | 208872.2188 | 208.8722 | 0.6956 | Venus 2 | 2021-08-11
174060.1875 | 174.0602 | 0.7628 | 174060.1875 | 174.0602 | 0.1225 | 174060.1875 | 174.0602 | 0.762 | Mercury 1 | 2021-10-02
130545.1328 | 130.5451 | 0.8808 | 130545.1328 | 130.5451 | 0.1415 | 130545.1328 | 130.5451 | 0.8799 | Mercury 2 | 2022-06-23
104436.1094 | 104.4361 | 0.9848 | 104436.1094 | 104.4361 | 0.1582 | 104436.1094 | 104.4361 | 0.9838 | Mercury 3 | 2023-06-20
87030.0938 | 87.0301 | 1.0788 | 87030.0938 | 87.0301 | 0.1733 | 87030.0938 | 87.0301 | 1.0777 | Mercury 4 | 2024-09-05
65272.5664 | 65.2726 | 1.2457 | 65272.5664 | 65.2726 | 0.2001 | 65272.5664 | 65.2726 | 1.2443 | Mercury 5 | 2025-01-09
52218.0547 | 52.2181 | 1.3928 | 52218.0547 | 52.2181 | 0.2237 | 52218.0547 | 52.2181 | 1.3913
43515.0469 | 43.515 | 1.5257 | 43515.0469 | 43.515 | 0.245 | 43515.0469 | 43.515 | 1.524
32636.2832 | 32.6363 | 1.7617 | 32636.2832 | 32.6363 | 0.283 | 32636.2832 | 32.6363 | 1.7597
26109.0273 | 26.109 | 1.9697 | 26109.0273 | 26.109 | 0.3164 | 26109.0273 | 26.109 | 1.9675
21757.5234 | 21.7575 | 2.1577 | 21757.5234 | 21.7575 | 0.3466 | 21757.5234 | 21.7575 | 2.1553
16318.1416 | 16.3181 | 2.4914 | 16318.1416 | 16.3181 | 0.4002 | 16318.1416 | 16.3181 | 2.4887
13054.5137 | 13.0545 | 2.7856 | 13054.5137 | 13.0545 | 0.4474 | 13054.5137 | 13.0545 | 2.7825
10878.7617 | 10.8788 | 3.0515 | 10878.7617 | 10.8788 | 0.4901 | 10878.7617 | 10.8788 | 3.0481
8159.0708 | 8.1591 | 3.5234 | 8159.0708 | 8.1591 | 0.5659 | 8159.0708 | 8.1591 | 3.5195
6527.2568 | 6.5273 | 3.9394 | 6527.2568 | 6.5273 | 0.6328 | 6527.2568 | 6.5273 | 3.9351
5439.3809 | 5.4394 | 4.3154 | 5439.3809 | 5.4394 | 0.6932 | 5439.3809 | 5.4394 | 4.3107
4079.5354 | 4.0795 | 4.9828 | 4079.5354 | 4.0795 | 0.8004 | 4079.5354 | 4.0795 | 4.9773
3263.6284 | 3.2636 | 5.5712 | 3263.6284 | 3.2636 | 0.8949 | 3263.6284 | 3.2636 | 5.4172
2719.6902 | 2.7197 | 6.103 | 2719.6902 | 2.7197 | 0.9803 | 2719.6902 | 2.7197 | 5.4172
2039.7678 | 2.0398 | 7.0468 | 2039.7678 | 2.0398 | 1.1319 | 2039.7678 | 2.0398 | 6.2416
1631.8142 | 1.6318 | 7.6694 | 1631.8142 | 1.6318 | 1.256 | 1631.8142 | 1.6318 | 6.9786
1359.8452 | 1.3598 | 7.6694 | 1359.8452 | 1.3598 | 1.3864 | 1359.8452 | 1.3598 | 7.6447
1019.8839 | 1.0199 | 8.8366 | 1019.8839 | 1.0199 | 1.4812 | 1019.8839 | 1.0199 | 8.8269
815.9071 | 0.81591 | 9.8801 | 815.9071 | 0.81591 | 1.5869 | 815.9071 | 0.81591 | 9.2831
679.9226 | 0.67992 | 10.8231 | 679.9226 | 0.67992 | 1.7385 | 679.9226 | 0.67992 | 9.2831
509.9419 | 0.50994 | 12.4968 | 509.9419 | 0.50994 | 2.0074 | 509.9419 | 0.50994 | 10.1114
407.9536 | 0.40795 | 13.1427 | 407.9536 | 0.40795 | 2.2444 | 407.9536 | 0.40795 | 11.3061
339.9613 | 0.33996 | 13.1427 | 339.9613 | 0.33996 | 2.4586 | 339.9613 | 0.33996 | 12.3853
254.971 | 0.25497 | 14.3154 | 254.971 | 0.25497 | 2.5382 | 254.971 | 0.25497 | 12.5712
169.9806 | 0.16998 | 17.5346 | 169.9806 | 0.16998 | 2.8166 | 169.9806 | 0.16998 | 12.5712
127.4855 | 0.12749 | 17.7979 | 127.4855 | 0.12749 | 3.2522 | 127.4855 | 0.12749 | 14.225
84.9903 | 0.08499 | 17.7979 | 84.9903 | 0.08499 | 3.4372 | 84.9903 | 0.08499 | 15.0779
63.7427 | 0.063743 | 20.1393 | 63.7427 | 0.063743 | 3.4372 | 63.7427 | 0.063743 | 15.0779
42.4952 | 0.042495 | 21.3468 | 42.4952 | 0.042495 | 3.9619 | 42.4952 | 0.042495 | 15.0779
31.8714 | 0.031871 | 21.3468 | 31.8714 | 0.031871 | 4.1226 | 31.8714 | 0.031871 | 15.0779
21.2476 | 0.021248 | 21.3468 | 21.2476 | 0.021248 | 4.1226 | 21.2476 | 0.021248 | 16.6475
15.9357 | 0.015936 | 21.3468 | 15.9357 | 0.015936 | 4.1226 | 15.9357 | 0.015936 | 16.6475
10.6238 | 0.010624 | 23.5691 | 10.6238 | 0.010624 | 4.1226 | 10.6238 | 0.010624 | 16.6475

## Data Volume
PS ID | PS size [Gbit] | Contents | Max DV per day | Comments
20 | 3 | ISA | 800 Mbit | PI input for performance test; Parallel PL ON (1542.4 bps) = 127 Mbit per day
21 | 3.5 | BELA | 3 Gbit | PI input for 6 hours of BELA commissioning
22 | 4 | MPO-MAG | 105 Mbit | MPO-MAG around boom deployment: 49.6 bps (1Hz) for max 24 hours before, 12704 bps (128Hz) for 2 hours, 49.6 bps (1Hz) for 24 hours; Parallel PL ON (49.6 bps) = 4.1 Mbit per day
23 | 10 | MERTIS | 9.7 Gbit | Detailed analysis based on commissioning activites
24 | 0.4 | MGNS | 287 Mbit | Data generation rate every 20 sec for 8 hours at 3.4 kbps = 95.6 Mbit Parallel PL ON (3.4 kbps) = 287 Mbit per day
25 | 2 | MIXS | 717 Mbit | 8700 bps avg rate for 8 hours = 239 Mbit Parallel PL ON (8700 bps) = 717 Mbit per day
26 | 5.7 | PHEBUS | 5.6 Gbit | PI input for 4 x 40 min observations on last PHEBUS day
27 | 6 | SERENA | 1.2 Gbit PICAM | PI input 3.6 Gbit for 3 days Others are TBD
28 | 10 | SIMBIO HRIC | 7.1 Gbit | Estimate of total data volume for HRIC channel performance test
29 | 3.5 | SIMBIO VIHI | 3 Gbit | Estimate of total data volume for VIHI channel performance test
30 | 13 | SIMBIO STC | 12.5 Gbit | Estimate of total data volume, including Orb simulation and STC channel performance test
31 | 0.5 | SIXS | 44 Mbit | 543 bps for 24 hours = 44 Mbit per day Parallel PL ON (543 bps) = 44 Mbit per day
32 | 0.2 | BERM |  | very little science data, not calculated
33 | 0.2 | MORE |  | very little HK data, not calculated
34 | 1 | MMO | 675 Mbit | 8 kbps fixed rate for 24h = 675 Mbit
35 | 3.8 | PL Aux | 225 Mbit | 2739 bps ISA for 24h = 225 Mbit 528 bps MORE for 10 hours = 18 Mbit
36 | 3 | Ka-Band | 24 Mbit | MGNS Data generation rate every 20 sec for 2 hours at 3.4 kbps = 24 Mbit